## DRS
Daily Record Sheet
Date | 1.10.16 |  |  | DRS Format Rev: |  | J | [6 empty] | Instrumentation Works |  |  |  |  | Site Instruction or Event | [10 empty] | OFFICE USE ONLY
Area Superintendent: |  |  |  | Area: |  | CIVILS | [6 empty] | Electrical Works | [15 empty] | DRS Populated by
Superintendent: | Andrew Skinley |  |  | Signature | [8 empty] | Communications Works | [15 empty] | Signature
Supervisor: | Craig Butler, Michael Horton |  |  | Signature |  | CJ Butler | [6 empty] | Preservation/Commissioning Support & LTSC | [15 empty] | Date Completed
Commerical / QS: |  |  |  | Signature | [8 empty] | Indirect Works | [5 empty] | A1BH | A2BA | A1ED | A2BC | A1BG
Important Notes: 1. If Constrained Hours are reported full details must be given to the Area QS for verification and for onward Client reporting purposes. If no details are provided these hours will not be considered constrained or taken into account for internal P/F Calculation purposes 2. Additional or non-scope Works may only be undertaken and reported under a Site Instruction or Event Number, any other hours reported for additional Works which do not reference an SI or Event Number will be reallocated to Scope Work. Area QS will provide Event Number when required 3. All hours reported for Additional Works or non-scope Works must be captured on a Daywork Sheet and presented to the Client for approval. Please include details of the SI and Daywork Sheet No. at the bottom of the DRS in order that the Commercial Dept. can track what Daywork Sheets remain outstanding for each SI / Event 4. If an Employee is not on site mark an "X" in the absent column. | [12 empty] | 8295A - Excavation | 8295B - Sand Filling | 8295C - Back Filling | 8295G - Disposal | 8297 - Minor Foundations | Site Facilities & Services | SI # | SI # | SI # | SI # | SI # | SI # | SI # | SI # | EV # | EV # | Total Checks
[20 empty] | 1288 | 711 | 1288 | 711
Name | Employee Number | Classification |  | Crew | SubCrew Grouping | Area if different | Company | Start | Finish | Total Hours | Absent | Comments | Above cells are for entry of FWBS Activities or Additional / Non Scope Activities If an SI or EV is selected Manually insert SI or EV number in cell directly below this selection | [15 empty] | Total | Check | Description of Work
Abbott, William | 50443 | Electrician - STD |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Abbottsmith, James | 56269 | Electrician - STD |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Adams, Christopher | 55239 | Electrician - STD |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Aliakbar, Ashkan | 56107 | Electrician - STD |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Alley, Riley | 54901 | Elect Apprentice 1st Year |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Allinson, Lee | 55660 | Electrician - STD |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Allwood, Tony | 54802 | Boilermaker Welder |  | Fab Shop |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Alpen, Link | 54609 | Boilermaker Welder |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Amaya, Jorge | 55685 | Electrician - STD |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Amos, Graham | 54034 | Instrument Technician |  | Temps |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Andersen, Will | 56470 | Electrical Mechanic Certified |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Anderson, Gavin | 55802 | Storeperson |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Andrews, Ian | 56055 | Electrician - STD |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Anker, Christan | 50539 | Electrician - STD |  | Comm LV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Arentsen, Dale | 55815 | Electrician - STD |  | Temps |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Argote, Gus | 54689 | Electrician - STD |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Arkinstall, Damien | 54908 | Elect Apprentice 1st Year |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Arnold, Craig | 56061 | Electrician - STD |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Backhouse, Travis | 55861 | Electrician - STD |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Baggott, Adam | 55521 | Trade Assistant |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Baharuddin, Zabedah | 56464 | Electrical Apprentice |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Baird, Peter | 56493 | Electrical Mechanic Certified |  | A200 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Baker, Jeffrey | 52711 | Electrician - STD |  | Preservation |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Baker, Steven | 55029 | Electrician - STD |  | Comm LV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Baldwin, Christopher | 55522 | Electrician - STD |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ball, Matthew | 56072 | Elect Apprentice 1st Year |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ball, Phillip | 56462 | Electrical Mechanic Certified |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bancroft, Travis | 55520 | Mechanic |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Barnes, Lachlan | 55412 | Electrician - STD |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Barter, Lachlan | 56023 | Boilermaker Welder |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bartkowski, Ian | 54559 | Storeperson |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bartlem, Matthew | 55479 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Baxter, Paul | 56149 | Electrician - STD |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bean, Robert | 56492 | Electrical Mechanic Certified |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Beeck, David | 201716 | Fork Lift Operator |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Beeson, Heath | 52714 | Trade Assistant |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bell, Belinda | 55823 | Electrical Apprentice |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bell, Michael | 52130 | Elect Apprentice 1st Year |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Benc, Aaron | 55136 | Electrician - STD |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bennett, Dean | 53194 | Electrical Mechanic Certified |  |  |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bennetts, Peter | 54555 | Boilermaker Welder |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bernardino, Joshua | 56238 | Boilermaker |  | Fab Shop |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Berry, Jedidiah | 56102 | Elect Apprentice 2nd Year |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Berthier, Jean-Paul | 55626 | Electrician - STD |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bessell, Adam | 56331 | Electrical Mechanic certified |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Beverstock, Jaydon | 53252 | Trade Assistant |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Biggs, Jackson | 55625 | Electrician - STD |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Biglands, Darren | 56109 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Blackmore, Geoffrey | 54780 | Electrician - STD |  | Temps |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Blake, Jordan | 55863 | Electrician - STD |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bliokas, Robert | 55110 | Special Class Electrician |  | QA/QC/HA |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Blythe, Luke | 56163 | Electrician - STD |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Boakes, Samuel | 54939 | Elect Apprentice 1st Year |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bonney, Jimi | 56110 | Trade Assistant |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Borell, Joshua | 56491 | Electrical Mechanic Certified |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Boswell, Mitchell | 56658 | Electrical Mechanic Certified |  |  |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Boulton, Thomas | 55682 | Trade Assistant |  | A200 MR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bowers, Bronwyn | 54036 | Instrument Technician |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bowman, Andrew | 56461 | Electrical Mechanic Certified |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bowyer, David | 56148 | Electrician - STD |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Boyle, Iain | 55453 | Leading Hand Electrician 10-19 |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bradley, Gavin | 46046 | Electrical Mechanic Certified |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bragg, Jeremy | 55862 | Electrician - STD |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bramston, Wade | 50336 | Leading Hand Electrician 10-19 |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Brandon, Heath | 55454 | Boilermaker Welder |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Brauer, Sebastian | 46270 | Electrical Mechanic Certified |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Braun, Maslan | 51735 | Electrician - STD |  | A200 Cable Pull-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bray, Hayden | 56522 | Electrical Mechanic Certified |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Broughton, Luke | 54852 | Dogman/Rigger |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Broughton, Ryan | 55664 | Trade Assistant |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Brown, Antony | 55523 | Electrician - STD |  | Temps |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Brown, Dylan | 53248 | Electrical Mechanic Certified |  |  |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Brown, Joshua | 55855 | Electrician - STD |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Brown, Mark | 56170 | Electrician - STD |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bruce, Donna | 54653 | Peggies |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bruce, Neil | 53695 | Mobile Crane Operator (up to 250Ton) |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Brunckhorst, Luke | 55112 | Electrician - STD |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Brunckhorst, Ryan | 56073 | Trade Assistant |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bryant, Leif | 55158 | Electrician - STD |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Buchhorn, Martin | 56390 | Electrical Boilermaker |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Buchmann, Adrian | 56405 | Electrical Mechanic HV Tester |  | Comm HV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Burmester, Shane | 55724 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Burrell, Mark | 54044 | Electrician - STD |  | Temps |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Bury, Paul | 56521 | Electrical Mechanic Certified |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Butlin, Allan | 56315 | Electrical Boilermaker |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Butters, Keith | 47937 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cables, William | 54081 | Electrician - STD |  | Preservation |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Calley, Dean | 56635 | Electrical Mechanic Certified |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cama, Gary | 55635 | Electrical Mechanic Certified |  | B100-G |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Campbell, Dean | 56520 | Electrical Mechanic Certified |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Canham, Gregory | 54971 | Leading Hand Mechanical 1-9 |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cappa, Peter | 56293 | Peggies |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cardosi, Marc | 55630 | Electrical Trade Assistant |  | B100-G |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Carling, Joshua | 54904 | Elect Apprentice 2nd Year |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Carrick, Jeremy | 56468 | Electrical Mechanic Certified |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Carter, Ricky | 56198 | Electrician - STD |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cash, Matthew | 55940 | Boilermaker Welder |  | C300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Casserly, Michael | 55706 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cassidy, Justin | 56460 | Electrical Mechanic Certified |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Castle, Shannon | 56074 | Trade Assistant |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cavanagh-Novelli, Jace | 51955 | Elect Apprentice 1st Year |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cendo, Anthony | 52771 | Trade Assistant |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Chadwick, Marc | 55879 | Elect Apprentice 1st Year |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Champion, Robert | 56489 | Electrical Mechanic Certified |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Chand, Kushneel | 55465 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Charles, Andrew | 56459 | Electrical Mechanic Certified |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Chefalachis, Matthew | 54687 | Electrician - STD |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cheung, Mathew | 55552 | Electrician - STD |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Church, Benjamin | 55949 | Electrician - STD |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Church, Michael | 55801 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Clark, Malcolm | 55693 | Boilermaker Welder |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Clark, Tony | 56020 | Electrician - STD |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Clarke, Nathan | 56197 | Electrician - STD |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Clarke, Neil | 56138 | Electrician - STD |  | Comm LV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Clarke, Ruben | 55941 | Boilermaker Welder |  | Fab Shop |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cleary, John | 54294 | Leading Hand Electrician 10-19 |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Clements, David | 56113 | Trade Assistant |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Clements, Jade | 55002 | Electrical Apprentice |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Clough, Russell | 56518 | Electrical Mechanic Certified |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Clout, Joshua | 55859 | Electrician - STD |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Coe, Glen | 56457 | Electrical Mechanic Certified |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Coe, Trevor | 56332 | Electrical Mechanic certified |  | A300-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Coghlan, Jess | 56037 | Electrician - STD |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Coghlan, Jonathon | 53153 | Electrical Mechanic Certified |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cole, Damien | 56420 | Electrical Mechanic Certified |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cole, Jake | 56167 | Electrician - STD |  | A300-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cole, Jason | 56218 | Trade Assistant |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cole, Matthew | 54553 | Boilermaker Welder |  | A100 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cole, Robert | 54855 | Truck Driver over 20 tonnes |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Coleman, Emma | 56018 | Trade Assistant |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Collyer, Benjamin | 56054 | Electrician - STD |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Conboy, Declan | 54281 | Electrician - STD |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Connor, Stephen | 56418 | Electrical Mechanic Certified |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cook, Damien | 55231 | Electrician - STD |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cook, James | 52810 | Trade Assistant |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cook, Stuart | 56636 | Electrical Mechanic Certified |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cooper, Murray | 56488 | Electrical Mechanic HV Tester |  | Comm HV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Coote, Angus | 55665 | Vehicle Operator (Hiab/Flat Bed) |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cootes, Michael | 55646 | Electrical Trade Assistant |  |  |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cornford, Robert | 55164 | Electrician - STD |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cornish, Thomas | 56196 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Coughlin, Noel | 56270 | Electrician - STD |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Coulin, Patrick | 56165 | Electrician - STD |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Craig, Justin | 56128 | Boilermaker |  | Fab Shop |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Crees, Bradley | 56162 | Electrician - STD |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cribbin, Gerard | 54766 | Leading Hand Electrician 10-19 |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Crisp, Tyler | 54906 | Elect Apprentice 1st Year |  | Temps |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Crockford, Simon | 52631 | Trade Assistant |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cubillo, Whitley | 56016 | Elect Apprentice 1st Year |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cullen, Diarmaid | 55689 | Electrician - STD |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cummings, David | 56247 | Electrician - STD |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Curtis, Brian | 53177 | Trade Assistant |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Cutts, Stephen | 55151 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
D'Addario, Frank | 56271 | Electrician - STD |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Daley, Matthew | 55406 | Electrician - STD |  | A100 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Davies, Antony | 56147 | Electrician - STD |  | A300-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Davies, Kevin | 55722 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Davies, Shawn | 56333 | Electrical Mechanic certified |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Davis, Samuel | 53133 | Trade Assistant |  | A100 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Day, Christopher | 55889 | Electrician - STD |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Day, Paul | 56246 | Electrician - STD |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
De Santis, Tyrone | 56192 | Elect Apprentice 3rd Year |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Deaves, Daniel | 55643 | Electrical Trade Assistant |  | B100-G |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Dehne, Jarrod | 55413 | Electrician - STD |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Delia, Chad | 53290 | Leading Hand Electrician 10-19 |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Densley, Campbell | 55798 | Storeperson |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Dezius, Joshua | 56316 | Electrical Mechanic certified |  | A200 MR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Dickson, Dale | 55652 | Electrician - STD |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Dignon, Scott | 56517 | Electrical Mechanic Certified |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Dillon, Michael | 56216 | Trade Assistant |  | Fab Shop |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Dixon, Michael | 56674 | Tube Fitter |  | A200 - Instro |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Dixon, Reece | 55547 | Electrician - STD |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Dobinson, Travis | 55355 | Electrician - STD |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Dodge, Stephen | 55888 | Boilermaker Welder |  | A200 MR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Doherty, Alan | 51013 | Electrical Mechanic Certified |  | A300-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Doherty, Michael James | 56317 | Electrical Mechanic certified |  | A200 MR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Doherty, Patrick | 56075 | Electrician - STD |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Doyle, Aaron | 56076 | Electrician - STD |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Doyle, Edward George | 53042 | Trade Assistant |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Doyle, Mitchell | 55775 | Electrical Mechanic Certified |  |  |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Drew, Barry | 51150 | Special Class Electrician |  | QA/QC - Tom |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Drew, Matthew | 56455 | Electrical Mechanic Certified |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Du Toit, Lance | 55624 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Duck, Mark | 56417 | Electrical Mechanic Certified |  | C400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Duff, Ryan | 56146 | Electrician - STD |  | A100 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Duffy, Kenny | 55656 | Electrician - STD |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Dunford, Peter | 55251 | Mobile Crane Operator (up to 250Ton) |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Dunkley, Peter | 56467 | Electrical Mechanic Certified |  | D200 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Dunn, Martin | 55627 | Electrician - STD |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Eades, Laurence | 56348 | Electrical Mechanic certified |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Earl, Wesley | 52816 | Trade Assistant |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Edgley, Shane | 56318 | Electrical Boilermaker |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Edwards, Aaron | 50759 | Electrician - STD |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Edwards, Henare | 55857 | Electrician - STD |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Edwards, Robert | 56639 | Electrical Mechanic Certified |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Egan, Forest | 56077 | Electrician - STD |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Eglington, Steven | 56349 | Painter |  | A200 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Eichmann, Leonard | 56053 | Electrician - STD |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Emery, Justin | 56350 | Electrical Boilermaker |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Engler, Craig | 55480 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Englishby, Ciaran | 52095 | Electrical Mechanic Certified |  | B100-G |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Evans, Clint | 54856 | Leading Hand Mechanical 1-9 |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Evans, Glenn | 55332 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Evans, Phillip | 56093 | Cable Jointer |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Fairbairn, Clinton | 55528 | Electrician - STD |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Falconer, Darrius | 56245 | Electrician - STD |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Fanning, Allen | 51717 | Electrician - STD |  | Temps |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Fanton, Peter | 55943 | Boilermaker Welder |  | C300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Farley, Nicholas | 55103 | Electrician - STD |  | Comm LV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Farnsworth, Raymond | 55648 | Electrical Mechanic Certified |  | B100-G |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Farrell, Ryan | 55604 | Electrician - STD |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ferguson, Codey | 56519 | Electrical Mechanic Certified |  | A300-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ferguson, Michael | 55674 | Trade Assistant |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Fernandes, Osby | 47341 | Instrumentation Technician |  | Completions |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Filippi, Massimo | 56617 | Instrumentation Technician |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Findlay, Brendan | 56641 | Rigger |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Fisher, Carl | 53943 | Electrician - STD |  | Comm LV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Fisher, Dean | 55135 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Fitzgerald, Kerry | 56516 | Electrical Mechanic Certified |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Fitzgerald, Shaun | 55329 | Electrician - STD |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Fitzgerald, Wayne | 55858 | Electrician - STD |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Fleming, Mark | 56078 | Electrician - STD |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Flint, Graham | 56079 | Trade Assistant |  | A100 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Flood, John | 47366 | Electrical Mechanic Certified |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ford, Brenton | 52755 | Leading Hand Electrician 10-19 |  | A100 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Forde, Adam | 53638 | Electrician - STD |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Foster, Matthew | 55688 | Electrician - STD |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Fox, Stephen | 55405 | Electrician - STD |  | Preservation |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Francis, Samuel | 56059 | Tube Fitter |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Francis, Ty | 55803 | Electrician - STD |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Frank, Gabai | 56111 | Trade Assistant |  | C300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Freudenberg, Christopher | 56416 | Electrical Mechanic Certified |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Frisch, Christopher | 56035 | Electrician - STD |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Fritz, Peter | 54090 | Storeperson |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Gablonski, Ross | 55810 | Boilermaker Welder |  | A200 MR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Gallagher, Jules | 56454 | Electrical Mechanic Certified |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Gallinagh, Adrian | 55864 | Electrician - STD |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Garritty, Benjamin | 56495 | Electrical Mechanic Certified |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Gauci, Anthony | 56515 | Electrical Mechanic Certified |  | A100 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Gaw, Alister | 55234 | Electrician - STD |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Geaney, John | 56272 | Electrician - STD |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Gear, David | 54688 | Electrician - STD |  | Comm LV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Gee, Michael | 52591 | Electrician - STD |  | Temps |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Geise, Gary | 56319 | Electrical Mechanic certified |  | A200 MR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Geisel, Wayne | 55813 | Mobile Crane Operator (up to 250Ton) |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
George, Christopher | 55109 | Electrician - STD |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
George, Clinton | 52783 | Electrician - STD |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Geraghty, Liam | 55529 | Electrician - STD |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Gerrard, Lindsay | 55960 | Elect Apprentice 4th Year |  | Materials |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Gersch-Mizen, Tyrone | 56220 | Electrician - STD |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Gibbs, Jack | 56021 | Electrician - STD |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Gibson, Cory | 56060 | Cable Jointer |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Giuliani, Adam | 54692 | Trade Assistant |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Godfrey, William | 53128 | Trade Assistant |  | A300-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Gogoll, Jesse | 56675 | Adult Apprentice - Electrical |  | D200 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Goldstone, Darryl | 56712 | Tube Fitter |  |  |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Good, Daniel | 52648 | Trade Assistant |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Goodson, Ryan | 54547 | Mechanic |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Gottani, Adrian | 56514 | Electrical Mechanic Certified |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Goundan, Kavin | 56145 | Electrician - STD |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Graham, Phillip | 54684 | Electrician - STD |  | A100 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Grant, Anthony | 55097 | Electrician - STD |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Grant, Stuart | 56452 | Electrical Mechanic Certified |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Greaves, Daniel | 55549 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Greenhalgh, Philip | 50709 | Electrician - STD |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Gregg, Neil | 55865 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Griffin, Jonathan | 55472 | Electrician - STD |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hampel, Ryan | 56124 | Boilermaker |  | C200 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Griffiths, Andrew | 54814 | Boilermaker Welder |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Grigg, Jeffrey | 47073 | Electrical Mechanic Certified |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Grigg, Kevin | 55614 | Electrician - STD |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Groarke, Christian | 55530 | Electrician - STD |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Guest, Geoffrey | 51711 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Guest, Shannon | 54902 | Elect Apprentice 1st Year |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Gunning, Darcy | 56525 | Electrical Apprentice |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Gutte, Christine | 55408 | Peggies |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Guy, Maxwell | 53138 | Electrical Mechanic Certified |  | B100-G |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hafoka, Alekisanita | 53228 | Electrical Mechanic Certified |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hall, Damien | 55944 | Boilermaker Welder |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hall, Warwick | 55100 | Electrician - STD |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Halton, Dwane | 55532 | Electrician - STD |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hamer, Simon | 56116 | Cable Jointer |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hamilton, Raymond | 56117 | Trade Assistant |  | A200 MR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Heaton, Jordan | 56143 | Electrician - STD |  | C400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hancock, Luke | 55237 | Electrician - STD |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hansen, Mitchell | 56320 | Electrical Boilermaker |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hansford, Justin | 52154 | Electrical Mechanic |  | A200 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hanson, Christopher | 55456 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hill, Matthew | 55672 | Electrician - STD |  | C300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hargest, Samuel | 56221 | Electrician - STD |  | Preservation |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Harnett, Geoffrey | 55341 | Electrician - STD |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Harnett, Ryan | 54663 | Leading Hand Electrician 10-19 |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Harp, Cameron | 56450 | Electrical Mechanic Certified |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Harper, Stephen | 55800 | Electrician - STD |  | A300-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Harrington, Bradley | 54473 | Electrician - STD |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Harrington, Phillip | 56494 | Electrical Mechanic Certified |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Harris, Elliot | 56230 | Trade Assistant |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Harris, Ian | 56185 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Harris, Rodney | 56523 | Electrical Mechanic Certified |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Harris, Samantha | 56451 | Cleaner |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Harrison, David | 56321 | Electrical Boilermaker |  | A200 MR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hartley, Callan | 56144 | Electrician - STD |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Harvey, Alan | 53096 | Adult Apprentice |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Harvey, Carolyn | 55822 | Peggies |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hayes, David | 55880 | Electrician - STD |  | A300-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hayes, Lawrence | 55307 | Electrician - STD |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hayes, Michael | 56225 | Electrician - STD |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hazelbane, Joseph | 56080 | Trade Assistant |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Headd, Robert | 53231 | Electrical Mechanic Certified |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Headon, Joe | 53097 | Trade Assistant |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hearnden, Grant | 56711 | Electrical Mechanic - LV Tester |  |  |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Heath, Damien | 56036 | Electrician - STD |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hunt, Julian | 55411 | Trade Assistant |  | C100 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Heffernan, Benjamin | 54664 | Electrician - STD |  | Comm LV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Heffernan, Thomas | 53124 | Electrical Mechanic Certified |  | B100-G |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Heironymus, Adam | 56056 | Electrician - STD |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Henderson, Ian | 55232 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Henriksen, Victor | 55676 | Trade Assistant |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Herbert, Benjamin | 56126 | Trade Assistant |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hettiger, Blake | 55545 | Electrician - STD |  | Preservation |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Higgins, Clayton | 54768 | Electrician - STD |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Higgs, David | 56183 | Electrician - STD |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hill, Christopher | 54905 | Elect Apprentice 1st Year |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hill, Joseph | 56115 | Trade Assistant |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Koloamatangi, Mark | 52933 | Trade Assistant |  | C100 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hill, Shaun | 56237 | Trade Assistant |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hill, Tyrone | 56524 | Electrical Mechanic Certified |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hinks, Brendan | 56231 | Electrician - STD |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hoar, Brad | 56351 | Adult Apprentice |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hoffman, Joshua | 56081 | Trade Assistant |  | A200 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hogg, Mathew | 56374 | Cable Jointer |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hohenhaus, Matthew | 54441 | Electrician - STD |  | A300-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hola, Halapolo | 56423 | Electrical Mechanic Certified |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Holdsworth, Nathan | 55780 | Electrical Mechanic Certified |  |  |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Holland, Jason | 53257 | Cable Jointer |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hollands, Rhys | 55883 | Elect Apprentice 1st Year |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hollier, Carl | 51954 | Elect Apprentice 1st Year |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hollingsworth, Christopher | 46508 | Electrician - STD |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Holloway, Benjamin | 56244 | Electrician - STD |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Holm, Sten | 56195 | Electrician - STD |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Holmes, Richard | 45925 | Electrical Mechanic certified |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Holstein, Nathan | 56706 | Electrical Mechanic Certified |  | Comm LV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Holt, Timothy | 55531 | Electrician - STD |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hooke, Bradley | 55671 | Electrician - STD |  | Temps |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hore, Aaron | 54038 | Electrical Mechanic certified |  | Materials |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Horsnell, Tristan | 55640 | Electrical Mechanic Certified |  | D200 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Horton, Andrew | 56234 | Electrician - STD |  | Preservation |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hough, Brendan | 55721 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Howell, Barry | 55459 | Electrician - STD |  | A200 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hudson, Michael | 55105 | Electrician - STD |  | Preservation |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hughes, Jonathan | 56322 | Electrical Mechanic certified |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hughes, Mark | 55606 | Electrician - STD |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Hughes, Michael | 56194 | Trades Assistant |  | Fab Shop |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Linehan, Owen | 53595 | Electrical Mechanic Certified |  | C300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Huther, John | 56465 | Electrical Mechanic Certified |  | A300-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Huynh, Vinh | 52285 | Electrician - STD |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Iannelli, Mark | 56542 | Cable Jointer |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ingles, Cesar | 56643 | Electrical Mechanic Certified |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ingles, Daniel | 56323 | Trades Assistant |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Intelisano, Antonio | 55466 | Electrician - STD |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Irwin, Jamie | 52473 | Elect Apprentice 1st Year |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ivancic, Goran | 56182 | Electrician - STD |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ivery, Tate | 45892 | Electrician - STD |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ives, Lindsay | 56058 | Electrician - STD |  | A300-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Jack, Owen | 55720 | Electrician - STD |  | Materials |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Jackson, Cori | 55533 | Electrician - STD |  | Comm LV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Jackson, David | 56474 | Driver - Motor Vehicle Over 6.09 Tonne |  | Training |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Jamieson, Christopher | 56334 | Electrical Mechanic certified |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Jamratphon, Janthima | 54847 | Peggies |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Jancec, Joseph | 55198 | Plumber |  | Temps |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Janssen, Lara | 55876 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Jarc, Bronte | 56176 | Electrician - STD |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Jarmyn, Bruce | 52932 | Trade Assistant |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Johnson, Brandon | 56224 | Electrician - STD |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Johnson, Cameron | 51049 | Electrical Mechanic Certified |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Johnson, Grant | 53131 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Johnson, Kenneth | 56425 | Electrical Mechanic Certified |  | Materials |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Joiner, Andrew | 55167 | Electrician - STD |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Joncour, Danika | 55312 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Jones, Ian | 53937 | Dogman/Rigger |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Jones, Jarrod | 56708 | Apprentice - Electrical |  |  |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Jones, Scott | 55462 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Jorgensen, Kyal | 56181 | Electrician - STD |  | A300-A 1 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Jupp, Nathan | 56031 | Painter |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Karaitiana, Kyle | 56273 | Electrician - STD |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kare Kare, Tawhai | 52355 | Trade Assistant |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kavanagh, Cillian | 51587 | Electrician - STD |  | A200 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kavanagh, James | 50741 | Electrical Mechanic Certified |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kaye, Jarrah | 56243 | Electrician - STD |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kearns, Luke | 53152 | Electrical Trade Assistant |  | B100-G |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Keehan, Paul | 50650 | Instrumentation Technician |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Keen, Stephen | 55534 | Trade Assistant |  | Materials |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Keller-Alvarez, Jamie | 56184 | Electrician - STD |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kelly, Bernard | 56131 | Trade Assistant |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kelly, Chris | 56175 | Electrician - STD |  | A200 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kelly, John | 56017 | Trade Assistant |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kelly, Paul | 55458 | Electrician - STD |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kennedy, Christopher | 55226 | Electrician - STD |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kennedy, Paul | 55797 | Electrician - STD |  | A200 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ketchell, Noama | 53188 | Trade Assistant |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kidd, David | 55331 | Electrician - STD |  | Comm HV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kilkenny, Martin | 56324 | Trades Assistant |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
King, Stephen | 53139 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kingdon, Allan | 55125 | Leading Hand Electrician 10-19 |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kloeden, Lyndon | 56335 | Electrical Mechanic certified |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Knight, Craig | 0 | Refrigeration Mechanic |  | Temps |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kofron, Michael | 56082 | Electrician - STD |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kohlman, Raymond | 54614 | Boilermaker Welder |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Loughran, Colin | 55633 | Electrical Trade Assistant |  | C200 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Koskela, Peter | 56142 | Electrician - STD |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kotany, Viktor | 56444 | Electrical Mechanic Certified |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kowal, Dylan | 55464 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kowcun, Steven | 52350 | Trade Assistant |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kraus-Chatfield, Selwynn | 51948 | Trade Assistant |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kurnoth, Poncie | 53935 | Trade Assistant |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kurnoth, Travis | 53944 | Trade Assistant |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kuyper, Jake | 56274 | Electrician - STD |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Kyle, Steven | 55481 | Electrician - STD |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Laarhoven, Robert | 56547 | Electrical Mechanic HV Tester |  | Comm HV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lake, Kenneth | 56352 | Electrical Boilermaker |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lambert, Alexander | 56130 | Boilermaker Welder |  | Fab Shop |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lancaster, Paul | 56141 | Electrician - STD |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lane, Robert | 56681 | Electrical Mechanic - HV Tester |  | Comm HV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lane, Trevor | 56083 | Trade Assistant |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Larkins, Michael | 56180 | Electrician - STD |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Latham, Graham | 56122 | Trade Assistant |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Laube, Rory | 54774 | Electrician - STD |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Laughton, Jeffrey | 56251 | Peggies |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lavery, Rodney | 56504 | Electrical Mechanic Certified |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lawler, Jack | 55719 | Electrician - STD |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lawrence, Brett | 56426 | Electrical Mechanic Certified |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Layton, Julian | 52819 | Trade Assistant |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lee, Ronald | 55677 | Trade Assistant |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Leehy, Dallas | 55663 | Electrician - STD |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Leite, Paulo | 55537 | Electrician - STD |  | Temps |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lemmon, Jay | 51718 | Electrician - STD |  | A200 MR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Leonard, Erwin | 55796 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Levick, Jake | 54907 | Elect Apprentice 1st Year |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lewis, Benjamin | 56445 | Electrical Mechanic Certified |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Liddy, Jason | 55884 | Storeperson |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Maccagnan, Frank | 56275 | Electrician - STD |  | C300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ling, Harvey | 51224 | Electrician - STD |  | A300-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Little, Derek | 56336 | Electrical Mechanic certified |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Littler, Peter | 55886 | Electrician - STD |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Llora, Matthew | 56447 | Electrical Mechanic Certified |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lockwood, Raymond | 47365 | Special Class Electrician |  | QA/QC/HA |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lodiong, Justin | 53184 | Trade Assistant |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Loehr, Frank | 56166 | Mobile Crane Operator (up to 250Ton) |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lott, Benjamen | 55535 | Trade Assistant |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mather, Kevin | 55623 | Electrician - STD |  | C200 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lovegrove, Macinlay | 54900 | Elect Apprentice 1st Year |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Low, Stephen | 56414 | Electrical Mechanic Certified |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lowth, Robert | 55323 | Electrician - STD |  | Comm HV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lucas, Daniel | 56446 | Electrical Mechanic Certified |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Luck, Jeffrey | 55152 | Electrician - STD |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ludwig, Mark | 55718 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Luff, Andrew | 55809 | Boilermaker Welder |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lunn, Joshua | 56204 | Trade Assistant |  | A200 MR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lupson, Mark | 56325 | Electrical Mechanic certified |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lush, Sam | #N/A | #N/A |  |  |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Luxton, Ruben | 55536 | Electrician - STD |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lymbery, Anthoney | 56353 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Lynch, Garry | 53938 | Mobile Crane Operator (up to 250Ton) |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McCrohan, John | 56026 | Electrician - STD |  | C400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
MacDonald, Malcolm | 56159 | Electrician - STD |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Macdonald, Phillip | 56242 | Electrician - STD |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mace, Bryan | 56233 | Electrician - STD |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mackay, Scott | 56276 | Electrician - STD |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Maconachie, Ryan | 55227 | Electrician - STD |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Maconochie, Simon | 55621 | Electrician - STD |  | A300-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Madlin, Jon | 56084 | Electrician - STD |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Maggiore, Andrew | 56448 | Instrumentation Technician |  | A200 - Instro |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Magriplis, Nectarios | 55812 | Boilermaker Welder |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Maher, Bradley | 56326 | Electrical Mechanic certified |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mallon, Stephen | 56241 | Electrician - STD |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Manning, David | 54691 | Trade Assistant |  | A100 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Marino, Karl | 55666 | Trade Assistant |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Maris, Luke | 54747 | Electrician - STD |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Marshall, Jason | 55717 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Martin, Christopher | 56064 | Electrician - STD |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Martin, Jason | 55867 | Electrician - STD |  | A200 Cable Pull-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mason, Aidan | 56498 | Electrical Mechanic Certified |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mason, Luke | 56327 | Electrical Mechanic certified |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mason, Peter | 56415 | Electrical Mechanic Certified |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mason, Wade | 53237 | Storeperson |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Matavire, Morgan | 55885 | Electrician - STD |  | Materials |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McKenzie, James | 56085 | Electrician - STD |  | C300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Matthews, Aidan | 53178 | Electrical Mechanic Certified |  | B100-G |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Matthews, Paul | 56215 | Electrician - STD |  | Temps |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Matthews, Rhys | 56403 | Electrical Mechanic HV Tester |  | Comm HV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Maxted, Warwick | 55946 | Boilermaker Welder |  | A100 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mayo, Robert | 55550 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McAdam, Russell | 55669 | Trade Assistant |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McBean, Stuart | 54581 | Electrical Mechanic Certified |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McCaffrey, Stuart | 52140 | Electrical Mechanic Certified |  | B100-G |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McCann, Jeremy | 52936 | Elect Apprentice 1st Year |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McCarthy, Jamie | 54690 | Electrician - STD |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McConn, Seamus | 55540 | Electrician - STD |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McConochie, Craig | 55099 | Electrician - STD |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McCormac, Mitchell | 56354 | Electrical Boilermaker |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McCoy, Warren | 55334 | Boilermaker Welder |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McCracken, Cameron | 56019 | Electrician - STD |  | A200 Cable Pull-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mollee, Nathan | 55690 | Electrician - STD |  | C300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McCrohon, Stephen | 56277 | Electrician - STD |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McCrudden, Enda | 55539 | Electrician - STD |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Morgan, Dan | 56634 | Electrical Mechanic Certified |  | C400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McDonald, Ryan | 56232 | Electrician - STD |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McGaffin, Luke | 55538 | Electrician - STD |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McGahey, Maurice | 55546 | Electrician - STD |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McGee, Matthew | 55866 | Electrician - STD |  | A200 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McGee, Richard | 55653 | Electrician - STD |  | A200 MR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McGowan, Ryan | 56278 | Electrician - STD |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McGrath, Shane | 55190 | Boilermaker Welder |  | A200 MR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McIntee, Nathan | 54789 | Tube Fitter |  | A200 - Instro |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McKay, Aaron | 45329 | Electrical Mechanic Certified |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
O'Donnell, Eamonn | 51758 | Electrical Mechanic Certified |  | C200 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McKeown, Michael | 55225 | Electrician - STD |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McKindley, Glenn | 54144 | Special Class Electrician |  | QA/QC - Tom |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McKinnon, Andrew | 56203 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McLennan, Mark | 56029 | Electrician - STD |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McLeod, Darren | 53044 | Elect Apprentice 1st Year |  | Temps |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McLoughlin, Martin | 53167 | Plumber |  | Temps |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McMillan, Adam | 56174 | Electrician - STD |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McNab, Callan | 55716 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McNair, Scott | 54043 | Electrician - STD |  | Comm LV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McNeill, Dylan | 52633 | Elect Apprentice 1st Year |  | A200 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McOnie, Shaun | 56173 | Electrician - STD |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
McQuillan, Ciaran | 56200 | Electrician - STD |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Meagher, Christopher | 56499 | Electrical Mechanic Certified |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Medlicott, Gray | 53243 | Electrician - STD |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Meier, Sarah | 56407 | Storeperson |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mengel, Walter | 55628 | Electrician - STD |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mengel, Wesley | 55655 | Electrician - STD |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mercer, Alastair | 56449 | Electrical Mechanic Certified |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mertens, Andrew | 54496 | Special Class Electrician |  | QA/QC/HA |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Miers, Paul | 56119 | Electrician - STD |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mijota, Lucas | 56214 | Electrician - STD |  | A200 MR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Millard, Timothy | 55577 | Leading Hand Electrician 10-19 |  | A200 Cable Pull-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Miller, Jonathan | 56202 | Electrician - STD |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Miller, Joshua | 56355 | Electrical Mechanic certified |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Miller, Troy | 55102 | Electrician - STD |  | A200 MR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Minchinton, Nigel | 53100 | Trade Assistant |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mirtschin, Paul | 56328 | Electrical Mechanic certified |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Missen, Grant | 56236 | Trade Assistant |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mitchell, Lindsay | 55667 | Trade Assistant |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mitchell, Paul | 56453 | Electrical Mechanic Certified |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mitchell, Richard | 54695 | Electrician - STD |  | Comm LV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Moday, Aldrin | 53140 | Trade Assistant |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mohr, Michael | 55675 | Trade Assistant |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Moir, Brendan | 55703 | Electrician - STD |  | Comm LV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Pocock, John | 56033 | Electrician - STD |  | C300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Moncrieff, Craig | 56512 | Electrical Mechanic Certified |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Moore, Alan | 55947 | Boilermaker Welder |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Moran, Callum | 55681 | Trade Assistant |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Rioli, Randall | 56164 | Trade Assistant |  | C300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Morris, Dillon | 54909 | Elect Apprentice 2nd Year |  | Temps |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Morrissey, Corey | 56217 | Electrician - STD |  | A100 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Morrow, Dion | 56179 | Trade Assistant |  | A200 MR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Motlap, Jaxon | 55856 | Elect Apprentice 1st Year |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mountney, John | 56502 | Electrical Mechanic Certified |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mugridge, Darryl | 54045 | Electrician - STD |  | Comm LV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Muir, Matthew | 56279 | Electrician - STD |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Munnelly, Karen | 54686 | Peggies |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Murphy, Gary | 56090 | Trade Assistant |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Murray, Joel | 55692 | Electrician - STD |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Murray, Sienna | 56250 | Peggies |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Murtagh, Sean | 56528 | Electrical Mechanic Certified |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Nam, Bun Thoeun | 55714 | Electrician - STD |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Nassif, Peter | 51374 | Electrician - STD |  | Comm LV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Naylor, Dudley | 54957 | Special Class Electrician |  | QA/QC/HA |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Neilsen, Gary | 54685 | Trade Assistant |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Neligan, Daniel | 56280 | Trade Assistant |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Nelson, Brock | 52725 | Electrical Mechanic Certified |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Newitt, Stephen | 55661 | Trade Assistant |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Newman, Ashley | 56529 | Storeperson |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ryan, Paul | 56153 | Electrician - STD |  | C200 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Nguyen, Huy | 55684 | Electrician - STD |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Nicholls, David | 56456 | Electrical Mechanic Certified |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Nichols, Aaron | 55868 | Boilermaker Welder |  | A100 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Nichols, Melissa | 55806 | Peggies |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Nielsen, Trent | 54771 | Leading Hand Electrician 10-19 |  | Comm LV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Noaks, Krystal | 56463 | Electrical Apprentice |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Nolan, Sean | 53045 | Plumber |  | Temps |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Norman, Gareth | 55156 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Novinc, Antun | 56171 | Electrician - STD |  | A200 Cable Pull-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
O' Callaghan, David | 56705 | Trades Assistant Electrical |  |  |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
O'Brien, Brodi | 54556 | Leading Hand Mechanical 1-9 |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
O'Connor, Con | 56424 | Electrical Mechanic Certified |  | Comm HV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
O'Connor, Daniel | 56178 | Electrician - STD |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Odgers, Stewart | 52147 | Elect Apprentice 1st Year |  | A200 Cable Pull-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Schigulski, Andrew | 56086 | Electrician - STD |  | C300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
O'Dwyer, Paul | 55820 | Mobile Crane Operator (up to 250Ton) |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ogden, Lionel | 53156 | Elect Apprentice 1st Year |  | Temps |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ogilvie, Alistair | 55713 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ohlenrott, Blair | 55124 | Electrician - STD |  | A100 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
O'Keefe, Andrew | 54035 | Electrician - STD |  | Materials |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Oliver, Graham | 56161 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Oliver, Janene | 55870 | Trade Assistant |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Onofrio, David | 56193 | Electrician - STD |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
O'Riordan, Ciaran | 56527 | Electrical Mechanic Certified |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Osborne, Justin | 56458 | Electrical Mechanic certified |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Page, Brendan | 55869 | Electrician - STD |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Parkyn, Michael | 56357 | Electrical Mechanic certified |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Parsons, Warren | 55418 | Electrician - STD |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Partridge, Jared | 56223 | Electrician - STD |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Partridge, Scott | 55860 | Boilermaker Welder |  | A200 - Instro |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Patterson, Luke | 52713 | Electrician - STD |  | Preservation |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Paul, Baby | 56421 | Electrical Mechanic Certified |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Paulis, Daniel | 55629 | Electrician - STD |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Pearce, Charles | 56501 | Electrical Mechanic Certified |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Pearce, Jason | 55712 | Electrician - STD |  | Materials |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Pearson, Shaw | 55890 | Electrician - STD |  | Materials |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Pegg, Daniel | 53225 | Trade Assistant |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Pendlington, Kim | 45838 | Tube Fitter |  | A200 - Instro |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Petie, Darren | 56158 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Petroff, John | 50293 | Electrician - STD |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Philips, Marten | 56526 | Electrical Mechanic Certified |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Phillips, Codey | 53103 | Trade Assistant |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Phillips, Mark Andrew | 54777 | Leading Hand Electrician 10-19 |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Phillips, Mark Barry | 55098 | Electrician - STD |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Pidgeon, Christopher | 55711 | Electrician - STD |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Pillay, Wesley | 55658 | Electrician - STD |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Pirie, Shaye | 54791 | Tube Fitter |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Pleli, Johann | 55679 | Trade Assistant |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Seton, Thomas | 56071 | Electrician - STD |  | C300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Plumridge, Shannon | 55324 | Electrician - STD |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Trotto, Michael | 55691 | Electrician - STD |  | C300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Porter, Daniel | 55662 | Trade Assistant |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Poulsen, Poul | 56281 | Electrician - STD |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Power, Michael | 53279 | Electrical Mechanic Certified |  | B100-G |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Preston, Kirk | 56497 | Electrical Mechanic Certified |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Preston, Lukas | 56500 | Electrical Mechanic Certified |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Priestley, Ian | 55101 | Electrician - STD |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Prior, Charlie | 55548 | Electrician - STD |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Pryce, Jordan | 54358 | Electrical Apprentice |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Pumpa, Lloyd | 56358 | Electrical Boilermaker |  | Fab Shop |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Purkis, Renee | 56434 | Storeperson |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Purton, Benn | 56207 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Putland, Mitchell | 56034 | Boilermaker |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Pyke, Hayden | 55414 | Electrician - STD |  | Preservation |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Quabba, Phillip | 56120 | Electrician - STD |  | Comm LV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Raharuhi, Rua | 55410 | Leading Hand Electrician 10-19 |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ralph, James | 53459 | Instrumentation Technician |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Redman, Andrew | 55221 | Trade Assistant |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Redpath, Michael | 55952 | Labourer |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Reeves, Christopher | 55891 | Cable Jointer |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Reid, Luke | 55482 | Electrician - STD |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Reinke, Brent | 55871 | Boilermaker Welder |  | A200 - Instro |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Renfrey, Adam | 56282 | Electrician - STD |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Reust, Shirley | 53121 | Leading Hand Electrician 10-19 |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Richardson, Brent | 55224 | Electrician - STD |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Richardson, Warren | 56431 | Electrical Mechanic Certified |  | Comm LV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Waller, James | 56640 | Electrical Mechanic Certified |  | C300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Riley, Dylan | 56359 | Electrical Boilermaker |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Wind, Sandra | 56292 | Storeperson |  | C200 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Roberts, Gerard | 55634 | Electrical Trade Assistant |  | B100-G |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Roberts, Matthew | 55892 | Trade Assistant |  | A100 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Robertson, Alan | 55726 | Electrical Mechanic Certified |  |  |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Robinson, Elaine | 54362 | Peggies |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Roe, Dylan | 55352 | Dogman/Rigger |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ronald, David | 55357 | Boilermaker Welder |  | Fab Shop |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Rose, Gary | 52929 | Trade Assistant |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Rosenbach, Nick | 56154 | Electrician - STD |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Rotumah, Shea | 56133 | Elect Apprentice 2nd Year |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Russell, David | 56168 | Mobile Crane Operator (up to 250Ton) |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Russell, Joanne | 56707 | Labourer |  |  |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ryan, Matthew | 52146 | Trade Assistant |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Wood, Timothy | 56534 | Electrical Mechanic Certified |  | C300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ryan, Raymond | 46601 | Special Class Electrician |  | QA/QC - Tom |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ryan, Seamus | 55710 | Electrician - STD |  | Materials |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Rybka, Cody | 52615 | Electrician - STD |  | A200 Cable Pull-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Salter, Matthew | 55893 | Boilermaker Welder |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Salvemini, Lee | 50854 | Electrical Mechanic Certified |  | D200 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Sambells, Roy | 56507 | Electrical Mechanic Certified |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Sanderson, Gregory | 56283 | Boilermaker |  | A200 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Sanderson, James | 52820 | Elect Apprentice 1st Year |  | A100 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Sando, Timothy | 56389 | Electrical Boilermaker |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Sargeant, Martin | 55811 | Boilermaker Welder |  | A100 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Sariago, Joshua | 55305 | Trade Assistant |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Sawley, Justin | 55709 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Scanlon, William | 55631 | Electrical Trade Assistant |  | B100-G |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Scannell, Jasper | 54033 | Trade Assistant |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Schembri, Caleb | 50660 | Electrician - STD |  | QA |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Griffith, Bradley | 56642 | Electrical Mechanic Certified |  | C300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Scothern, Dale | 53946 | Elect Apprentice 4th Year |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Scougall, Trent | 55309 | Electrician - STD |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Scrymgour, James | 56114 | Trade Assistant |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Seagrott, Jason | 56132 | Electrician - STD |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Seaman, Hannah | 56530 | Peggies |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Selby, Duncan | 56388 | Electrical Boilermaker |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Harford, Derek | 54397 | Electrician - STD |  | C300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Shannon, Brayden | 56123 | Elect Apprentice 3rd Year |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Shaw, Earl | 55415 | Electrician - STD |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Shaw-Reynolds, Daniel | 50602 | Electrician - STD |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Sheedy, Daniel | 56533 | Electrical Mechanic Certified |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Shepherd, Timothy | 56360 | Electrical Mechanic certified |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Sherwell, Darell | 56466 | Electrical Mechanic Certified |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Sherwood, Benjamin | 53182 | Trade Assistant |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Sherwood, Luke | 53158 | Trade Assistant |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Siganto, Rhys | 56235 | Trade Assistant |  | A200 Cable Pull-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Simmons, Michael | 56469 | Electrical Mechanic Certified |  | A200-Subs - JH |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Singaram, Vijayan | 55819 | Electrician - STD |  | Materials |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Singleton, Travis | 55457 | Boilermaker Welder |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Skippings, David | 54554 | Storeperson |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Slater, Craig | 54037 | Electrician - STD |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Smith, Brent | 56506 | Electrical Mechanic Certified |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Smith, Grant | 55821 | Boilermaker Welder |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Mcculloch, Dean | 56472 | Electrical Mechanic Certified |  | C300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Smith, Jai | 55641 | Electrical Trade Assistant |  | B100-G |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Smith, Ken | 55253 | Mobile Crane Operator (up to 250Ton) |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Smith, Luke Sonny | 56208 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Smith, Ryan | 53159 | Trade Assistant |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Smith, Tarrod | 56191 | Electrician - STD |  | A200 Cable Pull-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Smith, Warren | 56222 | Trade Assistant |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Smordowski, Adam | 54781 | Leading Hand Electrician 10-19 |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Snelling, Gary | 51460 | Electrician - STD |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Somerville, James | 55702 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Spehr, Mitch | 55673 | Electrician - STD |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Spinks, Thomas | 55461 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Spiteri, Keegan | 56210 | Electrician - STD |  | E300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Spiteri, Peter | 55311 | Electrician - STD |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Spurling, Luke | 56189 | Electrician - STD |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Squire, Desmond | 56209 | Electrician - STD |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Stack, Grant | 51786 | Electrical Mechanic Certified |  | A300-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Stagg, Ryan | 56362 | Communications Technician |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Stallan, Daniel | 55701 | Storeperson |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Stanek, Jerry | 52374 | Trade Assistant |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Starkey, Luke | 55306 | Electrician - STD |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Starkey, Nicholas | 56329 | Electrical Mechanic certified |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Staunton, Paul | 56284 | Electrician - STD |  | A200 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Stephenson, Damian | 52133 | Elect Apprentice 1st Year |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Stevens, Adam | 56430 | Electrical Mechanic Certified |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Stevens, Jacob | 56152 | Electrician - STD |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Stevens, Michael | 56199 | Electrician - STD |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Stevenson, Lee-Anne | 55348 | Peggies |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Stoertebecker, Jeannine | 56409 | Peggies |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Stoertebecker, Ronald | 55680 | Trade Assistant |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Stone, Timothy | 52808 | Trade Assistant |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Strachan, Murray | 56066 | Electrician - STD |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Strange, Stephen | 55704 | Trade Assistant |  | A200 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Stuart, Christopher | 56387 | Special Class Electrician |  | QA/QC/HA |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Sutherland, James | 55730 | Electrical Trade Assistant |  |  |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Sutton, Nigel | 56151 | Electrician - STD |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Swaddling, Nathan | 55818 | Electrician - STD |  | A300-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Swadling, David | 56150 | Leading Hand Electrician 10-19 |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Swan, David | 55407 | Electrician - STD |  | Preservation |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Szabatura, Richard | 51729 | Driver of Trucks over 20T |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Tarasuik, Andrew | 56213 | Electrician - STD |  | A200 Cable Pull-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Tawake, Viliame | 55817 | Electrician - STD |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Taylor, Matthew | 55460 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Taylor, Nathaniel | 56438 | Electrical Mechanic Certified |  | B100-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Taylor, Scott | 55678 | Trade Assistant |  | A200 Cable Pull-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Taylour, Lachlan | 55541 | Electrician - STD |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ten Hoope, Justin | 55700 | Electrician - STD |  | A200 Cable Pull-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Tennent, William | 56188 | Electrician - STD |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Teske, Bradley | 51062 | Electrician - STD |  | A200 PR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Thomas, David | 56063 | Electrician - STD |  | A300-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Thomas, Dominic | 53250 | Electrician - STD |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Thompson, Clint | 55162 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Thorne, Madelyn | 55347 | Labourer |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Thorne, Peter | 55948 | Boilermaker Welder |  | A100 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Thornton, David | 56373 | Rigger |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Timms, Steven | 55608 | Electrician - STD |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Tobin, Nathan | 55900 | Electrician - STD |  | A100 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Todd, Michael | 56125 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Tonello, Aaron | 55551 | Electrician - STD |  | Temps |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Topp, Lachlan | 55345 | Electrician - STD |  | A100 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Trotto, Christopher | 56219 | Trade Assistant |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Newton, Daniel | 56356 | Electrical Boilermaker |  | C200 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Truong, Tue | 55333 | Electrician - STD |  | A200 MR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Tuisuva, Joseva | 55027 | Storeperson |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Tunstall, David | 56240 | Electrician - STD |  | A200 Cable Pull-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Turner, Stuart | 56429 | Electrical Mechanic Certified |  | D200 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Tyack, Jay | 55687 | Electrician - STD |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Tysoe, Matthew | 55657 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Unsted, Antony | 55708 | Electrician - STD |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Ploughman, Brennan | 56637 | Electrical Mechanic Certified |  | C300 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Van Amersfoort, Roland | 55668 | Trade Assistant |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Van Deventer, Matthew | 54772 | Trade Assistant |  | COWS |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Vass, Joshua | 56187 | Electrician - STD |  | B100-D |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Verrall, Matthew | 56287 | Electrician - STD |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Vesey, Craig | 55409 | Boilermaker Welder |  | A100 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Vicary, Damian | 54778 | Electrician - STD |  | A200 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Vick, Brodie | 55874 | Trade Assistant |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Vickers, Jade | 56062 | Electrician - STD |  | A200 Cable Pull-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Vidler, John | 55654 | Electrician - STD |  | A300-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Virgona, Geoffrey | 56433 | Electrical Mechanic Certified |  | Temps |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Walden, Mickell | 56330 | Electrical Mechanic certified |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Walford, Dominik | 56127 | Electrician - STD |  | Comm LV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Walker, Craig | 54651 | Electrician - STD |  | A200-Subs - GP |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Walker, Luke | 56435 | Electrical Mechanic Certified |  | Comm HV |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Walker, Mark | 56239 | Electrician - STD |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Riddiford, Lance | 56156 | Electrician - STD |  | C500 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Warren, Reece | 56509 | Electrical Mechanic Certified |  | E400 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Warren, Ross | 56288 | Boilermaker |  | A200 MR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Waterton, Peter | 51087 | Elect Apprentice 4th Year |  | A200 MR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Watkin, Michael | 55951 | Electrician - STD |  | A100 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Watkins, Wade | 55343 | Trade Assistant |  | A300-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Watling, Hayden | 54237 | Boilermaker Welder |  | A200 MR Compressor |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Watson, Jason | 56088 | Trade Assistant |  | A200 Cable Pull-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Watson, Michael | 56290 | Electrician - STD |  | B100-C |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Waye, Mitchell | 55816 | Electrician - STD |  | A200 Cable Pull-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Webb, James | 56532 | Electrical Mechanic Certified |  | HV Team |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Weber, Benjamin | 51750 | Electrician - STD |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Weber, Colin | 56546 | Rigger |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Weekley, Travis | 56508 | Electrical Mechanic Certified |  | A200 Cable Pull-A |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Weeks, Timothy | 55899 | Electrician - STD |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Weise, Daniel | 56437 | Adult Apprentice |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Went, Owen | 55659 | Trade Assistant |  | Logistics |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Werndly, Luke | 56212 | Electrician - STD |  | B100-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Weston, Phillip | 56291 | Electrician - STD |  | B100-F |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Whan, Nathanael | 55416 | Electrician - STD |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Wheeler, Stanley | 56363 | Electrical Mechanic certified |  | A300-A 2 |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Whelan, Shane | 55898 | Trade Assistant |  | A200 vessels |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
White, Bronwyn | 56252 | Peggies |  | Stores/Shop/Site |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
White, Graeme | 56134 | Electrician - STD |  | A200-B |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
White, William | 53255 | Electrical Mechanic Certified |  | B100-G |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Whitehouse, Timothy | 55725 | Electrical Trade Assistant |  |  |  |  | Kentz |  |  | 0 | [18 empty] | 0 | 0
Whittle, Carlin | 55328 | Electrician - STD |  | A200 PR Compressor |  |  | Kentz
Williams, Gareth | 55707 | Electrician - STD |  | E400 |  |  | Kentz
Williamson, John | 55824 | Boilermaker Welder |  | A100 vessels |  |  | Kentz
Wilson, Craig | 56211 | Electrician - STD |  | E300 |  |  | Kentz
Wilson, Paul | 55542 | Electrician - STD |  | B100-B |  |  | Kentz
Wilson, Shayne | 56531 | Electrical Mechanic Certified |  | A200-Subs - GP |  |  | Kentz
Wiltshire, Peter | 51757 | Vehicle Operator (Hiab/Flat Bed) |  | Logistics |  |  | Kentz
Smith, Ian | 56112 | Electrician - STD |  | C500 |  |  | Kentz
Winterbotham, Duncan | 56471 | Electrical Mechanic Certified |  | E300 |  |  | Kentz
Withers, Anthony | 54039 | Instrument Technician |  | Logistics |  |  | Kentz
Wolthers, Brook | 54783 | Electrician - STD |  | A100 |  |  | Kentz
Uptin, Zachary | 55699 | Trade Assistant |  | C300 |  |  | Kentz
Woodcock, John | 56025 | Electrician - STD |  | A200 Cable Pull-B |  |  | Kentz
Woods, Justin | 45889 | Electrician - STD |  | E400 |  |  | Kentz
Woolf, Darren | 55814 | Storeperson |  | A200-B |  |  | Kentz
Woolley, Brett | 55683 | Electrician - STD |  | A200 Cable Pull-B |  |  | Kentz
Woolley, Reddrick | 53086 | Electrician - STD |  | A200 Cable Pull-B |  |  | Kentz
Woon, Michael | 55222 | Vehicle Operator (Hiab/Flat Bed) |  | Logistics |  |  | Kentz
Worthington, Graham | 50040 | Electrician - STD |  | A300-B |  |  | Kentz
Wright, Dylan | 56091 | Electrician - STD |  | B100-C |  |  | Kentz
Wright, Haydn | 55420 | Electrician - STD |  | A100 |  |  | Kentz
Wuest, Troy | 55895 | Mechanic |  | Temps |  |  | Kentz
Wyer, Jonathan | 56092 | Trade Assistant |  | A300-A 2 |  |  | Kentz
Yalden, Steven | 56024 | Trade Assistant |  | B100-F |  |  | Kentz
Yao, Shunfu | 56172 | Electrician - STD |  | B100-F |  |  | Kentz
Yee, Martin | 51716 | Electrician - STD |  | Preservation |  |  | Kentz
Yoong, Chin Nam | 52763 | Trade Assistant |  | HV Team |  |  | Kentz
Young, John | 54042 | Adult Apprentice |  | B100-A |  |  | Kentz
Young, Joseph | 56629 | Advanced Rigger (Telecomms) |  | Logistics |  |  | Kentz
Young, Michael | 56364 | Instrumentation Technician |  | Completions |  |  | Kentz
Yovich, Fabian | 56365 | Trades Assistant |  | A300-A 2 |  |  | Kentz
Yuwono, Dio | 56068 | Electrician - STD |  | A200 Cable Pull-B |  |  | Kentz
Allen, Steven |  | Operator |  | Rocktown
Barry, John |  | Operator |  | Rocktown
Barry, Michael |  | Carpenter |  | Rocktown
Bond, Adrian |  | Operator |  | Rocktown
Archer, Kurt | R&R | Operator |  | Rusca | [24 empty] | 0 |  |  | BackFills
Bell, John-Paul | R&R | Labourer |  | Rusca | [24 empty] | 0 |  |  | B1BA 4m3 FCR
Brown, Paul |  | Driver-Truck over 20T |  | Rusca | A100 |  |  |  |  | 8 | A1BB |  | 8 | [15 empty] | 8 | 0 | cr
Buie, Wellias | Sick | Labourer |  | Rusca | [24 empty] | 0 | 0 |  |  |  | A1BG 24 m3 FCR
Butler, Lynda |  | Driver-Truck over 20T |  | Rusca | A100 |  |  |  |  | 8 | A1BF |  | 8 | [15 empty] | 8 | 0 | cr
Campbell, Peter |  | Operator-Exc over 100BHP |  | Rusca | A100 |  |  |  |  | 8 | A1BB | [7 empty] | 8 | [9 empty] | 8 | 0 | ct
Cardona, Joseph |  | Truck Driver over 20T |  | Rusca | A100 | B100 |  |  |  | 8 |  |  |  | 4 | 4 | [13 empty] | 8 | 0 | bf
Chadun, Mica |  |  |  | Rusca | [5 empty] | 0 | [18 empty] | 0 | 0 |  |  |  |  | Excavations
Coburn, Joshua |  | Operator-Exc up to 100BHP |  | Rusca | A100 |  |  |  |  | 8 | A1ED | [9 empty] | 8 | [7 empty] | 8 | 0 | cr | Waste from site to EMA
Conlan, Brett |  | Operator-Exc over 100BHP |  | Rusca | A100 | A200 | B100 |  |  | 8 |  |  | 2 | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1 | [5 empty] | 8 | 0 |  | 2nd FCR 12m3
Corp, Cameron | R&R | Driver-Truck over 20T |  | Rusca | [24 empty] | 0 | 0
Elliott, Nicholas |  | Operator |  | Rocktown | [5 empty] | 0 | [18 empty] | 0 | 0
Dicandilo, Nicholas |  | Labourer |  | Rusca | A100 |  |  |  |  | 8 | A1BB | [11 empty] | 8 | [5 empty] | 8 | 0 | bf
Evans, Christopher |  | Labourer |  | Rocktown | [5 empty] | 0 | [18 empty] | 0 | 0 |  |  |  |  | Waste to EMA
Dunwell, Justin | R&R | Operator-Exc over 100BHP |  | Rusca | [24 empty] | 0 | 0
Dwyer, Jesse |  | Operator-Exc over 100BHP |  | Rusca | A200 | B100 |  |  |  | 8 | [7 empty] | 8 | [10 empty] | 8 | 0
Ellis, Jason |  | Labourer |  | Rusca | site wide |  |  |  |  | 8 | Fuel trailer |  | 2 | 1 | 2 |  |  |  |  | 1 | 1 | 1 | [6 empty] | 8 | 0 |  | Material into EMA
Field, Jim |  | Operator |  | Rocktown
Ford, Michael |  |  |  | Rocktown | [5 empty] | 0 | [18 empty] | 0 | 0
Erlandson, Jarred | A/L | Labourer |  | Rusca | [24 empty] | 0 | 0
Farrell, Andrew |  | Labourer |  | Rusca | E600 |  |  |  |  | 8 | [7 empty] | 8 | [10 empty] | 8 | 0
Faul, Peter | R&R | Driver-Truck over 20T |  | Rusca | [24 empty] | 0 | 0
Feeney, Conor |  | Labourer |  | Rusca | A100 |  |  |  |  | 8 | A1BG |  | 8 | [15 empty] | 8 | 0 | cr
Gates, Kevin |  | Operator-Exc over 100BHP |  | Rusca | A300 | A100 |  |  |  | 8 | Enviro | [6 empty] | 8 | [10 empty] | 8 | 0 |  | Siteworks
Hynes, Daniel |  | Carpenter |  | Rocktown | [5 empty] | 0 | [18 empty] | 0 | 0
Gilbert, Dale |  | Labourer |  | Rusca | B100 | A100 |  |  |  | 8 |  |  |  | 4 | 4 | [13 empty] | 8 | 0 | bf
Grey, Dean |  | Labourer |  | Rusca | A100 |  |  |  |  | 8 | A1BG |  | 8 | [15 empty] | 8 | 0 | cr
Gruszkowski, Michael |  | Operator-Exc over 100BHP |  | Rusca | A100 |  |  |  |  | 8 | A1BB | [7 empty] | 8 | [9 empty] | 8 | 0 | ct | Sandbags delivered onsite
Hale, Bryan |  | Truck Driver over 20T |  | Rusca | site wide |  |  |  |  | 8 | watercart |  | 2 | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1 | [5 empty] | 8 | 0 |  | 4 pallets sandbags to B1BA
Hall, Brett |  | Truck Driver over 20T |  | Rusca | A200 |  |  |  |  | 8 | A2BC | [10 empty] | 8 | [6 empty] | 8 | 0 | ph
Hanneford, Michael |  | Labourer | Rusca | Rusca | A200 |  |  |  |  | 8 | A2ER |  | 8 | [15 empty] | 8 | 0 | cr
Hayes, Matthew |  | Labourer |  | Rusca | A200 |  |  |  |  | 8 | A2BC | [10 empty] | 8 | [6 empty] | 8 | 0 | ct
Hilton, Nathan |  | Labourer |  | Rusca | A100 |  |  |  |  | 8 | A1EA |  | 8 | [15 empty] | 8 | 0 | cr | Compaction tests
Hogan, Brenton |  | Truck Operator |  | Rusca | A200 |  |  |  |  | 8 | A2BA | [8 empty] | 8 | [8 empty] | 8 | 0 | ct
Hollyngsworth, Richard |  | Truck Driver over 20T |  | Rusca | A100 |  |  |  |  | 8 | A1BF |  | 8 | [15 empty] | 8 | 0 | cr
Ireland, Ben |  | Truck Driver over 20T |  | Rusca | A200 |  |  |  |  | 8 | A2BA | [8 empty] | 8 | [8 empty] | 8 | 0 | ct
Jarman, Russell | R&R | Labourer |  | Rusca | [24 empty] | 0 | 0 |  | FCR delivered on site
Jarrett, Mathew | A/L | Labourer |  | Rusca | [24 empty] | 0 | 0 |  | New 56m3
Jensen, Scott |  | Labourer |  | Rusca | A200 |  |  |  |  | 8 | A2BA | [8 empty] | 8 | [8 empty] | 8 | 0 | ct | 2nd 4m3
Jones, Wade |  | Operator-Exc up to 100BHP |  | Rusca | B100 |  |  |  |  | 8 | B1BA/2 |  |  | 8 | [14 empty] | 8 | 0 | bf
Kaye, Luke |  | Operator-Front End Loader |  | Rusca | A100 |  |  |  |  | 7 | A1BG |  |  | 7 | [14 empty] | 7 | 0 | cr
Land, Benjamin |  | Concreator |  | Rocktown | [5 empty] | 0 | [18 empty] | 0 | 0
Lewis, Andrew |  | Labourer |  | Rocktown | [5 empty] | 0 | [18 empty] | 0 | 0
Lyons, Dylan |  | Concreator |  | Rocktown | [5 empty] | 0 | [18 empty] | 0 | 0
Keighley, Shane | R&R | Operator-Exc over 100BHP |  | Rusca | [24 empty] | 0 | 0
McCaughey, Thomas |  | Carpenter |  | Rocktown | [5 empty] | 0 | [18 empty] | 0 | 0
McGuire, Bryan |  | Labourer |  | Rocktown | [5 empty] | 0 | [18 empty] | 0 | 0
McIvor, Cathal |  | Concreator |  | Rocktown | [5 empty] | 0 | [18 empty] | 0 | 0
McKeown, Mark |  |  |  | Rocktown | [5 empty] | 0 | [18 empty] | 0 | 0
Kelly, Joseph |  | Truck Driver over 20T |  | Rusca | A200 |  |  |  |  | 8 | A2ER |  | 8 | [15 empty] | 8 | 0 | cr
Merta, Tully |  | Operator |  | Rocktown | [5 empty] | 0 | [18 empty] | 0 | 0
Morey, Paul |  |  |  | Rocktown | [5 empty] | 0 | [18 empty] | 0 | 0
Knight, Brenton |  | Operator-Exc over 100BHP |  | Rusca | B100 |  |  |  |  | 8 | B1BA/2 |  |  | 8 | [14 empty] | 8 | 0 | bf
O'Kane, Mark |  | Truck Driver |  | Rocktown
O'Toole, Martyn |  | Carpenter |  | Rocktown | [5 empty] | 0 | [18 empty] | 0 | 0
Maddaford, Michael | R&R | Operator-Exc over 100BHP |  | Rusca | [24 empty] | 0 | 0
Mayo, Peter |  | Labourer |  | Rusca | A100 |  |  |  |  | 8 | A1BG | [11 empty] | 8 | [5 empty] | 8 | 0 | bf
Murphy, Michael | R&R | Operator-Exc over 100BHP |  | Rusca | [24 empty] | 0 | 0
McQuillan, Dean | A/L | Operator-Backhoe |  | Rusca | [24 empty] | 0 | 0
Nibbs, Simon |  | Truck Driver over 20T |  | Rusca | A100 |  |  |  |  | 8 | A1BH |  | 8 | [15 empty] | 8 | 0 | cr
Perry, Brendan |  | Operator-Front End Loader |  | Rusca | B100 |  |  |  |  | 8 | B1BA/2 |  |  | 8 | [14 empty] | 8 | 0 | bf
Perry, Samuel |  | Operator-Front End Loader |  | Rusca | EMA |  |  |  |  | 8 |  |  |  | 4 | 4 | [13 empty] | 8 | 0
Pullen, Taylor |  | Labourer |  | Rusca | A100 |  |  |  |  | 8 | A1EN |  | 8 | [15 empty] | 8 | 0
Rhodes, Dillon | Sick | Truck Driver over 20T |  | Rusca | [24 empty] | 0 | 0
Robins, Jay |  | Labourer |  | Rusca | A100 |  |  |  |  | 8 | A1EN |  | 8 | [15 empty] | 8 | 0 | cr
Roe, Jason |  | Labourer |  | Rusca | [5 empty] | 8 | A2BC | [10 empty] | 8 | [6 empty] | 8 | 0 | ph
Sandersen, Shane |  | Operator-Exc over 100BHP |  | Rusca | A100 |  |  |  |  | 8 | A1EA |  | 8 | [15 empty] | 8 | 0 | ct
Williams, John |  | Operator |  | Rocktown | [5 empty] | 0 | [18 empty] | 0 | 0
Saveka, Joshua | R&R | Labourer |  | Rusca | [24 empty] | 0 | 0
Smiler, Kristopher |  | Labourer |  | Rusca | A100 |  |  |  |  | 8 | A1BG | [11 empty] | 8 | [5 empty] | 8 | 0 | bf
Stephens, Matthew | R&R | Labourer |  | Rusca | [24 empty] | 0 | 0
Tootoo, Quincy |  | Labourer |  | Rusca | E600 |  |  |  |  | 8 | E600 | Enviro | [5 empty] | 8 | [10 empty] | 8 | 0
Triplett, Anthony |  | Operator-Backhoe |  | Rusca | A200 |  |  |  |  | 8 | A2BC | [10 empty] | 8 | [6 empty] | 8 | 0
Tsapalianas, George |  | Labourer |  | Rusca | B100 |  |  |  |  | 8 | B1BA/2 |  |  | 3 | [8 empty] | 5 | [5 empty] | 8 | 0 | bf
Williams, Ronald |  | Labourer |  | Rusca | A100 |  |  |  |  | 8 | A1ED | [9 empty] | 8 | [7 empty] | 8 | 0 | cr
Williamson, Andrew | Sick | Operator-Exc over 100BHP |  | Rusca | [24 empty] | 0 | 0
Wilson, Victor |  | Operator-Exc over 100BHP |  | Rusca | A100 |  |  |  |  | 8 | A1EA |  | 8 | [15 empty] | 8 | 0 | cr
Wynn, Benjamin | R&R | Operator-Exc over 100BHP |  | Rusca | [24 empty] | 0 | 0
Zeiser, Michael |  | Operator-Exc over 100BHP |  | Rusca | A200 |  |  |  |  | 8 | A2BA | [8 empty] | 8 | [8 empty] | 8 | 0 | ct
[10 empty] | 0 | [18 empty] | 0 | 0
[10 empty] | 0 | [18 empty] | 0 | 0
[10 empty] | 0 | [18 empty] | 0 | 0
[10 empty] | 0 | [18 empty] | 0 | 0
[10 empty] | 0 | [18 empty] | 0 | 0
[10 empty] | 0 | [18 empty] | 0 | 0
[10 empty] | 0 | [18 empty] | 0 | 0
[10 empty] | 0 | [18 empty] | 0 | 0
[10 empty] | 0 | [18 empty] | 0 | 0
[10 empty] | 0 | [18 empty] | 0 | 0
[10 empty] | 0 | [18 empty] | 0 | 0
[10 empty] | 0 | [18 empty] | 0 | 0
[10 empty] | 0 | [18 empty] | 0 | 0
[10 empty] | 0 | [18 empty] | 0 | 0
[10 empty] | 0 | [18 empty] | 0 | 0
[10 empty] | 0 | [18 empty] | 0 | 0
[10 empty] | 0 | [18 empty] | 0 | 0
[10 empty] | 0 | [18 empty] | 0 | 0
[10 empty] | 0 | [18 empty] | 0 | 0
[10 empty] | 0 | [18 empty] | 0 | 0
Total | [9 empty] | 343 |  |  | 110 | 49 | 16 | 0 | 0 | 32 | 16 | 35 | 19 | 35 | 31 | 0 | 0 | 0 | 0 | 0 | 343
Standown due to Rain and Lightning - Time Start and Time Finish e.g. Red alert from 1pm to 3.30pm | [10 empty] | Constraint Code | Sub Crew Group | Enter hours Applicable to the Constraint Below for each FWBS. Enter time as actual hours only i.e. not cumulative manhours. Subcrew group must be filled in. | [15 empty] | Enter Description of Constraint in Field Below
0
Supervisor / Supt General Comments / proposal for Improvement / Action Required: | [28 empty] | 0
0
0
Plant & Equipment | [28 empty] | Area/Activity
Column1 | Column2 | Column3 | Column4 | Column5 | No | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23 | Column233 | Column234 | Column232 | Column2322 | Column24 | Column25 | Column26 | Column27 | Column28 | Column35 | Column352 | Column353 | Column36 | Column37 | Column372 | Column38
Type | Model | Plant Nos | Column21 | Area/Crew | No | FWBS | Company | Start | Finish | Hours |  | Comments | EXC | SAND | BF | DSPL | MIN FN | SF&S | SI | SI | SI | SI | SI | SI | SI |  | EV | EV | Area |  | Activity
VAC TRUCK |  | HV17 |  | A1BG | [5 empty] | 8 |  |  | 8 | [15 empty] | 8 |  | cr
VAC TRUCK |  | KH004 |  | A1ED | [5 empty] | 8 | [10 empty] | 8 | [7 empty] | 8 |  | cr
VAC TRUCK |  | KH007 |  | A1BH | [5 empty] | 8 |  |  | 8 | [15 empty] | 8 |  | cr
VAC TRUCK |  | KH008 |  | A1BG | [5 empty] | 8 |  |  | 8 | [15 empty] | 8 |  | cr
VAC TRUCK |  | KH014 |  | A2BA | [5 empty] | 8 | [9 empty] | 8 | [8 empty] | 8 |  | ct
VAC TRUCK |  | KH019 |  | A2BC | [5 empty] | 8 | [11 empty] | 8 | [6 empty] | 8 |  | ph
VAC TRUCK |  | BRK20 |  | A1BF | [5 empty] | 8 |  |  | 8 | [15 empty] | 8 |  | cr
VAC TRUCK |  | BRK23 |  | A2BG | [5 empty] | 8 |  |  | 8 | [15 empty] | 8 |  | cr
VAC TRUCK |  | BRK021 |  | A2BA | [5 empty] | 8 | [9 empty] | 8 | [8 empty] | 8 |  | ct
VAC TRUCK |  | VAC1 | [26 empty] | 0
VAC TRUCK |  | CCP 134 |  | E600 | [5 empty] | 8 | [7 empty] | 8 | [10 empty] | 8
VAC TRUCK |  | VT506 | [7 empty] | 8 |  |  | 8 | [15 empty] | 8 |  | cr
VAC TRUCK |  | VT507 |  | A1EN | [5 empty] | 8 |  |  | 8 | [15 empty] | 8 |  | cr
VAC TRUCK |  | VT508 |  | A1EA | [5 empty] | 8 |  |  | 8 | [15 empty] | 8 |  | cr
BODY WATERCART |  | TR07 |  | Sitewide | [5 empty] | 8 |  |  | 2 | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1 | [5 empty] | 8
EXCAVATOR 11T |  | EX001 | [26 empty] | 0
EXCAVATOR 11T |  | EX002 | [26 empty] | 0
EXCAVATOR 5T |  | EX024 |  | A1BH | [5 empty] | 8 | [8 empty] | 8 | [9 empty] | 8 |  | bf
EXCAVATOR 3.5T |  | B26 |  | A2BC | [5 empty] | 8 | [11 empty] | 8 | [6 empty] | 8 |  | ct
EXCAVATOR 3.5T |  | E32 |  | A1BG | [5 empty] | 8 |  |  | 8 | [15 empty] | 8
EXCAVATOR 1.4T |  | E018 | [26 empty] | 0 |  | ct
TRUCK |  | T10 | [26 empty] | 0
TRUCK |  | T7 | [26 empty] | 0
TRUCK |  | T18 |  | B100 | A100 |  |  |  |  | 8 |  |  |  | 3 | [8 empty] | 5 | [5 empty] | 8
TRUCK |  | T20 | [26 empty] | 0
TRUCK 5T |  | KH09 |  | A200 | B100 |  |  |  |  | 8 |  |  |  | 4 | 4 |  | 0 |  |  |  | 0 | [7 empty] | 8
TRUCK - DEWATER |  | KH13 |  | A200 | A100 |  |  |  |  | 8 |  |  |  | 4 | 4 | [13 empty] | 8
POZI TRACK |  | LSH002 |  | A200 | [5 empty] | 8 |  |  |  | 4 |  |  |  | 4 | [10 empty] | 8
POZI TRACK |  | 326 | [26 empty] | 0
POZI TRACK |  | CRS3947 |  | A100 | [5 empty] | 8 | [12 empty] | 8 | [5 empty] | 8
POZI TRACK |  | B23 |  | B1BA/1 | [5 empty] | 8 |  |  |  | 8 | [14 empty] | 8
HILUX UTE |  | LV077 |  | A100 | A200 |  |  |  |  | 8 |  |  | 3 | 1 | 1 | [5 empty] | 1 | 1 | 1 | [5 empty] | 8
HILUX UTE |  | LV084 |  | A100 | EMA | C400 |  |  |  | 8 |  |  | 6 | [5 empty] | 1 | 1 | [8 empty] | 8
HILUX UTE - FUEL TRAILER |  | LVH002 |  | Site wide | [5 empty] | 8 |  |  | 2 | 2 | 1 |  |  |  |  | 1 | 1 | 1 | [6 empty] | 8
HILUX UTE |  | LVH003 |  | A100 | [5 empty] | 8 | [8 empty] | 8 | [9 empty] | 8
CREW TRUCK |  | LV037 |  | B1BA/2 | [5 empty] | 8 |  |  |  | 8 | [14 empty] | 8
CREW TRUCK |  | LV081 |  | A1BG | [5 empty] | 8 |  |  | 4 | [9 empty] | 4 | [5 empty] | 8
CREW TRUCK |  | TR083 |  | E600 | [5 empty] | 8 |  |  | 4 |  |  |  |  | 4 | [10 empty] | 8
LOADER |  | LD009 |  | EMA | [5 empty] | 8 |  |  |  | 3 | 3 | 2 | [12 empty] | 8
PLATE COMPACTOR |  | 500kg |  | A2BC | [5 empty] | 8 | [12 empty] | 8 | [5 empty] | 8
PLATE COMPACTOR |  | 300kg |  | A2BD | [5 empty] | 8 |  |  |  | 4 | 4 | [13 empty] | 8
PLATE COMPACTOR |  | 90g |  | A2BC | [24 empty] | 0
JUMPING JACK |  | JACK 01 |  | B100 | [24 empty] | 0
FLEXI PUMP |  | FLEX | [26 empty] | 0
GENERATOR |  | GEN |  | B100 | [5 empty] | 8 |  |  |  | 8 | [14 empty] | 8
CONVEYORS |  | CONV x 3 | [26 empty] | 0
JACK HAMMER |  | HAM 001 | [26 empty] | 0
JACK HAMMER |  | HAM 002 | [26 empty] | 0
JACK HAMMER |  | HAM 003 | [26 empty] | 0
CONCRETE CUT SAW |  | SAW 01 | [26 empty] | 0
CONCRETE CUT SAW |  | SAW 02 | [26 empty] | 0
ROLLER 2.5T |  | RLK 003 | [26 empty] | 0
ROCK BREAKER |  | RBR | [26 empty] | 0
|  | Conveyors x 5 | [26 empty] | 0
|  | Generator | [26 empty] | 0
Total | [8 empty] | 0 | 272 | 0 | 0 | 93 | 50 | 18 | 2 | 0 | 16 | 17 | 19 | 11 | 19 | 27 | 0 | 0 | 0 | 0 | 0 | 272
[10 empty] | 0 | [18 empty] | 0
[10 empty] | 0 | [18 empty] | 0 | 0
[10 empty] | 0 | [18 empty] | 0 | 0
[8 empty] | 0 | 0 | 0 | [18 empty] | 34 | -34 | 0 | 0 |  |  | 0 | 0 |  | 0
[10 empty] | 0 | [18 empty] | 34 | -34 | 0 | 0 |  |  | 0 | 0 |  | 0
Details of Additional / Non Scope Activities | [11 empty] | Hours | Dayworks # |  | SI / EV # |  | Details of Additional / Non Scope Activities | [14 empty] | Hours |  | Dayworks # |  |  | SI / EV #
Back fill cable trench A1BG CVL 3 and ELE 1 Align | [11 empty] | 31 | 61895 |  | 711 | [21 empty] | 0
SI #1288
Excavate for cable coil under U ditch with Vac truck A1ED | [11 empty] | 19 | 61896 |  | 711
Excavate earthing trenches with Vac trucks A2BA | [11 empty] | 35 | 61898 |  | 1288 | [16 empty] | 0 |  |  |  |  | 0
|  | Pot hole with Vac truck A2BC to locate cables so that excavator can dig earth trench | [9 empty] | 35 | 61897 |  | 1288 | [16 empty] | 0 |  |  |  |  | 0
Excavate earthing trench western side of A1BH module | [11 empty] | 16 | 61894 |  | FI
SI #1288
Note on AE10: Drew Dunn: Auto Populate

## Code Print SHeet
Code | Construction Activities Description |  |  | Code | Type of Constraint - Daily Timesheet Reporting (DRS)
| Instrument Works |  |  | S1 | Wet Weather / Lightning Stoppages
7110 | 7110 - Panel, Rack and Cabinet | 1 |  | S2 | Permit Not Available (Be Specific)
7120 | 7120 - Control Systems / Computer System | 1 |  | S3 | Scaffolding Not Available (Refer to and Attach Specific Scaff Request)
7150 | 7150 - Cable Way | 1 |  | S4 | Free Issue Materials Not Available (Refer to and Attach Specific CMIV)
7160 | 7160 - Cable | 1 |  | S5 | Unnamed Cyclone (Tie down and clean up)(BEFORE/AFTER Red Alert Event)
7170 | 7170 - Cable Entry Sealing | 1 |  | S6 | Priority given to other Contractors / Redirection by JKC/others (Instructed to cease work and relocate resources) E.G. Hydrotesting in the area, lifting operations in the area etc.
7310 | 7310 - Local Instrument | 1 |  | S7 | Cranage Not Available (Beyond Kentz obligation(<50T))
7320 | 7320 - Local Panel and Enclosure | 1 |  | S8 | Waiting on Client QA/QC (For Hold Points Only, Refer to and Attach Specific RFI)
7510 | 7510 - Pipe Mount Type | 1 |  | S9 | Vendor Service Person Not Available
7520 | 7520 - Self-Standing Type | 1 |  | S10 | High Winds
7530 | 7530 - Analyser 3-Side Shelter | 1 |  | S11 | Stop Work Authority Enacted
7540 | 7540 - Analyser House | 1 |  | S12 | Crew Stand Down - Compassionate
7550 | 7550 - Sample Conditioning Rack | 1 |  | S13 | Emergency Evacuation / Drill (JKC or Kentz)
7811 | 7811 - Cable Way | 1 |  | S14 | SIMOPS with Commissioning (Specific instances where works are impacted and Kentz Construction are required to cease and relocate resources)
7812 | 7812 - Cable Laying | 1 |  | S15 | Kentz Rework
7813 | 7813 - Termination and Cable Gland Installation for Main Cable | 1 |  | S16 | Communications Drop Out (E.g. Cable Pulling Work Temp. Suspended)
7815 | 7815 - Junction Box | 1 |  | S17 | Downtime for rehydration breaks
7821 | 7821 - Cable Way | 1 |  | S18 | Dewatering Trenches Excavated by ELE-1
7822 | 7822 - Branch Cabling and Cable Gland Installation | 1 |  | S19 | Spare
7830 | 7830 - Impulse Tubing and Tracing | 1 |  | S20 | Spare
7840 | 7840 - Air Piping and Tubing | 1 |  | S21 | Spare
7850 | 7850 - Support Fabrication | 1 |  | S22 | Spare
7861 | 7861 - Supply and Install Tag No. Plate / Labels | 1 |  | S23 | Spare
7863 | 7863 - Polymeric Cable Protection Cover (to AS 4702) | 1 |  | S24 | Spare
7864 | 7864 - Instrument Protection | 1
7865 | 7865 - Cable Route Marker | 1 |  | P1 | Disruption to Works caused by Client and/or Other Subcontractor (Note: We can continue to work in this instance)
7866 | 7866 - Cable Marker (to AS/NZS 2648.1) | 1 |  | P2 | Spare
7867 | 7867 - Excavation | 1 |  | P3 | Spare
7868 | 7868 - Backfilling | 1 |  | P4 | Spare
7869 | 7869 - Minor Foundations | 1 |  | P5 | Spare
7870 | 7870 - Support For Piping Flushing Activities | 1
7920 | 7920 - Function Testing | 1 |  | K1 | Plant/Equipment Breakdowns (unforseen)
7930 | 7930 - Precommissioning Checks | 1 |  | K2 | Material Not Available
| Electrical Works |  |  | K3 | Equipment Unavailable
8110 | 8110 - Generator & Associated Equipment | 2 |  | K4 | Transport Unavailable
8120 | 8120 - Transformer, Harmonic Filter and Neutral Earthing Resistor | 2 |  | K5 | QA/QC Not Available for inspections
8130 | 8130 - Gas Insulated Switchgear (GIS) installed inside LER by Module Fabricator | 2 |  | K6 | Spare
8140 | 8140 - SWITCHGEAR AND MCC | 2 |  | K7 | Spare
8150 | 8150 - UPS system | 2 |  | K8 | Spare
8160 | 8160 - Bus Duct | 2 |  | K9 | Spare
8170 | 8170 - Control, Distribution & Misc Panels | 2 |  | K10 | Spare
8180 | 8180 - Power Distribution Control System (PDCS) | 2
8191 | 8191 - LER Receipt | 2
8192 | 8192 - LIR Receipt | 2
8220 | 8220 - Local Equipment (Outside) | 2
8260 | 8260 - Power and Control Cabling | 2
8271 | 8271 - Termination of Cable (including Compound Filled Gland) | 2
8272 | 8272 - Termination of Cables (including Non Compound Filled Gland) | 2
8273 | 8273 - Splicing of cable | 2
8280 | 8280 - Cable Way | 2
8295A | 8295A - Excavation | 2
8295B | 8295B - Sand Filling | 2
8295C | 8295C - Back Filling | 2
8295D | 8295D - Polymeric Cable Protection Cover (to AS 4702) | 2
8295E | 8295E - Cable Marker (to AS/NZS 2648.1) | 2
8295F | 8295F - Stub-up PVC conduit | 2
8295G | 8295G - Disposal | 2
8296 | 8296 - Cable Route Markers | 2
8297 | 8297 - Minor Foundations | 2
8298 | 8298 - Fabrication of Supports For Cableway and Cable Supports | 2
8299 | 8299 - Installation of Miscellaneous Supports | 2
8320 | 8320 - Lighting in Plant | 2
8330 | 8330 - Street, Fence, Security | 2
8340 | 8340 - Aircraft Obstacle Light | 2
8350 | 8350 - Navigation Light | 2
8395A | 8395A - Excavation | 2
8395B | 8395B - Sand Filling | 2
8395C | 8395C - Back Filling | 2
8395D | 8395D - Polymeric Cable Protection CoverTile (to AS 4702) | 2
8395E | 8395E - Cable Warning Marker Sheet (to AS/NZS 2648.1) | 2
8395F | 8395F - Disposal | 2
8396 | 8396 - Cable Route Marker | 2
8410 | 8410 - Wiring of Earthing | 2
8420 | 8420 - Earthing Electrode | 2
8430 | 8430 - Connection to Equipment | 2
8440 | 8440 - Air Terminal | 2
8490 | 8490 - Other Work | 2
Communications Works
8610 | 8610 - Wired System | 3
8620 | 8620 - Wireless System | 3
8630 | 8630 - LAN/WAN & Data Communication System | 3
8640 | 8640 - Other Communication System | 3
8650 | 8650 - Nurse Call /Distress System | 3
8660 | 8660 - Cabling | 3
8670 | 8670 - Termination/Splicing of Cable | 3
8680 | 8680 - Cable Way | 3
8695A | 8695A - Excavation of Cable Trench | 3
8695B | 8695B - Manual Excavation of buried coiled cables | 3
8695C | 8695C - Sand Filling | 3
8695E | 8695E - Back Filling | 3
8695F | 8695F - Polymeric Cable Protection CoverTile (to AS 4702) | 3
8695G | 8695G - Cable Warning Marker Sheet (to AS/NZS 2648.1) | 3
8695H | 8695H - Disposal | 3
8696 | 8696 - Cable Route Marker | 3
8697 | 8697 - Pole and Mast | 3
8710 | 8710 - Impressed current cathodic protection | 2
8720 | 8720 - Sacrificial Anode System | 2
8793 | 8793 - Soil Access Box | 2
8795Aa | 8795Aa - Excavation | 2
8795Ab | 8795Ab - Manual Excavation of buried coiled cables | 2
8795B | 8795B - Sand Filling | 2
8795C | 8795C - Back Filling | 2
8795D | 8795D - Cable Protection Tile | 2
8795E | 8795E - Cable Warning Sheet (Polymeric cable tile) | 2
8796 | 8796 - Cable Route Marker | 2
8810 | 8810 - Heater Panel | 2
8820 | 8820 - Heating Element | 2
8860 | 8860 - Cabling - Low Voltage | 2
8870 | 8870 - Termination | 2
8910 | 8910 - Precommissioning Checks | 2
8920 | 8920 - Function Testing | 3
FMIT | QAQC Field Material Inspections & Testing
4
Bill 4 | Bill No. 4 - ELE-1 Preservation Tabulation | 4
Bill 5 | Bill No. 5 - ELE-1 Commissioning Support Tabulation | 4
6410 | IPCQ - Minor Subcontract Works | 4
6420 | CBI - Minor Subcontract Works | 4
6430 | KAEFER - Minor Subcontract Works | 4
Code | Other Activities
5
31X22a | Maintenance crew for plant and electrics | 5
31X22c | Driver / operators for sundry plant and equipment | 5
31W2 | Training | 5
31X19 | Material Control / Stores Personnel | 5
31X21 | Peggys | 5
TEMP | Site Facilities & Services | 5
SI | SI # | 6 | Site Instruction
EV | EV # | 6 | Event, other work not covered under SI

## FWBS List
Code | Construction Activities Description
Instrument Works
7110 | 7110 - Panel, Rack and Cabinet | 1
7120 | 7120 - Control Systems / Computer System | 1 |  | 7110 - Panel, Rack and Cabinet
7150 | 7150 - Cable Way | 1 |  | 7120 - Control Systems / Computer System
7160 | 7160 - Cable | 1 |  | 7150 - Cable Way
7170 | 7170 - Cable Entry Sealing | 1 |  | 7160 - Cable
7310 | 7310 - Local Instrument | 1 |  | 7170 - Cable Entry Sealing
7320 | 7320 - Local Panel and Enclosure | 1 |  | 7310 - Local Instrument
7510 | 7510 - Pipe Mount Type | 1 |  | 7320 - Local Panel and Enclosure
7520 | 7520 - Self-Standing Type | 1 |  | 7510 - Pipe Mount Type
7530 | 7530 - Analyser 3-Side Shelter | 1 |  | 7520 - Self-Standing Type
7540 | 7540 - Analyser House | 1 |  | 7530 - Analyser 3-Side Shelter
7550 | 7550 - Sample Conditioning Rack | 1 |  | 7540 - Analyser House
7811 | 7811 - Cable Way | 1 |  | 7550 - Sample Conditioning Rack
7812 | 7812 - Cable Laying | 1 |  | 7811 - Cable Way
7813 | 7813 - Termination and Cable Gland Installation for Main Cable | 1 |  | 7812 - Cable Laying
7815 | 7815 - Junction Box | 1 |  | 7813 - Termination and Cable Gland Installation for Main Cable
7821 | 7821 - Cable Way | 1 |  | 7815 - Junction Box
7822 | 7822 - Branch Cabling and Cable Gland Installation | 1 |  | 7821 - Cable Way
7830 | 7830 - Impulse Tubing and Tracing | 1 |  | 7822 - Branch Cabling and Cable Gland Installation
7840 | 7840 - Air Piping and Tubing | 1 |  | 7830 - Impulse Tubing and Tracing
7850 | 7850 - Support Fabrication | 1 |  | 7840 - Air Piping and Tubing
7861 | 7861 - Supply and Install Tag No. Plate / Labels | 1 |  | 7850 - Support Fabrication
7863 | 7863 - Polymeric Cable Protection Cover (to AS 4702) | 1 |  | 7861 - Supply and Install Tag No. Plate / Labels
7864 | 7864 - Instrument Protection | 1 |  | 7863 - Polymeric Cable Protection Cover (to AS 4702)
7865 | 7865 - Cable Route Marker | 1 |  | 7864 - Instrument Protection
7866 | 7866 - Cable Marker (to AS/NZS 2648.1) | 1 |  | 7865 - Cable Route Marker
7867 | 7867 - Excavation | 1 |  | 7866 - Cable Marker (to AS/NZS 2648.1)
7868 | 7868 - Backfilling | 1 |  | 7867 - Excavation
7869 | 7869 - Minor Foundations | 1 |  | 7868 - Backfilling
7870 | 7870 - Support For Piping Flushing Activities | 1 |  | 7869 - Minor Foundations
7920 | 7920 - Function Testing | 1 |  | 7870 - Support For Piping Flushing Activities
7930 | 7930 - Precommissioning Checks | 1 |  | 7920 - Function Testing
Electrical Works
8110 | 8110 - Generator & Associated Equipment | 2
8120 | 8120 - Transformer, Harmonic Filter and Neutral Earthing Resistor | 2
8130 | 8130 - Gas Insulated Switchgear (GIS) installed inside LER by Module Fabricator | 2
8140 | 8140 - SWITCHGEAR AND MCC | 2
8150 | 8150 - UPS system | 2
8160 | 8160 - Bus Duct | 2
8170 | 8170 - Control, Distribution & Misc Panels | 2
8180 | 8180 - Power Distribution Control System (PDCS) | 2
8191 | 8191 - LER Receipt | 2
8192 | 8192 - LIR Receipt | 2
8220 | 8220 - Local Equipment (Outside) | 2 |  | 7930 - Precommissioning Checks
8260 | 8260 - Power and Control Cabling | 2 |  | 8220 - Local Equipment (Outside)
8271 | 8271 - Termination of Cable (including Compound Filled Gland) | 2 |  | 8260 - Power and Control Cabling
8272 | 8272 - Termination of Cables (including Non Compound Filled Gland) | 2 |  | 8271 - Termination of Cable (including Compound Filled Gland)
8273 | 8273 - Splicing of cable | 2 |  | 8272 - Termination of Cables (including Non Compound Filled Gland)
8280 | 8280 - Cable Way | 2 |  | 8273 - Splicing of cable
8295A | 8295A - Excavation | 2 |  | 8280 - Cable Way
8295B | 8295B - Sand Filling | 2 |  | 8295A - Excavation
8295C | 8295C - Back Filling | 2 |  | 8295B - Sand Filling
8295D | 8295D - Polymeric Cable Protection Cover (to AS 4702) | 2 |  | 8295C - Back Filling
8295E | 8295E - Cable Marker (to AS/NZS 2648.1) | 2 |  | 8295D - Polymeric Cable Protection Cover (to AS 4702)
8295F | 8295F - Stub-up PVC conduit | 2 |  | 8295E - Cable Marker (to AS/NZS 2648.1)
8295G | 8295G - Disposal | 2 |  | 8295F - Stub-up PVC conduit
8296 | 8296 - Cable Route Markers | 2 |  | 8295G - Disposal
8297 | 8297 - Minor Foundations | 2 |  | 8296 - Cable Route Markers
8298 | 8298 - Fabrication of Supports For Cableway and Cable Supports | 2 |  | 8297 - Minor Foundations
8299 | 8299 - Installation of Miscellaneous Supports | 2 |  | 8298 - Fabrication of Supports For Cableway and Cable Supports
8320 | 8320 - Lighting in Plant | 2 |  | 8299 - Installation of Miscellaneous Supports
8330 | 8330 - Street, Fence, Security | 2 |  | 8320 - Lighting in Plant
8340 | 8340 - Aircraft Obstacle Light | 2
8350 | 8350 - Navigation Light | 2 |  | 8330 - Street, Fence, Security
8395A | 8395A - Excavation | 2 |  | 8350 - Navigation Light
8395B | 8395B - Sand Filling | 2 |  | 8395A - Excavation
8395C | 8395C - Back Filling | 2 |  | 8395B - Sand Filling
8395D | 8395D - Polymeric Cable Protection CoverTile (to AS 4702) | 2 |  | 8395C - Back Filling
8395E | 8395E - Cable Warning Marker Sheet (to AS/NZS 2648.1) | 2 |  | 8395D - Polymeric Cable Protection CoverTile (to AS 4702)
8395F | 8395F - Disposal | 2 |  | 8395E - Cable Warning Marker Sheet (to AS/NZS 2648.1)
8396 | 8396 - Cable Route Marker | 2 |  | 8395F - Disposal
8410 | 8410 - Wiring of Earthing | 2 |  | 8396 - Cable Route Marker
8420 | 8420 - Earthing Electrode | 2 |  | 8410 - Wiring of Earthing
8430 | 8430 - Connection to Equipment | 2 |  | 8420 - Earthing Electrode
8440 | 8440 - Air Terminal | 2 |  | 8430 - Connection to Equipment
8490 | 8490 - Other Work | 2 |  | 8440 - Air Terminal
Communications Works
8610 | 8610 - Wired System | 3 |  | 8490 - Other Work
8620 | 8620 - Wireless System | 3 |  | 8610 - Wired System
8630 | 8630 - LAN/WAN & Data Communication System | 3 |  | 8620 - Wireless System
8640 | 8640 - Other Communication System | 3 |  | 8630 - LAN/WAN & Data Communication System
8650 | 8650 - Nurse Call /Distress System | 3 |  | 8640 - Other Communication System
8660 | 8660 - Cabling | 3 |  | 8650 - Nurse Call /Distress System
8670 | 8670 - Termination/Splicing of Cable | 3 |  | 8660 - Cabling
8680 | 8680 - Cable Way | 3 |  | 8670 - Termination/Splicing of Cable
8695A | 8695A - Excavation of Cable Trench | 3 |  | 8680 - Cable Way
8695B | 8695B - Manual Excavation of buried coiled cables | 3 |  | 8695A - Excavation of Cable Trench
8695C | 8695C - Sand Filling | 3 |  | 8695B - Manual Excavation of buried coiled cables
8695E | 8695E - Back Filling | 3 |  | 8695C - Sand Filling
8695F | 8695F - Polymeric Cable Protection CoverTile (to AS 4702) | 3 |  | 8695E - Back Filling
8695G | 8695G - Cable Warning Marker Sheet (to AS/NZS 2648.1) | 3 |  | 8695F - Polymeric Cable Protection CoverTile (to AS 4702)
8695H | 8695H - Disposal | 3 |  | 8695G - Cable Warning Marker Sheet (to AS/NZS 2648.1)
8696 | 8696 - Cable Route Marker | 3 |  | 8695H - Disposal
8697 | 8697 - Pole and Mast | 3 |  | 8696 - Cable Route Marker
8710 | 8710 - Impressed current cathodic protection | 2 |  | 8697 - Pole and Mast
8720 | 8720 - Sacrificial Anode System | 2 |  | 8710 - Impressed current cathodic protection
8793 | 8793 - Soil Access Box | 2 |  | 8720 - Sacrificial Anode System
8795Aa | 8795Aa - Excavation | 2 |  | 8810 - Heater Panel
8795Ab | 8795Ab - Manual Excavation of buried coiled cables | 2 |  | 8820 - Heating Element
8795B | 8795B - Sand Filling | 2 |  | 8860 - Cabling - Low Voltage
8795C | 8795C - Back Filling | 2 |  | 8870 - Termination
8795D | 8795D - Cable Protection Tile | 2 |  | 8910 - Precommissioning Checks
8795E | 8795E - Cable Warning Sheet (Polymeric cable tile) | 2
8796 | 8796 - Cable Route Marker | 2
8810 | 8810 - Heater Panel | 2
8820 | 8820 - Heating Element | 2
8860 | 8860 - Cabling - Low Voltage | 2
8870 | 8870 - Termination | 2
8910 | 8910 - Precommissioning Checks | 2
8920 | 8920 - Function Testing | 3
FMIT | QAQC Field Material Inspections & Testing
4
Bill 4 | Bill No. 4 - ELE-1 Preservation Tabulation | 4
Bill 5 | Bill No. 5 - ELE-1 Commissioning Support Tabulation | 4
6410 | IPCQ - Minor Subcontract Works | 4
6420 | CBI - Minor Subcontract Works | 4
6430 | KAEFER - Minor Subcontract Works | 4
Code | Other Activities
5
31X22a | Maintenance crew for plant and electrics | 5
31X22c | Driver / operators for sundry plant and equipment | 5
31W2 | Training | 5
31X19 | Material Control / Stores Personnel | 5
31X21 | Peggys | 5
TEMP | Site Facilities & Services | 5
SI | SI # | 6 | Site Instruction
EV | EV # | 6 | Event, other work not covered under SI

## Chart Master
Row Labels
8000 - ELECTRICAL
8100 - POWER GENERATOR & SUBSTATION
8110 - Generator & Associated Equipment
8112 - Emergency Generator (2214kW)
(blank)
(blank)
(blank)
8120 - Transformer, Harmonic Filter and Neutral Earthing Resistor
8121 - Transformer (nonfield assembly)
(blank)
(blank)
(blank)
8122 - Transformer (Field Assembly)
8122A - 10 MVA
(blank)
(blank)
8122B - 16 MVA
(blank)
(blank)
8122C - 18 MVA
(blank)
(blank)
8122D - 20 MVA
(blank)
(blank)
8122E - 22 MVA
(blank)
(blank)
8122F - 30 MVA
(blank)
(blank)
8122G - 26.3 MVA & 26.4 MVA
(blank)
(blank)
8122H - 50.3 MVA
(blank)
(blank)
8122I - 68.6 MVA (Earthing Transformer)
(blank)
(blank)
8122J - 95 MVA with OLTC
(blank)
(blank)
8122K - 160 MVA and above with OLTC
(blank)
(blank)
8122L - 2.8 MVA
(blank)
(blank)
8122M - 3.9 MVA
(blank)
(blank)
8126 - Harmonic Filter
8126A - 4 Branch Filter Bank 8MVA
(blank)
(blank)
8126B - 4 Branch Filter Bank 17MVA
(blank)
(blank)
8127 - Outdoor Harmonic Filter Resistor
(blank)
(blank)
(blank)
8128 - Neutral Earthing Resistor (NER)
8128A - 6.6kV
(blank)
(blank)
8128B - 33kV
(blank)
(blank)
8128C - 132kV
(blank)
(blank)
8130 - Gas Insulated Switchgear (GIS) installed inside LER by Module Fabricator
No Code
8130A - 132kV GIS
(blank)
(blank)
8130B - 33kV GIS
(blank)
(blank)
8130C - Below 33kV GIS
(blank)
(blank)
8140 - SWITCHGEAR AND MCC
8141 - Switchgear and MCC installed inside LER by Module Fabricator
8141A - Low Vol. Switchgear
(blank)
(blank)
8141B - Low Vol. MCC
(blank)
(blank)
8141C - 6 KV to 14.6 KV Switchgear and MCC
(blank)
(blank)
8141D - 15 KV to 40.5 KV Switchgear
(blank)
(blank)
8142 - Switchgear and MCC installed inside buildings at Site
8142A - Low Vol. Switchgear
(blank)
(blank)
8142B - Low Vol. MCC
(blank)
(blank)
8150 - UPS system
8151 - UPS installed inside LER/LIR by Module Fabricator
8151A - AC UPS
8151AA - Single Type
(blank)
8151AB - Dual Type
(blank)
8151B - DC UPS
8151BA - Single Type
(blank)
8151BB - Dual Type
(blank)
8152 - UPS installed inside Buildings at Site
8152A - AC UPS
8152AA - Single Type
(blank)
8152AB - Dual Type
(blank)
8152B - DC UPS
8152BA - Single Type
(blank)
8152BB - Dual Type
(blank)
8153 - Battery Bank
8153A - Battery Cell Q'ty:0 to 49 cells
(blank)
(blank)
8153B - Battery Cell Q'ty:50 to 99 cells
(blank)
(blank)
8153C - Battery Cell Q'ty:100 to 149 cells
(blank)
(blank)
8153D - Battery Cell Q'ty:150 to 199 cells
(blank)
(blank)
8153E - Battery Cell Q'ty:200 to 249 cells
(blank)
(blank)
8153F - Battery Cell Q'ty:250 to 299 cells
(blank)
(blank)
8153G - Battery Cell Q'ty:300 to 349 cells
(blank)
(blank)
8153H - Battery Cell Q'ty:350 to 399 cells
(blank)
(blank)
8153I - Battery Cell Q'ty:400 to 449 cells
(blank)
(blank)
8153J - Battery Cell Q'ty:450 to 499 cells
(blank)
(blank)
8153K - Battery Cell Q'ty:500 to 549 cells
(blank)
(blank)
8153L - Battery Cell Q'ty:550 to 599 cells
(blank)
(blank)
8153M - Battery Cell Q'ty:600 to 649 cells
(blank)
(blank)
8153N - Battery Cell Qty 972
(blank)
(blank)
8160 - Bus Duct
8161 - LV Bus Duct
8161A - L= 5m & Below
(blank)
(blank)
8161B - L= 5.1m to 10m
(blank)
(blank)
8161C - L= 10.1m to 15m
(blank)
(blank)
8161D - L= 15m Over
(blank)
(blank)
8162 - 6.6kV Bus Duct
8162A - L= 5m & Below
(blank)
(blank)
8162B - L= 5.1m to 10m
(blank)
(blank)
8162C - L= 10.1m to 15m
(blank)
(blank)
8162D - L= 15m Over
(blank)
(blank)
8163 - 33kV Bus Duct
8163A - L= 5m & Below
(blank)
(blank)
8163B - L= 5.1m to 10m
(blank)
(blank)
8163C - L= 10.1m to 15m
(blank)
(blank)
8163D - L= 15m Over
(blank)
(blank)
8170 - Control, Distribution & Misc Panels
8171 - Floor Mount Panel installed inside LER by Module Fabricator
8171A - Up to 800W panel
(blank)
(blank)
8171B - Above 800W panel
(blank)
(blank)
8173 - Floor Mount Panel installed at Site
8173A - Up to 800W panel
(blank)
(blank)
8173B - Above 800W panel
(blank)
(blank)
8172 - Wall-Mount Panel installed inside LER by Module Fabricator
(blank)
(blank)
(blank)
8174 - Wall-Mount Panel
(blank)
(blank)
(blank)
8180 - Power Distribution Control System (PDCS)
8181 - PDCS Controller Cabinet
8181A - PDCS Controller Cabinet installed at Site
(blank)
(blank)
8181B - PDCS Controller Cabinet installed by Module Fabricator
(blank)
(blank)
8182 - Human Machine Interface (HMI) Cabinet
8182A - Human Machine Interface (HMI) Cabinet installed at Site
(blank)
(blank)
8182B - Human Machine Interface (HMI) Cabinet installed by Module Fabricator
(blank)
(blank)
8183 - Load Shed Controller Cabinet
8183A - Load Shed Controller Cabinet installed at Site
(blank)
(blank)
8183B - Load Shed Controller Cabinet installed by Module Fabricator
(blank)
(blank)
8190 - Prefabricated Buildings and Auxliiaries
8191 - LER Receipt
8191A - Main Substation Modules (1) and (2)
(blank)
(blank)
8191B - VSDS LER
(blank)
(blank)
8191C - All Other LER
(blank)
(blank)
8192 - LIR Receipt
8192A - All LIR
(blank)
(blank)
8200 - POWER WORK
8210 - Motor and Motor Operated Valve (MOV)
8211 - Motor
(blank)
(blank)
(blank)
8214 - MOV
(blank)
(blank)
(blank)
8220 - Local Equipment (Outside)
8221 - Control Station
(blank)
(blank)
(blank)
8222 - Local Dist. Panel/Starter
(blank)
(blank)
(blank)
8224 - Local Control Panel for Package Equipment
(blank)
(blank)
(blank)
8225 - Power Junction Box
8225AA - Power Junction Box (less than 10000 mm2, e.g WxH 100mm x 100mm)
(blank)
(blank)
8225AB - Power Junction Box (less than 22500 mm2, e.g WxH 150mm x 150mm)
(blank)
(blank)
8225AC - Power Junction Box (less than 30000 mm2, e.g WxH 200mm x 150mm)
(blank)
(blank)
8225AD - Power Junction Box (less than 60000 mm2, e.g WxH 300mm x 200mm)
(blank)
(blank)
8225AE - Power Junction Box (less than 90000 mm2, e.g WxH 300mm x 300mm)
(blank)
(blank)
8225AF - Power Junction Box (less than 180000 mm2, e.g WxH 600mm x 300mm)
(blank)
(blank)
8225AG - Power Junction Box (greater than 180000 mm2, e.g WxH 900mm x 300mm)
(blank)
(blank)
8225BA - Ex d Power Junction Box (less than 10000 mm2, e.g WxH 100mm x 100mm)
(blank)
(blank)
8225BB - Ex d Power Junction Box (less than 22500 mm2, e.g WxH 150mm x 150mm)
(blank)
(blank)
8225BC - Ex d Power Junction Box (less than 30000 mm2, e.g WxH 200mm x 150mm)
(blank)
(blank)
8225BD - Ex d Power Junction Box (less than 60000 mm2, e.g WxH 300mm x 200mm)
(blank)
(blank)
8225BE - Ex d Power Junction Box (less than 90000 mm2, e.g WxH 300mm x 300mm)
(blank)
(blank)
8225BF - Ex d Power Junction Box (less than 180000 mm2, e.g WxH 600mm x 300mm)
(blank)
(blank)
8225BG - Ex d Power Junction Box (greater than 180000 mm2, e.g WxH 900mm x 300mm)
(blank)
(blank)
8223 - 3 Phase Power Outlet
(blank)
(blank)
(blank)
8260 - Power and Control Cabling
8261 - Cable
8261A - Low Voltage
8261Aa - 0.6/1kV _ Below 10sqmm
(blank)
8261Ab - 0.6/1kV _ 10sqmm to below 50sqmm
(blank)
8261Ac - 0.6/1kV _ 50sqmm to below 120sqmm
(blank)
8261Ad - 0.6/1kV _ 120sqmm to below 300mm2
(blank)
8261Ae - 0.6/1kV _ 300sqmm and above
(blank)
8261B - 1.8/3kV Cable
(blank)
(blank)
8261C - 3.6/6kV Cable
(blank)
(blank)
8261D - 6/10kV Cable
8261Da - 6/10kV Cable _ Below 70sqmm
8261Daa - 6/10kV Cable _ Below 70sqmm _ 3C
8261Dab - 6/10kV Cable _ Below 70sqmm _ 1C
8261Db - 6/10kV Cable _ 70sqmm to below 185sqmm
8261Dba - 6/10kV Cable _ 70sqmm to below 185sqmm _ 3C
8261Dbb - 6/10kV Cable _ 70sqmm to below 185sqmm _ 1C
8261Dc - 6/10kV Cable _ 185sqmm and above
8261Dca - 6/10kV Cable _ 185sqmm and above _ 3C
8261Dcb - 6/10kV Cable _ 185sqmm and above _ 1C
8261E - 19/33kV Cable
(blank)
(blank)
8261F - 45 KV to 72.5 KV Cable
(blank)
(blank)
8261G - 76/132kV Cable
8261Ga - 76/132kV _ Below 800sqmm
(blank)
8261Gb - 76/132kV _ 800sqmm and above
(blank)
8261H - Control
8261Ha - Control _ less than 8C
(blank)
8261Hb - Control _ 8C to less than 12C
(blank)
8261Hc - Control _ 12C to less than 20C
(blank)
8261Hd - Control _ 20C and more
(blank)
8261He - Control _ RTD Cable (5T)
(blank)
8261Hf - Control _ Fiber Optic Cable (2 to 6 Core)
(blank)
8261Hg - Control _ Fiber Optic Cable (7 to 12 Core)
(blank)
8261Hh - Control _ Fiber Optic Cable (24 Core)
(blank)
8261Hi - Control _ Fiber Optic Cable (36 Core)
(blank)
8261Hj - Control _ Fiber Optic Cable (48 Core)
(blank)
8261Hk - Control _ Fiber Optic Cable (60 Core)
(blank)
8261Hl - Control _ Fiber Optic Cable (72 Core)
(blank)
8263 - Cable (for when cable is installed and left coiled by other subcontractors)
8263A - Low Voltage
8263Aa - 0.6/1kV _ Below 10sqmm
(blank)
8263Ab - 0.6/1kV _ 10sqmm to below 50sqmm
(blank)
8263Ac - 0.6/1kV _ 50sqmm to below 120sqmm
(blank)
8263Ad - 0.6/1kV _ 120sqmm to below 300mm2
(blank)
8263Ae - 0.6/1kV _ 300sqmm and above
(blank)
8263B - 1.8/3kV Cable
(blank)
(blank)
8263C - 3.6/6kV Cable
(blank)
(blank)
8263D - 6/10kV Cable
8263Da - 6/10kV Cable _ Below 70sqmm
8263Daa - 6/10kV Cable _ Below 70sqmm _ 3C
8263Dab - 6/10kV Cable _ Below 70sqmm _ 1C
8263Db - 6/10kV Cable _ 70sqmm to below 185sqmm
8263Dba - 6/10kV Cable _ 70sqmm to below 185sqmm _ 3C
8263Dbb - 6/10kV Cable _ 70sqmm to below 185sqmm _ 1C
8263Dc - 6/10kV Cable _ 185sqmm and above
8263Dca - 6/10kV Cable _ 185sqmm and above _ 3C
8263Dcb - 6/10kV Cable _ 185sqmm and above _ 1C
8263E - 19/33kV Cable
(blank)
(blank)
8263F - 45 KV to 72.5 KV Cable
(blank)
(blank)
8263G - 76/132kV Cable
8263Ga - 76/132kV _ Below 800sqmm
(blank)
8263Gb - 76/132kV _ 800sqmm and above
(blank)
8263H - Control
8263Ha - Control _ less than 8C
(blank)
8263Hb - Control _ 8C to less than 12C
(blank)
8263Hc - Control _ 12C to less than 20C
(blank)
8263Hd - Control _ 20C and more
(blank)
8263He - Control _ RTD Cable (5T)
(blank)
8263Hf - Control _ Fiber Optic Cable (2 to 6 Core)
(blank)
8263Hg - Control _ Fiber Optic Cable (7 to 12 Core)
(blank)
8263Hh - Control _ Fiber Optic Cable (24 Core)
(blank)
8263Hi - Control _ Fiber Optic Cable (36 Core)
(blank)
8263Hj - Control _ Fiber Optic Cable (48 Core)
(blank)
8263Hk - Control _ Fiber Optic Cable (60 Core)
(blank)
8263Hl - Control _ Fiber Optic Cable (72 Core)
(blank)
8270 - Termination and Splicing of Cable
8271 - Termination of Cable (including Compound Filled Gland)
8271A - Low Voltage
8271Aa - 0.6/1kV _ Below 10sqmm
(blank)
8271Ab - 0.6/1kV _ 10sqmm to below 50sqmm
(blank)
8271Ac - 0.6/1kV _ 50sqmm to below 120sqmm
(blank)
8271Ad - 0.6/1kV _ 120sqmm to below 300mm2
(blank)
8271Ae - 0.6/1kV _ 300sqmm and above
(blank)
8271B - 1.8/3kV Cable
(blank)
(blank)
8271C - 3.6/6kV Cable
(blank)
(blank)
8271D - 6/10kV Cable
8271Da - 6/10kV Cable _ Below 70sqmm
8271Daa - 6/10kV Cable _ Below 70sqmm _ 3C
8271Dab - 6/10kV Cable _ Below 70sqmm _ 1C
8271Db - 6/10kV Cable _ 70sqmm to below 185sqmm
8271Dba - 6/10kV Cable _ 70sqmm to below 185sqmm _ 3C
8271Dbb - 6/10kV Cable _ 70sqmm to below 185sqmm _ 1C
8271Dc - 6/10kV Cable _ 185sqmm and above
8271Dca - 6/10kV Cable _ 185sqmm and above _ 3C
8271Dcb - 6/10kV Cable _ 185sqmm and above _ 1C
8271E - 19/33kV Cable
(blank)
(blank)
8271F - 45 KV to 72.5 KV Cable
(blank)
(blank)
8271G - 76/132kV Cable
8271Ga - 76/132kV _ Below 800sqmm
(blank)
8271Gb - 76/132kV _ 800sqmm and above
(blank)
8271H - Control
8271Ha - Control _ less than 8C
(blank)
8271Hb - Control _ 8C to less than 12C
(blank)
8271Hc - Control _ 12C to less than 20C
(blank)
8271Hd - Control _ 20C and more
(blank)
8271He - Control _ RTD Cable (5T)
(blank)
8271Hf - Control _ Fiber Optic Cable (2 to 6 Core)
(blank)
8271Hg - Control _ Fiber Optic Cable (7 to 12 Core)
(blank)
8271Hh - Control _ Fiber Optic Cable (24 Core)
(blank)
8271Hi - Control _ Fiber Optic Cable (36 Core)
(blank)
8271Hj - Control _ Fiber Optic Cable (48 Core)
(blank)
8271Hk - Control _ Fiber Optic Cable (60 Core)
(blank)
8271Hl - Control _ Fiber Optic Cable (72 Core)
(blank)
8272 - Termination of Cables (including Non Compound Filled Gland)
8272A - Low Voltage
8272Aa - 0.6/1kV _ Below 10sqmm
(blank)
8272Ab - 0.6/1kV _ 10sqmm to below 50sqmm
(blank)
8272Ac - 0.6/1kV _ 50sqmm to below 120sqmm
(blank)
8272Ad - 0.6/1kV _ 120sqmm to below 300mm2
(blank)
8272Ae - 0.6/1kV _ 300sqmm and above
(blank)
8272B - 1.8/3kV Cable
(blank)
(blank)
8272C - 3.6/6kV Cable
(blank)
(blank)
8272D - 6/10kV Cable
8272Da - 6/10kV Cable _ Below 70sqmm
8272Daa - 6/10kV Cable _ Below 70sqmm _ 3C
8272Dab - 6/10kV Cable _ Below 70sqmm _ 1C
8272Db - 6/10kV Cable _ 70sqmm to below 185sqmm
8272Dba - 6/10kV Cable _ 70sqmm to below 185sqmm _ 3C
8272Dbb - 6/10kV Cable _ 70sqmm to below 185sqmm _ 1C
8272Dc - 6/10kV Cable _ 185sqmm and above
8272Dca - 6/10kV Cable _ 185sqmm and above _ 3C
8272Dcb - 6/10kV Cable _ 185sqmm and above _ 1C
8272E - 19/33kV Cable
(blank)
(blank)
8272F - 45 KV to 72.5 KV Cable
(blank)
(blank)
8272G - 76/132kV Cable
8272Ga - 76/132kV _ Below 800sqmm
(blank)
8272Gb - 76/132kV _ 800sqmm and above
(blank)
8272H - Control
8272Ha - Control _ less than 8C
(blank)
8272Hb - Control _ 8C to less than 12C
(blank)
8272Hc - Control _ 12C to less than 20C
(blank)
8272Hd - Control _ 20C and more
(blank)
8272He - Control _ RTD Cable (5T)
(blank)
8272Hf - Control _ Fiber Optic Cable (2 to 6 Core)
(blank)
8272Hg - Control _ Fiber Optic Cable (7 to 12 Core)
(blank)
8272Hh - Control _ Fiber Optic Cable (24 Core)
(blank)
8272Hi - Control _ Fiber Optic Cable (36 Core)
(blank)
8272Hj - Control _ Fiber Optic Cable (48 Core)
(blank)
8272Hk - Control _ Fiber Optic Cable (60 Core)
(blank)
8272Hl - Control _ Fiber Optic Cable (72 Core)
(blank)
8273 - Splicing of cable
8273B - 1.8/3kV Cable
(blank)
(blank)
8273C - 3.6/6kV Cable
(blank)
(blank)
8273D - 6/10kV Cable
8273Da - 6/10kV Cable _ Below 70sqmm
8273Daa - 6/10kV Cable _ Below 70sqmm _ 3C
8273Dab - 6/10kV Cable _ Below 70sqmm _ 1C
8273Db - 6/10kV Cable _ 70sqmm to below 185sqmm
8273Dba - 6/10kV Cable _ 70sqmm to below 185sqmm _ 3C
8273Dbb - 6/10kV Cable _ 70sqmm to below 185sqmm _ 1C
8273Dc - 6/10kV Cable _ 185sqmm and above
8273Dca - 6/10kV Cable _ 185sqmm and above _ 3C
8273Dcb - 6/10kV Cable _ 185sqmm and above _ 1C
8273E - 19/33kV Cable
(blank)
(blank)
8273F - 45 KV to 72.5 KV Cable
(blank)
(blank)
8273G - 76/132kV Cable
8273Ga - 76/132kV _ Below 800sqmm
(blank)
8273Gb - 76/132kV _ 800sqmm and above
(blank)
8273H - Control
8273Hf - Control _ Fiber Optic Cable (2 to 6 Core)
(blank)
8273Hg - Control _ Fiber Optic Cable (7 to 12 Core)
(blank)
8273Hh - Control _ Fiber Optic Cable (24 Core)
(blank)
8273Hi - Control _ Fiber Optic Cable (36 Core)
(blank)
8273Hj - Control _ Fiber Optic Cable (48 Core)
(blank)
8273Hk - Control _ Fiber Optic Cable (60 Core)
(blank)
8273Hl - Control _ Fiber Optic Cable (72 Core)
(blank)
8290 - Other Work
8295 - Cable Trench
8295A - Excavation
8295Aa - Excavation of cable trench
(blank)
8000 - ELECTRICAL | 8100 - POWER GENERATOR & SUBSTATION | 8110 - Generator & Associated Equipment | 8112 - Emergency Generator (2214kW) | (blank) | (blank) | (blank) | 8295Ab - Manual Excavation of buried coiled cables
The LNG facilities includes provision of power generation, the facilities will operate in island mode. Power generation will be by gas turbines and steam turbines, CCPP, provided by other subcontractor. A diesel emergency generation provision is provided. Power from the CCPP is received at the main substation (L-300-SS-101 buildings and equipment provide by other subcontractors) at 132kV, this is then distributed to Site on pre-fabricated fully equipped LER at 33kV. Power is then distributed from these LERs to the users. The majority of the power users are located in the process plant which will be of a modular design to the greatest extent practical. Generally the LV power users, such as motors, lighting and small power, will be pre-cabled to interface junction boxes (by others) and Site run cables will be connected to the interface junction boxes at the edge of the module. For MV motors no interface junction boxes will be provided and the MV motors will be connected directly to the LERs. The majority of the process and utility equipment for the facilities will be delivered to Site in the form of modules. Modularisation also extends to providing the main substation and the local electrical rooms as modules. These modules will be electrically complete as far as possible at the fabrication yard prior to delivery to Site. All equipment supplied on modules will be installed and precommissioned by other subcontractors (FAB-1, FAB-2, FAB-3 and FAB-4) in accordance with all applicable Australian Standards. Subcontractor shall energise stick built and module electrical installations in accordance with the NT Electricity Reform Regulation and all applicable regulations and standards. Documentation for all tests completed at the module yards will be made available to Subcontractor on request and any tests completed at the module yard do not need to be repeated by Subcontractor as part of this scope of Works. For lighting small power, and other electrical systems (communication type equipment) the module fabricators scope of work includes the installation of both fittings and local cabling. Subcontractor shall connect these systems back to the power / control source from junction boxes mounted within the modules. The Works includes full inspection, testing and energisation of the items constructed or installed by Subcontractor and pre-energisation and commissioning tests for items constructed by others. The Works include: • Above ground cable way and cable installation; • Installation and testing of items related to power generation and substation such as Transformers, Bus Duct, Switchgear/MCC, Power Distribution System(PDCS) and UPS/Batteries; • Preservation and testing of equipment; • Installation and testing of lighting/socket, earthing, cathodic protection and electrical heating; and • Installation and testing of telecommunication and security systems. | This category covers installation work of equipment in relation to power generators and substations including assembling and alignment. The foundation works will be by installed by Contractor for reinforced foundations or covered under FWBS8297. Grouting is considered part of this work unit. External earth, power and control cable installation and terminations are excluded from this FWBS and covered under FWBS 8200 and FWBS 8400. Power generation from the CCPP is excluded from the FWBS scope. Typical installation details for substation work is shown in document L780-DE-DTL- 0001.001 referenced in Exhibit E. This scope of works and definition is composed of the following sub-categories as per types of materials: | [5 empty] | (blank)
8295Ac - Removal of Temporary Sand and Geofabric Material
(blank)
8295Ad - Excavation Under LER Buildings
(blank)
8295B - Sand Filling
8295Ba - Sand Filling-under Building
(blank)
8295Bb - Sand Filling-not under Building
(blank)
8295Bc - Fluidised Thermal Backfill – under building
(blank)
8295Bd - Fluidised Thermal Backfill – not under building
(blank)
8295C - Back Filling
(blank)
(blank)
8295D - Polymeric Cable Protection Cover (to AS 4702)
(blank)
(blank)
8295E - Cable Marker (to AS/NZS 2648.1)
(blank)
(blank)
8295F - Stub-up PVC conduit
8295Fa - 100 - 150mm dia 1500-2000mm radius bend
(blank)
8295Fb - 100 - 150mm dia 1000-1500mm radius bend
(blank)
8295Fc - 100 - 150mm dia 500-1000mm radius bend
(blank)
8295Fd - 100 - 150mm dia up to 500mm radius bend
(blank)
8295Fe - less than 100mm dia 500-1500mm radius bend
(blank)
8295Ff - less than 100mm dia up to 500mm radius bend
(blank)
8295Fg - 100-150mm dia straight stub up
(blank)
8295Fh - less than 100mm dia straight stub up
(blank)
8295G - Disposal
(blank)
(blank)
8296 - Cable Route Markers
(blank)
(blank)
(blank)
8297 - Minor Foundations
8297A - Minor Foundations less than 0.1M3
(blank)
(blank)
8297B - Minor Foundations 0.1 to 0.15M3
(blank)
(blank)
8298 - Fabrication of Supports For Cableway and Cable Supports
8298A - Weight: below 1kg
(blank)
(blank)
8298B - Weight: 1kg to below 5kg
(blank)
(blank)
8298C - Weight: 5kg to below 15kg
(blank)
(blank)
8298D - Weight: 15kg to below 25kg
(blank)
(blank)
8298E - Weight: 25kg to below 35kg
(blank)
(blank)
8298F - Weight: 35kg to below 45kg
(blank)
(blank)
8298G - Weight: 190kg to 210kg approximately 200kg
(blank)
(blank)
8298H - Weight: 290kg to 310kg approximately 300kg
(blank)
(blank)
8299 - Installation of Miscellaneous Supports
8299A - Weight: below 1kg
(blank)
(blank)
8299B - Weight: 1kg to below 5kg
(blank)
(blank)
8299C - Weight: 5kg to below 15kg
(blank)
(blank)
8299D - Weight: 15kg to below 25kg
(blank)
(blank)
8299E - Weight: 25kg to below 35kg
(blank)
(blank)
8299F - Weight: 35kg to below 45kg
(blank)
(blank)
8299G - Weight: 190kg to 210kg approximately 200kg
(blank)
(blank)
8299H - Weight: 290kg to 310kg approximately 300kg
(blank)
(blank)
8280 - Cable Way
8283 - Removal & Reinstallation of MF Installed Ladder Cover
8283A - Cable Ladder 300mm Width
(blank)
(blank)
8283B - Cable Ladder 600mm Width
(blank)
(blank)
8283C - Cable Ladder 900mm Width
(blank)
(blank)
8284 - Cable Transit
8284A - Cable Transit Frame
(blank)
(blank)
8284B - Cable Transit Block
(blank)
(blank)
8284C - Cable Transit Block at LIR
(blank)
(blank)
8284D - Cable Transit Block at LIR (Spare)
(blank)
(blank)
8285 - Grating Penetration (300mm X 300mm)
(blank)
(blank)
(blank)
8281 - Cable Ladder or Tray & Cover - Galvanised Steel
8281A - Perforated Cable Tray equal to or less than 200mm Width
(blank)
(blank)
8281B - Cable Ladder 300mm Width
(blank)
(blank)
8281C - Cable Ladder 600mm Width
(blank)
(blank)
8281D - Cable Ladder 900mm Width
(blank)
(blank)
8281E - Perforated Cable Tray Cover equal to or less than 200mm Width
(blank)
(blank)
8281F - Cable Ladder Cover 300mm Width
(blank)
(blank)
8281G - Cable Ladder Cover 600mm Width
(blank)
(blank)
8281H - Cable Ladder Cover 900mm Width
(blank)
(blank)
8282 - Cable Ladder or Tray & Cover - Stainless Steel
8282A - Perforated Cable Tray equal to or less than 200mm Width
(blank)
(blank)
8282B - Cable Ladder 300mm Width
(blank)
(blank)
8282C - Cable Ladder 600mm Width
(blank)
(blank)
8282D - Cable Ladder 900mm Width
(blank)
(blank)
8282E - Perforated Cable Tray Cover equal to or less than 200mm Width
(blank)
(blank)
8282F - Cable Ladder Cover 300mm Width
(blank)
(blank)
8282G - Cable Ladder Cover 600mm Width
(blank)
(blank)
8282H - Cable Ladder Cover 900mm Width
(blank)
(blank)
8300 - LIGHTING
8320 - Lighting in Plant
8321 - Lighting Pole
8321A - Up to 3M Height
(blank)
(blank)
8321B - Above 3M Height up to 8M Height
(blank)
(blank)
8321C - Above 8M Height up to 15M Height
(blank)
(blank)
8322 - Lighting Mast
8322A - Up to 30M Height
(blank)
(blank)
8322B - Above 30M Height
(blank)
(blank)
8323 - Lighting Fixture with Cabling Works
8323A - Fluorescent
(blank)
(blank)
8323B - Metal Halide
(blank)
(blank)
8323C - Flood Light
(blank)
(blank)
8324 - Single Phase Convenience Outlet with Cabling Works
(blank)
(blank)
(blank)
8330 - Street, Fence, Security
8332 - Lighting Mast
8332A - Up to 30M Height
(blank)
(blank)
8332B - Above 30M Height
(blank)
(blank)
8333 - Lighting Fixture
(blank)
(blank)
(blank)
8337 - Termination
(blank)
(blank)
(blank)
8338 - Cable Way
8338A - Conduit Piping
(blank)
(blank)
8338B - Perforated Cable Tray - Galvanised Steel
(blank)
(blank)
8338C - Perforated Cable Tray - Stainless Steel
(blank)
(blank)
8331 - Lighting Pole
8331B - Above 3M Height up to 8M Height
(blank)
(blank)
8331C - Above 8M Height up to 15M Height
(blank)
(blank)
8336 - Cabling - max 35mm2
(blank)
(blank)
(blank)
8340 - Aircraft Obstacle Light
8343 - Lighting Fixture
(blank)
(blank)
(blank)
8344 - Control Panel
(blank)
(blank)
(blank)
8346 - Cabling
(blank)
(blank)
(blank)
8347 - Termination
(blank)
(blank)
(blank)
8348 - Cable Way
8348A - Conduit Piping
(blank)
(blank)
8348B - Perforated Cable Tray - Galvanised Steel
(blank)
(blank)
8348C - Perforated Cable Tray - Stainless Steel
(blank)
(blank)
8350 - Navigation Light
8353 - Lighting Fixture
(blank)
(blank)
(blank)
8354 - Control Panel
(blank)
(blank)
(blank)
8356 - Cabling
(blank)
(blank)
(blank)
8357 - Termination
(blank)
(blank)
(blank)
8358 - Cable Way
8358A - Conduit Piping
(blank)
(blank)
8358B - Perforated Cable Tray - Galvanised Steel
(blank)
(blank)
8358C - Perforated Cable Tray - Stainless Steel
(blank)
(blank)
8390 - Other Work
8395 - Cable Trench
8395A - Excavation
8395Aa - Excavation of cable trench
(blank)
8395Ab - Manual Excavation of buried coiled cables
(blank)
8395B - Sand Filling
(blank)
(blank)
8395C - Back Filling
(blank)
(blank)
8395D - Polymeric Cable Protection CoverTile (to AS 4702)
(blank)
(blank)
8395E - Cable Warning Marker Sheet (to AS/NZS 2648.1)
(blank)
(blank)
8395F - Disposal
(blank)
(blank)
8396 - Cable Route Marker
(blank)
(blank)
(blank)
8400 - EARTHING
8410 - Wiring of Earthing
8410A - Wiring of Underground Earthing (25sqmm, bare copper)
(blank)
(blank)
(blank)
8410B - Wiring of Underground Earthing (70sqmm, bare copper)
(blank)
(blank)
(blank)
8410C - Wiring of Underground Earthing (120sqmm, bare copper)
(blank)
(blank)
(blank)
8410D - Underground Thermoweld Connection
(blank)
(blank)
(blank)
8410E - Stub-up PVC conduit
(blank)
(blank)
(blank)
8410F - Wiring of Earthing (35 sqmm and less, PVC Yellow / Green)
(blank)
(blank)
(blank)
8410G - Wiring of Earthing (70sqmm, PVC Yellow / Green)
(blank)
(blank)
(blank)
8410H - Wiring of Earthing (95sqmm and above, PVC Yellow / Green)
(blank)
(blank)
(blank)
8410I - Aboveground "C" type compression clamp
(blank)
(blank)
(blank)
8410J - Earthing Bar
(blank)
(blank)
(blank)
8410K - Earthing Boss
(blank)
(blank)
(blank)
8420 - Earthing Electrode
(blank)
(blank)
(blank)
(blank)
8430 - Connection to Equipment
(blank)
(blank)
(blank)
(blank)
8440 - Air Terminal
8441 - Downconductor
(blank)
(blank)
(blank)
8490 - Other Work
8493 - Inspection Pit
(blank)
(blank)
(blank)
8495 - Boring Depth
(blank)
(blank)
(blank)
8600 - COMMUNICATION SYSTEM
8610 - Wired System
8611 - Public Address and General Alarm System
8611A - Amplifier Cabinet
(blank)
(blank)
8611B - Intercom station
8611Ba - Intercom station (indoor unit)
(blank)
8611Bb - Intercom station (outdoor unit hazardous area)
(blank)
8611Bc - Intercom station (outdoor unit non hazardous area)
(blank)
8611C - Speaker
8611Ca - Speaker (Indoor)
(blank)
8611Cb - Speaker (Outdoor unit hazardous area)
(blank)
8611Cc - Speaker (Outdoor unit non hazardous area)
(blank)
8611Cd - Speaker Support
(blank)
8611E - Junction Box
8611Ea - Junction Box (Hazardous Area)
(blank)
8611Eb - Junction Box (Non Hazardous Area)
(blank)
8611F - Beacon
8611Fa - Beacon (Hazardous Area)
(blank)
8611Fb - Beacon (Non Hazardous Area)
(blank)
8611Fb - Beacon Support
(blank)
8612 - Telephone System
8612A - IP PABX
(blank)
(blank)
8612B - Attendant Console
(blank)
(blank)
8612C - Telephone Handset
8612Ca - IP Telephone handset
(blank)
8612Cb - Analogue Telephone Handset w/ acoustic hood (Hazardous Area)
(blank)
8612Cc - Analogue Telephone Handset (Hazardous Area)
(blank)
8612Cd - Telephone Support
(blank)
8612D - MDF/IDF
8612Da - MDF
(blank)
8612Db - IDF
(blank)
8612E - Cat 6 Patch Panel
(blank)
(blank)
8612F - Analog Terminal Adapter
(blank)
(blank)
8612G - UPS with Integral Battery
8612Ga - UPS with Integral Battery - 3KVA
(blank)
8612Gb - UPS with Integral Battery - 5KVA
(blank)
8612H - Single AC UPS
(blank)
(blank)
8612I - Battery Rack
(blank)
(blank)
8620 - Wireless System
8621 - Microwave System
8621A - Central Cabinet
(blank)
(blank)
8621B - Outdoor Equipment
8621Ba - 65m Structure
(blank)
8621Bb - 30m Structure
(blank)
8621Bc - 10m Structure
(blank)
8621C - Operation Console
(blank)
(blank)
8622 - UHF TETRA Radio
8622A - Central Cabinet
(blank)
(blank)
8622B - Outdoor Equipment
(blank)
(blank)
8622C - TETRA Radio Console, Network Management Terminal and Set-up PC
(blank)
(blank)
8622D - TETRA Desk Mounted Radio
(blank)
(blank)
8622E - UHF Active Repeater for Indoor Coverage
(blank)
(blank)
8622F - UHF Active Repeater for Outdoor Coverage
(blank)
(blank)
8622G - UHF Passive Repeater for Indoor Coverage
(blank)
(blank)
8623 - Satellite Phone System
(blank)
(blank)
(blank)
8624 - VHF and HF Radio
8624A - Central Cabinet
(blank)
(blank)
8624B - Antenna System
8624Ba - VHF Antenna
(blank)
8624Bb - HF Antenna
(blank)
8625 - Antenna Supprt Structure
8625A - Support Structure 65m
(blank)
(blank)
8625B - Support Structure 30m
(blank)
(blank)
8625C - Support Structure 10m
(blank)
(blank)
8630 - LAN/WAN & Data Communication System
8631 - LAN/WAN
8631A - Central Cabinet
(blank)
(blank)
8631B - Local Cabinet
(blank)
(blank)
8631C - Cat 6 Patch Panel
(blank)
(blank)
8631D - Central Console
(blank)
(blank)
8631E - Access Switch
(blank)
(blank)
8631F - FO Media Converter with chasssis
(blank)
(blank)
8632 - Mobile Data System
8632A - Central Cabinet
(blank)
(blank)
8632B - Local Cabinet
(blank)
(blank)
8632C - Central Console
(blank)
(blank)
8632D - Wi-Fi Access Point
8632Da - Wi-Fi Access Point (Indoor)
(blank)
8632Db - Wi-Fi Access Point Outdoor (Weatherproof)
(blank)
8632Dc - Wi-Fi Access Point Outdoor (Hazardous Area)
(blank)
8640 - Other Communication System
8641 - CCTV System
8641A - Central Cabinet
(blank)
(blank)
8641B - Local Cabinet
(blank)
(blank)
8641C - Desk Top Type Operation Console
(blank)
(blank)
8641D - Monitor
(blank)
(blank)
8641E - Camera
8641Ea - CCTV Indoor Dome type Camera
(blank)
8641Eb - CCTV Weatherproof Dome Type Camera
(blank)
8641Ec - CCTV Weatherproof Dual Head Camera
(blank)
8641Ed - CCTV Hazardous Area Camera - Pole Mounted
(blank)
8641Ee - CCTV Hazardous Area Camera - Platform (Stick Built)
(blank)
8641Ef - CCTV Hazardous Area Camera - Platform (MFY Installed)
(blank)
8641F - Video Encorder
(blank)
(blank)
8642 - Source Transfer Switch
8642A - Source Transfer Switch
(blank)
(blank)
8642B - Wiring for Source Transfer Switch
(blank)
(blank)
8649 - Hotline System
8649A - Central Cabinet
(blank)
(blank)
8649B - Fibre Optic Patch Panel
(blank)
(blank)
8649C - Media Converter
(blank)
(blank)
8649D - Master Station
(blank)
(blank)
8649E - Hotline Terminal
(blank)
(blank)
8643 - Security System - RADAR
8643A - Central Cabinet
(blank)
(blank)
8643C - Monitor/Display/Control Unit
(blank)
(blank)
8643D - RADAR Antenna and Rotating Equipment
(blank)
(blank)
8643F - Long Range CCTV Camera
(blank)
(blank)
8644 - Security System - Long Range Acoustic Device (LRAD)
8644A - Central Cabinet
(blank)
(blank)
8644B - LRAD Device
(blank)
(blank)
8644C - LRAD Control Console
(blank)
(blank)
8645 - Security System - Fence Intrusion Detection System (FIDS)
8645A - Central Cabinet
(blank)
(blank)
8645B - Local Cabinet
(blank)
(blank)
8645C - Fibre Optic Sensor Cable
(blank)
(blank)
8645D - Gate Isolation Unit
(blank)
(blank)
8645E - Operator Console
(blank)
(blank)
8646 - Security System - Access Control System
8646A - Central Cabinet
(blank)
(blank)
8646B - Local Cabinet
(blank)
(blank)
8646C - Badge Production PC with Camera
(blank)
(blank)
8646D - Monitoring PC
(blank)
(blank)
8646E - Manual Controller Remote Control Push Button
(blank)
(blank)
8646F - Biometric Reader Indoor Non-Hazardous Area
(blank)
(blank)
8646G - Security Gate
8646Ga - Double Sliding Gate (6 m opening)
(blank)
8646Gb - Double Sliding Gate (9 m opening)
(blank)
8646Gc - Outdoor Turnstile Gate
(blank)
8646Gd - Rising Arm Gate
(blank)
8646Ge - Fence Gate Access Control Equipment
(blank)
8646Gf - Crash Barrier (Main Gate)
(blank)
8646Gg - Swing Gate
(blank)
8647 - Security System - Intercom System
8647A - Central Cabinet
(blank)
(blank)
8647B - Intercom Station
(blank)
(blank)
8647C - Outdoor Intercom Station
(blank)
(blank)
8648 - Personnel Locator System (PLS) and E-Mustering System
8648A - Central Cabinet
(blank)
(blank)
8648B - PLS Wi-Fi Access Point
8648Ba - PLS Wi-Fi Access Point (Hazardous Area)
(blank)
8648Bb - PLS Wi-Fi Access Point (Non Hazardous Area)
(blank)
8648C - Exciter and Location Receiver
(blank)
(blank)
8648D - Muster Point Equipment
(blank)
(blank)
8650 - Nurse Call /Distress System
8651 - Ship to Shore Link (SSL)
8651A - Central Cabinet
(blank)
(blank)
8651B - Fibre Optic Cable Reel
(blank)
(blank)
8651C - Electrical Cable Reel
(blank)
(blank)
8651D - Hotline Terminal
(blank)
(blank)
8652 - Radio Emergency Shut Down (ESD) System
8652A - Radio SSL Fixed Station
(blank)
(blank)
8652B - Radio SSL Antenna
(blank)
(blank)
8652C - Radio SSL Remote Station
(blank)
(blank)
8653 - Video conferencing System
8653A - Large Terminal
(blank)
(blank)
8653B - Medium Terminal
(blank)
(blank)
8653C - Small Terminal
(blank)
(blank)
8653D - Personal System
(blank)
(blank)
8654 - Telecoms Network Management System
8654A - Central Cabinet
(blank)
(blank)
8654B - Network Time Server
(blank)
(blank)
8654C - PC with Alarm Monitoring
(blank)
(blank)
8654D - RTU
(blank)
(blank)
No Code
8650A - Central Cabinet
(blank)
(blank)
8650B - PC with Management and Call Logger
(blank)
(blank)
8650C - Address Console
(blank)
(blank)
8650D - Corridor Distress Light
(blank)
(blank)
8650E - Call Unit
(blank)
(blank)
8660 - Cabling
8661 - Cable
8661A - Power Cable
8661Aa - 0.6/1kV _ Below 10sqmm
(blank)
8661Ab - 0.6/1kV _ 10sqmm to below 50sqmm
(blank)
8661B - Control Cable
8661Ba - Control _ less than 8C
(blank)
8661Bb - Control _ 8C to less than 12C
(blank)
8661Bc - Control _ 12C and more
(blank)
8661C - Fiber Optic Cable
8661Ca - 12 Fibre Cable
(blank)
8661Cb - 24 Fibre Cable
(blank)
8661Cc - 48 Fibre Cable
(blank)
8661Cd - 6 Fibre Cable
(blank)
8661D - Copper Twisted Pair Cable
8661Da - CAT 3 Indoor
(blank)
8661Db - CAT 6A indoor
(blank)
8661Dc - CAT 3 Outdoor
(blank)
8661E - Coaxial Cable
8661Ea - Low Density Foam Corrugated Copper with OD < or = 13 mm
(blank)
8661Eb - Low Density Foam Corrugated Copper with OD > 13 mm
(blank)
8661Ec - Shielded Cable with a OD < or = 10.5 mm
(blank)
8661Ed - Shielded Cable with a OD > 10.5 mm
(blank)
8661F - Fibre Optic Patch Cord
8661Fa - Fibre Optic Patch Cord - within single cabinet
(blank)
8661Fb - Fibre Optic Patch Cord - between adjacent cabinets
(blank)
8661G - CAT 6A Patch Cabling
8661Ga - CAT 6A Patch Cabling - within single cabinet
(blank)
8661Gb - CAT 6A Cabling - between adjacent cabinets
(blank)
8670 - Termination/Splicing of Cable
8672 - Termination _ including Non Compound Filled Gland
8672A - Power Cable
8672Aa - 0.6/1kV _ Below 10sqmm
(blank)
8672Ab - 0.6/1kV _ 10sqmm to below 50sqmm
(blank)
8672B - Control Cable
8672Ba - Control _ less than 8C
(blank)
8672Bb - Control _ 8C to less than 12C
(blank)
8672Bc - Control _ 12C and more
(blank)
8672C - Fiber Optic Cable
8672Ca - 12 Fibre Cable
(blank)
8672Cb - 24 Fibre Cable
(blank)
8672Cc - 48 Fibre Cable
(blank)
8672Cd - 6 Fibre Cable
(blank)
8672D - Copper Twisted Pair Cable
8672Da - CAT 3 Indoor
(blank)
8672Db - CAT 6A indoor
(blank)
8672Dc - CAT 3 Outdoor
(blank)
8672E - Coaxial Cable
8672Ea - Low Density Foam Corrugated Copper with OD < or = 13 mm
(blank)
8672Eb - Low Density Foam Corrugated Copper with OD > 13 mm
(blank)
8672Ec - Shielded Cable with a OD < or = 10.5 mm
(blank)
8672Ed - Shielded Cable with a OD > 10.5 mm
(blank)
8673 - Splicing of Fibre Optic Cable
8673A - Fiber Optic Cable
8673Aa - 12 Fibre Cable
(blank)
8673Ab - 24 Fibre Cable
(blank)
8673Ac - 48 Fibre Cable
(blank)
8673Ad - 6 Fibre Cable
(blank)
8674 - FO Cabinet With Distribution Trays
(blank)
(blank)
(blank)
8671 - Termination - including Compound Filled Gland
8671A - Power Cable
8671Aa - 0.6/1kV - Below 10sqmm
(blank)
8671Ab - 0.6/1kV - 10sqmm to below 50sqmm
(blank)
8671B - Control Cable
8671Ba - Control - less than 8C
(blank)
8671Bb - Control - 8C to less than 12C
(blank)
8671Bc - Control - 12C and more
(blank)
8671C - Fiber Optic Cable
8671Ca - 12 Fibre Cable
(blank)
8671Cb - 24 Fibre Cable
(blank)
8671Cc - 48 Fibre Cable
(blank)
8671Cd - 6 Fibre Cable
(blank)
8671D - Copper Twisted Pair Cable
8671Da - CAT 3 Indoor
(blank)
8671Db - CAT 6A indoor
(blank)
8671Dc - CAT 3 Outdoor
(blank)
8671E - Coaxial Cable
8671Ea - Low Density Foam Corrugated Copper with OD < or = 13 mm
(blank)
8671Eb - Low Density Foam Corrugated Copper with OD > 13 mm
(blank)
8671Ec - Shielded Cable with a OD < or = 10.5 mm
(blank)
8671Ed - Shielded Cable with a OD > 10.5 mm
(blank)
8675 - Yellow Cable Duct for FO Cabling
(blank)
(blank)
(blank)
8680 - Cable Way
8681 - Cable Ladder or Tray & Cover
8681A - Perforated Cable Tray 150mm Width
(blank)
(blank)
8681B - Cable Ladder 300mm Width
(blank)
(blank)
8681C - Cable Ladder 600mm Width
(blank)
(blank)
8681D - Cable Ladder 900mm Width
(blank)
(blank)
8681E - Perforated Cable Tray Cover 150mm Width
(blank)
(blank)
8681F - Cable Ladder Cover 300mm Width
(blank)
(blank)
8681G - Cable Ladder Cover 600mm Width
(blank)
(blank)
8681H - Cable Ladder Cover 900mm Width
(blank)
(blank)
8682 - Conduit Piping for Conduit Wiring System
8682A - Rigid Metal Conduit
(blank)
(blank)
8682B - Rigid PVC Conduit
(blank)
(blank)
8684 - Removal & Reinstallation of MF Installed Ladder Cover
8684A - Cable Ladder Cover 300mm Width
(blank)
(blank)
8684B - Cable Ladder Cover 600mm Width
(blank)
(blank)
8684C - Cable Ladder Cover 900mm Width
(blank)
(blank)
8683 - Stub-up PVC conduit
8683A - 100 - 150mm dia 1500-2000mm radius bend
(blank)
(blank)
8683B - 100 - 150mm dia 1000-1500mm radius bend
(blank)
(blank)
8683C - 100 - 150mm dia 500-1000mm radius bend
(blank)
(blank)
8683D - 100 - 150mm dia up to 500mm radius bend
(blank)
(blank)
8683E - less than 100mm dia 500-1500mm radius bend
(blank)
(blank)
8683F - less than 100mm dia up to 500mm radius bend
(blank)
(blank)
8683G - 100-150mm dia straight stub up
(blank)
(blank)
8683H - less than 100mm dia straight stub up
(blank)
(blank)
8690 - Other Work
8695 - Cable Trench
8695A - Excavation of Cable Trench
(blank)
(blank)
8695B - Manual Excavation of buried coiled cables
(blank)
(blank)
8695C - Sand Filling
(blank)
(blank)
8695D - FTB (instead of sand filling)
(blank)
(blank)
8695E - Back Filling
(blank)
(blank)
8695F - Polymeric Cable Protection CoverTile (to AS 4702)
(blank)
(blank)
8695G - Cable Warning Marker Sheet (to AS/NZS 2648.1)
(blank)
(blank)
8695H - Disposal
(blank)
(blank)
8696 - Cable Route Marker
(blank)
(blank)
(blank)
8697 - Pole and Mast
8697A - Pole (up to 5M)
(blank)
(blank)
8697B - Pole (up to 8M)
(blank)
(blank)
8697C - Pole (up to 15M)
(blank)
(blank)
8697D - Mast (above 15M)
(blank)
(blank)
8700 - CATHODIC PROTECTION
8710 - Impressed current cathodic protection
8712 - Test Box and Bond Box
(blank)
(blank)
(blank)
8713 - Anode
8713A - Rod Type
(blank)
(blank)
8713B - Ribbon/Line Type
(blank)
(blank)
8714 - Reference Electrode
(blank)
(blank)
(blank)
8717 - Splicing and Connection
8717A - U/G Splicing
(blank)
(blank)
8717B - Connection to Piping/Equipment
(blank)
(blank)
8719 - Boring
(blank)
(blank)
(blank)
8711 - Transformer-Rectifier
(blank)
(blank)
(blank)
8716 - Cabling - Low Voltage
(blank)
(blank)
(blank)
8720 - Sacrificial Anode System
8722 - Test Box and Bond Box
(blank)
(blank)
(blank)
8723 - Anode
(blank)
(blank)
(blank)
8724 - Reference Electrode
(blank)
(blank)
(blank)
8727 - Splicing and Connection
8727A - U/G Splicing
(blank)
(blank)
8727B - Connection to Piping/Equipment
(blank)
(blank)
8726 - Cabling - Low Voltage
(blank)
(blank)
(blank)
8790 - Other Works
8793 - Soil Access Box
(blank)
(blank)
(blank)
8795 - Cable Trench
No Code
8795Aa - Excavatiom
(blank)
8795Ab - Manual Excavation of buried coiled cables
(blank)
8795B - Sand Filling
(blank)
(blank)
8795C - Back Filling
(blank)
(blank)
8795D - Cable Protection Tile
(blank)
(blank)
8795E - Cable Warning Sheet (Polymeric cable tile)
(blank)
(blank)
8796 - Cable Route Marker
(blank)
(blank)
(blank)
8800 - ELECTRICAL HEAT TRACING
8810 - Heater Panel
(blank)
(blank)
(blank)
(blank)
8820 - Heating Element
8821 - Self Regulating Type
(blank)
(blank)
(blank)
8870 - Termination
(blank)
(blank)
(blank)
(blank)
8860 - Cabling - Low Voltage
(blank)
(blank)
(blank)
(blank)
8900 - PRECOMMISSIONING CHECKS AND FUNCTION TESTING
8910 - Precommissioning Checks
No Code
No Code
8910AG - EP06 SOCKET OUTLET
(blank)
8910AH - EP07 JUNCTION BOX
(blank)
8910AJ - EP09 CONTROL STATION
(blank)
8910AK - EP10 CABLE TRAY AND LADDER
(blank)
8910AQ - EP16 EARTH BOSS ON SKID / MODULE
(blank)
8910AS - EP18 GENERATOR
(blank)
8910AT - EP19 POWER TRANSFORMER
(blank)
8910AW - EP22 HV (OPERATIONAL VOLTAGE ≥1.0 KV) BUS DUCT
(blank)
8910AZ - EP25 HV (OPERATIONAL VOLTAGE ≥1.0 KV) MOTOR
(blank)
8910BA - EP26 BATTERY
(blank)
8910BB - EP27 ELECTRIC HEATER
(blank)
8910BD - EP29 EARTH BAR
(blank)
8910BE - EP30 EARTH ROD
(blank)
8910BF - EP31 METERING TRANSFORMER
(blank)
8910BI - TP01 TELECOMMUNICATIONS PA/GA LOUDSPEAKER
(blank)
8910BJ - TP02 TELECOMMUNICATIONS BEACON
(blank)
8910BK - TP03 TELECOMMUNICATIONS ACCESS CONTROL EQUIPMENT
(blank)
8910BL - TP04 TELECOMMUNICATIONS NETWORK EQUIPMENT
(blank)
8910BN - TP06 TELECOMMUNICATIONS TELECOMS CABINET
(blank)
8910BO - TP07 TELECOMMUNICATIONS RADIO EQUIPMENT
(blank)
8910BP - TP08 TELECOMMUNICATIONS METEOROLOGICAL SENSOR
(blank)
8910BR - TP10 TELECOMMUNICATIONS WORKSTATION / CONSOLES
(blank)
8910BS - TP11 TELECOMMUNICATIONS MISCELLANEOUS EQUIPMENT
(blank)
8910BT - TP12 TELECOMMUNICATIONS FOBOT / PATCH PANEL
(blank)
8910BU - TP13 TELECOMMUNICATIONS CCTV CAMERA
(blank)
8910BY - TP17 TELECOMMUNICATIONS FIBRE OPTIC CABLE
(blank)
8910CC - EP35 Cathodic Protection
(blank)
8910CD - EP36 Lightning Protection
(blank)
No Code
8910AAa - XP01 Hazardous Area
8910AAb - XP03 Hazardous Area
8910ADm - EP03 CONTROL PANEL / CONSOLE
8910ADs - EP03 CONTROL PANEL / CONSOLE
8910AEm - EP04 CHARGER / INVERTER
8910AEs - EP04 CHARGER / INVERTER
8910ALm - EP11 DISTRIBUTION BOARD
8910ALs - EP11 DISTRIBUTION BOARD
8910AMm - EP12 LV (OPERATIONAL VOLTAGE <1.0 KV) SWITCHGEAR
8910AMs - EP12 LV (OPERATIONAL VOLTAGE <1.0 KV) SWITCHGEAR
8910ANm - EP13 HV (OPERATIONAL VOLTAGE ≥1.0 KV) SWITCHGEAR
8910ANs - EP13 HV (OPERATIONAL VOLTAGE ≥1.0 KV) SWITCHGEAR
8910AVm - EP21 LV (OPERATIONAL VOLTAGE <1.0 KV) SWITCHBOARD
8910AVs - EP21 LV (OPERATIONAL VOLTAGE <1.0 KV) SWITCHBOARD
8910AUm - EP20 HV (OPERATIONAL VOLTAGE ≥1.0 KV) SWITCHBOARD
8910AUs - EP20 HV (OPERATIONAL VOLTAGE ≥1.0 KV) SWITCHBOARD
8910AB - EP01 LV (OPERATIONAL VOLTAGE <1.0 KV) CABLE
(blank)
8910AC - EP02 LV (OPERATIONAL VOLTAGE <1.0 KV) MOTOR
(blank)
8910AF - EP05 LIGHT FITTING
(blank)
8910AI - EP08 EARTHING SYSTEMS
(blank)
8910AO - EP14 MISCELLANEOUS EQUIPMENT
(blank)
8910AP - EP15 INSTALLATION ON SKID
(blank)
8910AR - EP17 COILED CABLE
(blank)
8910AX - EP23 LV (OPERATIONAL VOLTAGE <1.0 KV) BUS DUCT
(blank)
8910AY - EP24 HV (OPERATIONAL VOLTAGE ≥1.0 KV) CABLE
(blank)
8910BC - EP28 NEUTRAL EARTHING RESISTOR
(blank)
8910BG - EP32 AUXILIARY TRANSFORMER
(blank)
8910BH - EP33 Heat Tracing (Pre-insulation)
(blank)
8910CB - EP34 Heat Tracing (Post-insulation)
(blank)
8910BM - TP05 TELECOMMUNICATIONS TELEPHONE UNIT
(blank)
8910BQ - TP09 TELECOMMUNICATIONS CONTROLLER UNITS
(blank)
8910BV - TP14 TELECOMMUNICATIONS JUNCTION BOX
(blank)
8910BW - TP15 TELECOMMUNICATIONS TELECOMS CABLE
(blank)
8910BX - TP16 TELECOMMUNICATIONS CAT 6A CABLE
(blank)
8910BZ - TP18 TELECOMMUNICATIONS ANTENNA / DISH
(blank)
8910CA - TP19 TELECOMMUNICATIONS COAXIAL CABLE
(blank)
8920 - Function Testing
No Code
No Code
No Code
8920ATa - EC20 PROTECTION RELAY
8920ATb - EC41 PROTECTION RELAY（REF630)
8920ATc - EC42 PROTECTION RELAY（UNDERVOLTAGE） (not used)
8920ATd - EC43 PROTECTION RELAY（PR122）
8920ATe - EC44 PROTECTION RELAY（REF610）
8920ATf - EC45 PROTECTION RELAY（REF615）
8920ATg - EC46 PROTECTION RELAY（REM615）
8920ATh - EC47 PROTECTION RELAY（REM630）
8920ATi - EC48 PROTECTION RELAY（SIPROTEC 7SD6101）
8920ATj - EC49 PROTECTION RELAY（RIO600）
8920ATk - EC50 PROTECTION RELAY（SIPROTEC 7SJ63）
8920ATl - EC51 PROTECTION RELAY（SIPROTEC 7SJ64）
8920ATm - EC52 PROTECTION RELAY（SIPROTEC 7UT61）
8920ATn - EC53 PROTECTION RELAY（SIPROTEC 7SS5251）
8920ATo - EC54 PROTECTION RELAY（SIPROTEC 7SS5220）
8920AU - EC21 UNINTERRUPTIBLE POWER SUPPLY (UPS) SYSTEM
8920AV - EC22 INSTALLATION ON SKID
8920AW - EC23 SOCKET OUTLET CIRCUIT
8920AX - EC24 PANEL INSTRUMENT
8920AY - EC25 HEAT TRACING CIRCUIT
No Code
8920BA - ETXX Earth Loop Impedance Test
8920BC - EC27 HEATER CONTROL PANEL
8920BD - EC29 POWER TRANSFORMER DIFFERENTIAL PROTECTION
8920BE - EC31 LINE DIFFERENTIAL PROTECTION TEST
8920BF - EC32 INTERFACE TEST BETWEEN SWITCHGEAR
8920BG - EC37 CATHODIC PROTECTION
8920AA - EC01 LIGHTING CIRCUIT
(blank)
8920AB - EC02 SWITCHGEAR AND CUBICLE
(blank)
8920AC - EC03 HEATER
(blank)
8920AD - EC04 MOTOR CONTROL CENTER (MCC) / STARTER
(blank)
8920AE - EC05 CONTROL PANEL
(blank)
8920AF - EC06 BATTERY CHARGER
(blank)
8920AG - EC07 BATTERY
(blank)
8920AH - EC09 GENERATOR, LOW VOLTAGE (LV) (not used)
(blank)
8920AI - EC08 GENERATOR, HIGH VOLTAGE (HV)
(blank)
8920AJ - EC10 POWER TRANSFORMER
(blank)
8920AK - EC11 MOTOR
(blank)
8920AL - EC12 MOTOR RUN TEST, NO LOAD
(blank)
8920AM - EC13 MOTOR LOAD RUN TEST, ONE (1) HOUR (not used)
(blank)
8920AN - EC14 MOTOR LOAD RUN TEST, FOUR (4) HOUR (not used)
(blank)
8920AO - EC15 SWITCHBOARD
(blank)
8920AP - EC16 DISTRIBUTION BOARD
(blank)
8920AQ - EC17 CURRENT TRANSFORMER (CT)
(blank)
8920AR - EC18 METERING TRANSFORMER, HIGH VOLTAGE (HV)
(blank)
8920AS - EC19 METERING TRANSFORMER, LOW VOLTAGE (LV)
(blank)
7000 - INSTRUMENTATION
7100 - Control System Installation (Indoor)
7110 - Panel, Rack and Cabinet
7111 - Floor Mount Type Panels, Rack and Cabinet including
7111A - 2.0m W x 1.0m D x 2.1m H (approx)
(blank)
(blank)
7111B - 1.0m W x 0.8m D x 2.1m H (approx)
(blank)
(blank)
7111C - 0.8m W x 0.8m D x 2.1m H (approx)
(blank)
(blank)
7111D - 0.8m W x 0.5m D x 2.1m H (approx) ( PDP )
(blank)
(blank)
7112 - Wall Mount Type
7112A - 1.0m W x 0.4m D x 1.0m H (approx)
(blank)
(blank)
7112B - 0.6m W x 0.4m D x 0.8m H (approx) (FAP, HSSD)
(blank)
(blank)
7112C - 0.6m W x 0.4m D x 1.8m H (approx)
(blank)
(blank)
7120 - Control Systems / Computer System
7121 - Operator Station
7121A - Console Type ( Typ. 1,65m W x 1.4m D x 0.75m H ) (OPC)
(blank)
(blank)
7121B - Desk mount type
(blank)
(blank)
7121C - Cabinet Type ( 0.8m W x 0.8m D x 2.1m H ) (OPC)
(blank)
(blank)
7121D - Console Type ( Typ. 0.55m W x 1.15m D x 1.45m H ) (OPC)
(blank)
(blank)
7122 - Printers and peripherals
7122A - Printer, Fax, Scanner
(blank)
(blank)
7122B - Network Switch / Router/ Converters
(blank)
(blank)
7123 - ICSS Large Display
7123A - ICSS LARGE DISPLAY (Screen & Projector)
(blank)
(blank)
7123B - ICSS LARGE DISPLAY (Approx 60" Display)
(blank)
(blank)
7150 - Cable Way
7151 - Cable Ladder Galvanised Steel
7151A - 150mm Cable Ladder
(blank)
(blank)
7151B - 300mm Cable Ladder
(blank)
(blank)
7151C - 450mm Cable Ladder
(blank)
(blank)
7151D - 900mm Cable Ladder
(blank)
(blank)
7152 - Perforated Tray Galvanised Steel
7152A - 100mm Perforated Tray
(blank)
(blank)
7152B - 150mm Perforated Tray
(blank)
(blank)
7152C - 300mm Perforated Tray
(blank)
(blank)
7160 - Cable
7161 - Plugin Type PreFabricated System Cable
7161A - 10Pr or 20c and below
(blank)
(blank)
7161B - 20Pr or 40c
(blank)
(blank)
7162 - Hard wired Cable
7162A - 29 Cores
(blank)
(blank)
7162B - 1020 Cores
(blank)
(blank)
7162C - 2140 Cores
(blank)
(blank)
7162D - 41 Cores
(blank)
(blank)
7163 - FO Patch cord with connectors
(blank)
(blank)
(blank)
7164 - Coaxial Cable
(blank)
(blank)
(blank)
7165 - Network (LAN) Cables
(blank)
(blank)
(blank)
7170 - Cable Entry Sealing
7171 - Cable Transit
No Code
7171Ba - Transit Block with Cable
(blank)
7171Bb - Transit Block Spare
(blank)
7171A - Cable Transit Frame
(blank)
(blank)
7171C - Cable Gland
(blank)
(blank)
7300 - Local Instrument and/or Panel Installation
7310 - Local Instrument
7311 - Pipe Stanchion Mount Type Instrument
7311F - Flow Instruments
7311Fa - Instrument without Capillary Tube
(blank)
7311Fb - Instrument with Capillary Tube
(blank)
7311Fc - Flow Transmitter; Vortex (Remote)
(blank)
7311Fd - Flow Transmitter; Ultrasonic (Remote)
(blank)
7311L - Level Instruments
7311La - Instrument without Capillary Tube
(blank)
7311Lb - Instrument with Capillary Tube
(blank)
7311P - Pressure Instruments
7311Pa - Instrument without Capillary Tube
(blank)
7311Pb - Instrument with Capillary Tube
(blank)
7311Pc - Differential Pressure Transmitter / Indicator
(blank)
7311T - Temperature Instruments
7311Ta - Instrument without Capillary Tube
(blank)
7311Tb - Instrument with Capillary Tube
(blank)
7311Tc - Temperature Transmitter / Indicator (Remote)
(blank)
7311Td - Skinmount Temperature Element
(blank)
7311X - Other Instrument / Device
7311Xa - AFC Vibration SW
(blank)
7311Xb - AFC CPMS (TIM) Acceler Meter w/Cable
(blank)
7311Xc - AFC CPMS (TIM) TIM Housing
(blank)
7311Xd - AFC CPMS (TIM) ProTIMR
(blank)
7311Xe - Hand Switch
(blank)
7312 - Direct Mount Type Instrument
(blank)
(blank)
(blank)
7313 - Bracket or Wall Mount Type Instrument
(blank)
(blank)
(blank)
7315 - Fire and Gas Field Devices
No Code
7315FD - IR Flame Detector
(blank)
7315HD - Heat Detector
(blank)
7315SD - Smoke Detector
(blank)
7315MC - Manual Alarm Call Point (MAC)
(blank)
7315TD - Low Temperature Spill Detector
(blank)
7315GD - Flammable Gas Detector
(blank)
7315GL - Open Path type Flammable Gas Detector
(blank)
7315GT - Toxic Gas Detector
(blank)
7315GC - CO2 Gas Detector
(blank)
7315FA - Fire Audible Alarm (Horn)
(blank)
7315FB - Fire Alarm beacon
(blank)
7315GA - Gas Audible Alarm (Horn)
(blank)
7315GB - Gas Alarm Beacon
(blank)
7319 - Other Mount type Instrument
(blank)
(blank)
(blank)
7320 - Local Panel and Enclosure
(blank)
(blank)
(blank)
(blank)
7500 - Analyser Installation
7510 - Pipe Mount Type
(blank)
(blank)
(blank)
(blank)
7520 - SelfStanding Type
7521 - Loose Shipment Item assembly of SelfStanding Analyser
(blank)
(blank)
(blank)
7522 - Self standing type – nonmodule
(blank)
(blank)
(blank)
7530 - Analyser 3Side Shelter
(blank)
(blank)
(blank)
(blank)
7540 - Analyser House
(blank)
(blank)
(blank)
(blank)
7550 - Sample Conditioning Rack
(blank)
(blank)
(blank)
(blank)
7800 - Cabling and Piping
7810 - Main Cable
7811 - Cable Way
7811A - Cable Ladder Galvanised Steel
7811Aa - 150mm Cable Ladder
(blank)
7811Ab - 300mm Cable Ladder
(blank)
7811Ac - 450mm Cable Ladder
(blank)
7811Ad - 600mm Cable Ladder
(blank)
7811Ae - 900mm Cable Ladder
(blank)
7811Af - 150mm Cable Ladder Stainless Steel
(blank)
7811Ag - 300mm Cable Ladder Stainless Steel
(blank)
7811Ah - 450mm Cable Ladder Stainless Steel
(blank)
7811Ai - 600mm Cable Ladder Stainless Steel
(blank)
7811Aj - 900mm Cable Ladder Stainless Steel
(blank)
7811B - Conduit Stub Up
7811Ba - Less than 100mm Diameter, 600 mm radius bend
(blank)
7811Bb - 100150mm Diameter, 600 mm radius bend
(blank)
7811C - Cable Ladder Cover
7811Ca - 150mm Cable Ladder
(blank)
7811Cb - 300mm Cable Ladder
(blank)
7811Cc - 450mm Cable Ladder
(blank)
7811Cd - 600mm Cable Ladder
(blank)
7811Ce - 900mm Cable Ladder
(blank)
7811D - Removal & Reinstallation of MF Installed Ladder Cover
7811Da - 150mm Cable Ladder
(blank)
7811Db - 300mm Cable Ladder
(blank)
7811Dc - 450mm Cable Ladder
(blank)
7811Dd - 600mm Cable Ladder
(blank)
7811De - 900mm Cable Ladder
(blank)
7812 - Cable Laying
7812A - Armoured Metal Cable
7812Aa - Cable
7812Aaa - 210 cores
7812Aab - 1120 cores
7812Aac - 2140 cores
7812Aad - 41 cores over
7812Ab - Cable(for when cable is installed and left coiled by other subcontractors)
7812Aba - 210 cores
7812Abb - 1120 cores
7812Abc - 2140 cores
7812Abd - 41 cores over
7812B - Nonarmored Metal cable(not for when cable is installed and left coiled by other subcontractors)
7812Ba - 210 cores
(blank)
7812Bb - 1120 cores
(blank)
7812Bc - 2140 cores
(blank)
7812Bd - 41 cores over
(blank)
7812C - Armored Fibre Optic Cable
7812Ca - Cable
7812Caa - 26 Cores
7812Cab - 7 Cores and over
7812Cac - 24 Cores and over
7812Cad - 48 Cores and over
7812Cb - Cable(for when cable is installed and left coiled by other subcontractors)
7812Cba - 26 Cores
7812Cbb - 723 Cores
7812Cbc - 24 Cores
7812Cbd - 48 Cores
7812D - Nonarmored Metal cable(not for when cable is installed and left coiled by other subcontractors)
7812Da - 26 Cores
(blank)
7812Db - 7 Cores and over
(blank)
7812Dc - 24 Cores and over
(blank)
7812Dd - 48 Cores and over
(blank)
7813 - Termination and Cable Gland Installation for Main Cable
7813A - Metal cable
(blank)
(blank)
7813B - Fibre Optic Cable
(blank)
(blank)
7813C - Cable gland installation
7813Ca - Compound Type Cable Gland
(blank)
7813Cb - NonCompound Type Cable Gland
(blank)
7815 - Junction Box
7815A - 40 Terminals or less
7821Aa - 100mm CableTray
(blank)
7821Ab - 150mm Cable Tray
(blank)
7821Ac - 300mm Cable Tray
(blank)
7821Ad - 200mm Cable Tray
(blank)
7815B - 41 to 80 Terminals
(blank)
(blank)
7815C - 81 Terminals and over
(blank)
(blank)
7820 - Branch Cable
7821 - Cable Way
7821A - Perforated Tray Galvanised Steel / SS for D000
(blank)
(blank)
7821C - Perforated Angle Galvanised Steel / SS for D000 (max. 50 x 50mm)
(blank)
(blank)
7822 - Branch Cabling and Cable Gland Installation
7822A - Armoured Metel Cable (approx. 40m in length)
(blank)
(blank)
7822B - Nonarmored Metal cable (approx. 40m in length)
(blank)
(blank)
7822C - Armored Fiber Optic Cable (approx. 40m in length)
(blank)
(blank)
7822D - Nonarmored Fiber Optic Cable (approx. 40m in length)
(blank)
(blank)
7822E - Cable gland installation
7822Ea - Compound Type Cable Gland
(blank)
7822Eb - NonCompound Type Cable Gland
(blank)
7830 - Impulse Tubing and Tracing
7832 - Tubing
7832A - For Differential Pressure Instrument
7832Aa - Pedestal Mount Type (15m tubing)
(blank)
7832Ab - Line Mount Type (2m tubing)
(blank)
7832B - Pressure Instrument (6m tubing)
(blank)
(blank)
7832C - Analyser Sample Lines (60m tubing)
(blank)
(blank)
7832D - Other Sensing Line (6m tubing)
(blank)
(blank)
7833 - Pretraced Bundle Tube
7833A - For Differential Pressure Instrument
7833Aa - Pedestal Mount Type (15m tubing)
(blank)
7833Ab - Line Mount Type (2m tubing)
(blank)
7833B - Pressure Instrument (6m tubing)
(blank)
(blank)
7833C - Analyser Sample Lines (60m tubing)
(blank)
(blank)
7833D - Other Sensing Line (6m tubing)
(blank)
(blank)
7834 - Heat Tracing
7834B - Electrical heat Tracing
7834Ba - For Differential Pressure Instrument (for 15m tubing)
(blank)
7834Bb - Pressure Instrument (for 6m tubing)
(blank)
7834Bc - Analyser Sample Lines (for 60m tubing)
(blank)
7834Bd - Other Sensing Line (for 6m tubing)
(blank)
7840 - Air Piping and Tubing
7841 - Air Supply System
7841A - Tubing System
(blank)
(blank)
7841B - Manifold Header System
(blank)
(blank)
7841C - Air Supply Piping and tubing system
(blank)
(blank)
7842 - Pneumatic Signal Tubing
7842A - For Converter Signal (I/P, P/I)
(blank)
(blank)
7842B - For Transmitter/Controller Signal
(blank)
(blank)
7842C - For Fire Detection Signal
(blank)
(blank)
7850 - Support Fabrication
7851 - Stanchion
7851A - Pedestal Mount Type
7851Aa - DN50 x 1500mmL, sch40, CS
(blank)
7851Ab - DN50 x 1700mmL, sch40, CS
(blank)
7851Ac - DN50 x 600mmL, sch40, CS
(blank)
7851Ad - DN150 x 3000mmL, sch40, CS
(blank)
7851B - Line Mount Type
(blank)
(blank)
7852 - Frame / Bracket
7852A - For Junction Box
(blank)
(blank)
7852B - For Auxiliary Instrument
(blank)
(blank)
7853 - Cable Duct/Ladder support for Main Cable
7853A - Weight : under 5kg
(blank)
(blank)
7853B - Weight : 5 to 15kg
(blank)
(blank)
7853C - Weight : above 15kg
(blank)
(blank)
7854 - Grating Penetrations (300mm X 300mm)
(blank)
(blank)
(blank)
7860 - Miscellaneous Installation
7861 - Supply and Install Tag No. Plate / Labels
7861A - Name plate for instruments, Type A
(blank)
(blank)
7861B - Name plate for instruments, Type B
(blank)
(blank)
7863 - Polymeric Cable Protection Cover (to AS 4702)
(blank)
(blank)
(blank)
7864 - Instrument Protection
(blank)
(blank)
(blank)
7865 - Cable Route Marker
7864A - Sun Shade
(blank)
(blank)
7866 - Cable Marker (to AS/NZS 2648.1)
(blank)
(blank)
(blank)
7867 - Excavation
7867A - Excavation of Cable trench
7867Aa - Excavation of Cable Trenchunder Building
(blank)
7867Ab - Excavation of Cable Trenchnot under Building
(blank)
7867C - Manual Excavation of buried coiled cables
(blank)
(blank)
7868 - Backfilling
7868A - Back filling by Soil
(blank)
(blank)
7868B - Sand filling
7868Ba - Sand Fillingunder Building
(blank)
7868Bb - Sand Fillingnot under Building
(blank)
7868C - Disposal
(blank)
(blank)
7869 - Minor Foundations
7869A - Minor Foundations Less Than 0.05M3
(blank)
(blank)
7869B - Minor Foundations 0.05 to 0.15M3
(blank)
(blank)
7870 - Support For Piping Flushing Activities
7871 - Cable Removal/Reinstallation
(blank)
(blank)
(blank)
7872 - Air Supply Removal/Reinstallation
(blank)
(blank)
(blank)
7900 - Inspections, Precommissioning Checks and Function Testing
7920 - Function Testing
No Code
No Code
7920AA - JC01 – INSTRUMENT PANEL, ENERGISATION
(blank)
7920AB - JC02 – SERIAL LINK
(blank)
7920AC - JC03 – ACTUATED VALVE, MODULATING
(blank)
7920AD - JC04 – ACTUATED VALVE, SWITCHING (ON/OFF)
(blank)
7920AE - JC05 – DAMPER
(blank)
7920AF - JC06 – TRANSMITTER
(blank)
7920AG - JC07 – ANALOG OUTPUT
(blank)
7920AH - JC08 – REMOTE INDICATOR
(blank)
7920AI - JC09 – DISCRETE INPUT
(blank)
7920AJ - JC10 – DISCRETE OUTPUT
(blank)
7920AK - JC11 – ANALYSER / COMPLEX INSTRUMENT
(blank)
7920AL - JC12 – PUSHBUTTON
(blank)
7920AM - JC13 – GAS / FLAME DETECTOR
(blank)
7920AN - JC14 – SMOKE / HEAT DETECTOR (not used)
(blank)
7920AO - JC15 – MCC / ICSS Signals
(blank)
7920AP - JC16 – MOV
(blank)
7920AQ - JC17 – CONDITION AND PERFORMANCE MONITORING SYSTEM
(blank)
7920AR - JC18 – TRENDMASTER SYSTEM ACCELEROMETER
(blank)
7930 - Precommissioning Checks
No Code
No Code
No Code
7930AAA - XP01 Hazardous Area Consolidated
7930AAB - XP03 Hazardous Area Site
7930ACB - JP02 Calibration Transmitters
7930ACC - JP02 Calibration Pressure / Temperature Switch
7930ACD - JP02 Calibration Control Valve
7930ACE - JP02 Calibration OnOff Valve
7930AB - JP01 Miscellaneous Equipment
(blank)
7930AC - JP02 Caliabration
7930ACA - JP02 Calibration Pressure / Temperature Gauge
7930AD - JP03 Local Gauge
(blank)
7930AE - JP04 Instrument Installation
(blank)
7930AF - JP05 Bursting Disk
(blank)
7930AG - JP06 Actuated Valve Assembly
(blank)
7930AH - JP07 Temperatuere Element
(blank)
7930AI - JP08 Instrument Installation On Skid
(blank)
7930AJ - JP09 Control Panel/Console
(blank)
7930AK - JP10 Junction Box
(blank)
7930AL - JP11 Instrument Cable
(blank)
7930AM - JP12 Annunciator Panel
(blank)
7930AN - JP13 Fire and Gas Device
(blank)
7930AO - JP14 Frangible Bulb/Pneumatic Detection & Deluge System
(blank)
7930AP - JP15 Earthing System
(blank)
7930AQ - JP16 Flow Orifice
(blank)
7930AR - JP17 Relief Valve
(blank)
7930AS - JP18 Instrument Tubing Cleaning & Testing
(blank)
7930AT - JP19 CAT 6 Cable
(blank)
7930AU - JP20 CAT6A Cable
(blank)
7930AV - JP21 Fibre Optic Cable
(blank)
7930AW - JP22 Earth Bar
(blank)
Grand Total
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## List of Norms
1 |  | 6
Appendix 1: Initial Subcontract Price
Bill No. 13: ELE-1A&B Electrical
FWBS Code |  | Norms (Adjusted for weather 7.5%) | Norms (Adjusted QA/QC, HSE, Supv. -10.64%) | Norms Original
Description
8100 |  |  |  | -
-
-
-
-
-
8110 | Generator and Associated Equipment |  |  | -
8112 | Emergency Generator (2214kW) |  |  | -
8120 | Transformer, Harmonic Filter and Neutral Earthing Resistor |  |  | -
8121 | Transformer (non field assembly) |  |  | -
8122 | Transformer (Field Assembly) |  |  | -
8122A | 10 MVA | 266.4191 | 288.0207 | 322.315
8122B | 16 MVA | 266.3985 | 287.9983 | 322.29
8122C | 18 MVA | 266.3778 | 287.976 | 322.265
8122D | 20 MVA | 355.2269 | 384.0291 | 429.755
8122E | 22 MVA | 355.169 | 383.9665 | 429.685
8122F | 30 MVA | 355.2269 | 384.0291 | 429.755
8122G | 26.3 MVA & 26.4 MVA | 355.1704 | 383.968 | 429.6867
8122H | 50.3 MVA | 1287.4893 | 1391.8803 | 1557.61
8122I | 68.6 MVA (Earthing Transformer) | 1287.7001 | 1392.1082 | 1557.865
8122J | 95 MVA with OLTC | 1287.7001 | 1392.1082 | 1557.865
8122K | 160 MVA and above with OLTC | 1443.1095 | 1560.1184 | 1745.88
8122L | 2.8 MVA | 133.2096 | 144.0103 | 161.1575
8122M | 3.9 MVA | 133.2116 | 144.0126 | 161.16
8126 | Harmonic Filter |  |  | -
8126A | 4 Branch Filter Bank 8MVA | 44.3956 | 47.9953 | 53.71
8126B | 4 Branch Filter Bank 17MVA | 44.3956 | 47.9953 | 53.71
8127 | Outdoor Harmonic Filter Resistor | 47.9485 | 51.8362 | 58.0083
8128 | Neutral Earthing Resistor (NER) |  |  | -
8128A | 6.6kV | 34.629 | 37.4367 | 41.8943
8128B | 33kV |  |  | -
8128C | 132kV |  |  | -
8130 | Gas Insulated Switchgear (GIS) installed inside LER by Module Fabricator |  |  | -
8130A | 132kV GIS | 111.0085 | 120.0091 | 134.2985
8130B | 33kV GIS | 66.6051 | 72.0056 | 80.5792
8130C | Below 33kV GIS | 49.9461 | 53.9958 | 60.425
8140 | Switchgear and MCC |  |  | -
8141 | Switchgear and MCC installed inside LER by Module Fabricator |  |  | -
8141A | Low Vol. Switchgear | 12.2096 | 13.1996 | 14.7713
8141B | Low Vol. MCC | 12.2094 | 13.1994 | 14.771
8141C | 6 KV to 14.6 KV Switchgear and MCC | 12.2097 | 13.1997 | 14.7714
8141D | 15 KV to 40.5 KV Switchgear |  |  | -
8142 | Switchgear and MCC installed inside buildings at Site |  |  | -
8142A | Low Vol. Switchgear | 20.2039 | 21.842 | 24.4427
8142B | Low Vol. MCC | 20.2038 | 21.842 | 24.4427
8150 | UPS system |  |  | -
8151 | UPS installed inside LER/LIR by Module Fabricator |  |  | -
8151A | AC UPS |  |  | -
8151AA | Single Type | 12.2102 | 13.2003 | 14.772
8151AB | Dual Type |  |  | -
8151B | DC UPS |  |  | -
8151BA | Single Type | 12.2096 | 13.1995 | 14.7712
8151BB | Dual Type |  |  | -
8152 | UPS installed inside Buildings at Site |  |  | -
8152A | AC UPS |  |  | -
8152AA | Single Type | 20.2039 | 21.842 | 24.4427
8152AB | Dual Type |  |  | -
8152B | DC UPS |  |  | -
8152BA | Single Type |  |  | -
8152BB | Dual Type |  |  | -
8153 | Battery Bank |  |  | -
8153A | Battery Cell Q'ty:0 to 49 cells |  |  | -
8153B | Battery Cell Q'ty:50 to 99 cells | 90.0185 | 97.3172 | 108.9047
8153C | Battery Cell Q'ty:100 to 149 cells |  |  | -
8153D | Battery Cell Q'ty:150 to 199 cells | 176.0528 | 190.3274 | 212.9894
8153E | Battery Cell Q'ty:200 to 249 cells |  |  | -
8153F | Battery Cell Q'ty:250 to 299 cells |  |  | -
8153G | Battery Cell Q'ty:300 to 349 cells | 336.9946 | 364.3185 | 407.6975
8153H | Battery Cell Q'ty:350 to 399 cells |  |  | -
8153I | Battery Cell Q'ty:400 to 449 cells |  |  | -
8153J | Battery Cell Q'ty:450 to 499 cells |  |  | -
8153K | Battery Cell Q'ty:500 to 549 cells |  |  | -
8153L | Battery Cell Q'ty:550 to 599 cells |  |  | -
8153M | Battery Cell Q'ty:600 to 649 cells |  |  | -
8153N | Battery Cell Qty 972 | 892.0658 | 964.3955 | 1079.225
8160 | Bus Duct |  |  | -
8161 | LV Bus Duct |  |  | -
8161A | L= 5m & Below | 46.6604 | 50.4437 | 56.45
8161B | L= 5.1m to 10m | 74.3982 | 80.4305 | 90.0073
8161C | L= 10.1m to 15m | 102.1461 | 110.4282 | 123.5768
8161D | L= 15m Over | 135.4543 | 146.4371 | 163.8732
8162 | 6.6kV Bus Duct |  |  | -
8162A | L= 5m & Below |  |  | -
8162B | L= 5.1m to 10m |  |  | -
8162C | L= 10.1m to 15m |  |  | -
8162D | L= 15m Over | 135.4501 | 146.4326 | 163.8681
8163 | 33kV Bus Duct |  |  | -
8163A | L= 5m & Below |  |  | -
8163B | L= 5.1m to 10m |  |  | -
8163C | L= 10.1m to 15m |  |  | -
8163D | L= 15m Over | 135.4641 | 146.4476 | 163.885
8170 | Control, Distribution and Miscellaneous Panels |  |  | -
8171 | Floor Mount Panel installed inside LER by Module Fabricator |  |  | -
8171A | Up to 800W panel | 6.6601 | 7.2001 | 8.0574
8171B | Above 800W panel | 6.6595 | 7.1995 | 8.0567
8172 | Wall Mount Panel installed inside LER by Module Fabricator | 4.4395 | 4.7995 | 5.371
8173 | Floor Mount Panel |  |  | -
8173A | Up to 800W panel | 19.7597 | 21.3618 | 23.9053
8173B | Above 800W panel |  |  | -
8174 | Wall Mount Panel | 9.5468 | 10.3209 | 11.5498
8180 | Power Distribution Control System (PDCS) |  |  | -
8181 | PDCS Controller Cabinet |  |  | -
8181A | PDCS Controller Cabinet installed at Site | 19.7602 | 21.3624 | 23.906
8181B | PDCS Controller Cabinet installed by Module Fabricator | 5.5499 | 5.9999 | 6.7143
8182 | Human Machine Interface (HMI) Cabinet |  |  | -
8182A | Human Machine Interface (HMI) Cabinet installed at Site | 19.7608 | 21.363 | 23.9067
8182B | Human Machine Interface (HMI) Cabinet installed by Module Fabricator | 5.5498 | 5.9997 | 6.7141
8183 | Load Shed Controller Cabinet |  |  | -
8183A | Load Shed Controller Cabinet installed at Site |  |  | -
8183B | Load Shed Controller Cabinet installed by Module Fabricator | 5.55 | 6 | 6.7144
8190 | Prefabricated Buildings and Auxiliaries |  |  | -
8191 | LER Receipt |  |  | -
8191A | Main Substation Modules (1) and (2) | 777.4605 | 840.4978 | 940.575
8191B | VSDS LER | 1082.3349 | 1170.0918 | 1309.4133
8191C | All Other LER | 1082.423 | 1170.1871 | 1309.52
8192 | LIR Receipt |  |  | -
8192A | All LIR | 1082.4129 | 1170.1762 | 1309.5078
8200 | Power Work |  |  | -
| Installation of equipment including:- |  |  | -
| · Collection of material from Contractor’s warehouse, staging area or laydown/storage area; |  |  | -
| · Temporary storage as required; |  |  | -
| · Provision of all required construction materials and consumables; |  |  | -
| · Installation in accordance with supplied drawings and specifications; |  |  | -
8210 | Motor and Motor Operated Valve (MOV) |  |  | -
8211 | Motor |  |  | -
8214 | MOV |  |  | -
8220 | Local Equipment (Outside) |  |  | -
8221 | Control Station | 5.3346 | 5.7672 | 6.4539
8222 | Local Dist. Panel/Starter | 5.9762 | 6.4607 | 7.23
8223 | 3 Phase Power Outlet | 6.6712 | 7.2121 | 8.0708
8224 | Local Control Panel for Package Equipment | 10.9765 | 11.8665 | 13.2794
8225 | Power Junction Box |  |  | -
8225AA | Power Junction Box (less than 10000 mm2, e.g WxH 100mm x 100mm) |  |  | -
8225AB | Power Junction Box (less than 22500 mm2, e.g WxH 150mm x 150mm) |  |  | -
8225AC | Power Junction Box (less than 30000 mm2, e.g WxH 200mm x 150mm) | 4.447 | 4.8076 | 5.38
8225AD | Power Junction Box (less than 60000 mm2, e.g WxH 300mm x 200mm) | 7.7813 | 8.4123 | 9.4139
8225AE | Power Junction Box (less than 90000 mm2, e.g WxH 300mm x 300mm) | 7.7804 | 8.4112 | 9.4128
8225AF | Power Junction Box (less than 180000 mm2, e.g WxH 600mm x 300mm) | 8.3362 | 9.0121 | 10.0852
8225AG | Power Junction Box (greater than 180000 mm2, e.g WxH 900mm x 300mm) | 11.4005 | 12.3249 | 13.7924
8225BA | Ex d Power Junction Box (less than 10000 mm2, e.g WxH 100mm x 100mm) |  |  | -
8225BB | Ex d Power Junction Box (less than 22500 mm2, e.g WxH 150mm x 150mm) | 3.7842 | 4.091 | 4.5781
8225BC | Ex d Power Junction Box (less than 30000 mm2, e.g WxH 200mm x 150mm) | 4.4479 | 4.8086 | 5.3811
8225BD | Ex d Power Junction Box (less than 60000 mm2, e.g WxH 300mm x 200mm) | 8.0592 | 8.7126 | 9.75
8225BE | Ex d Power Junction Box (less than 90000 mm2, e.g WxH 300mm x 300mm) | 8.0592 | 8.7126 | 9.75
8225BF | Ex d Power Junction Box (less than 180000 mm2, e.g WxH 600mm x 300mm) | 8.6143 | 9.3128 | 10.4217
8225BG | Ex d Power Junction Box (greater than 180000 mm2, e.g WxH 900mm x 300mm) | 11.9541 | 12.9234 | 14.4621
8260 | Power and Control Cabling |  |  | -
8261 | Cable |  |  | -
8261A | Low Voltage |  |  | -
8261Aa | 0.6/1kV _ Below 10sqmm | 0.11833 | 0.12792 | 0.14316
8261Ab | 0.6/1kV _ 10sqmm to below 50sqmm | 0.15207 | 0.1644 | 0.18397
8261Ac | 0.6/1kV _ 50sqmm to below 120sqmm | 0.17427 | 0.1884 | 0.21083
8261Ad | 0.6/1kV _ 120sqmm to below 300mm2 | 0.35068 | 0.37911 | 0.42426
8261Ae | 0.6/1kV _ 300sqmm and above | 0.61081 | 0.66033 | 0.73896
8261B | 1.8/3kV Cable |  |  | -
8261C | 3.6/6kV Cable |  |  | -
8261D | 6/10kV Cable |  |  | -
8261Da | 6/10kV Cable _ Below 70sqmm |  |  | -
8261Daa | 6/10kV Cable _ Below 70sqmm _ 3C | 0.28527 | 0.3084 | 0.34512
8261Dab | 6/10kV Cable _ Below 70sqmm _ 1C |  |  | -
8261Db | 6/10kV Cable _ 70sqmm to below 185sqmm |  |  | -
8261Dba | 6/10kV Cable _ 70sqmm to below 185sqmm _ 3C | 0.39759 | 0.42983 | 0.48101
8261Dbb | 6/10kV Cable _ 70sqmm to below 185sqmm _ 1C |  |  | -
8261Dc | 6/10kV Cable _ 185sqmm and above |  |  | -
8261Dca | 6/10kV Cable _ 185sqmm and above _ 3C |  |  | -
8261Dcb | 6/10kV Cable _ 185sqmm and above _ 1C | 0.70535 | 0.76254 | 0.85334
8261E | 19/33kV Cable | 0.94117 | 1.0175 | 1.1386
8261F | 45 KV to 72.5 KV Cable | 1.2302 | 1.33 | 1.4883
8261G | 76/132kV Cable |  |  | -
8261Ga | 76/132kV _ Below 800sqmm | 2.4237 | 2.6203 | 2.9323
8261Gb | 76/132kV _ 800sqmm and above | 2.9788 | 3.2204 | 3.6038
8261H | Control |  |  | -
8261Ha | Control _ less than 8C | 0.12943 | 0.13992 | 0.15658
8261Hb | Control _ 8C to less than 12C | 0.14034 | 0.15171 | 0.16978
8261Hc | Control _ 12C to less than 20C | 0.19583 | 0.21171 | 0.23692
8261Hd | Control _ 20C and more | 0.24025 | 0.25973 | 0.29066
8261He | Control _ RTD Cable (5T) | 0.17382 | 0.18792 | 0.21029
8261Hf | Control _ Fiber Optic Cable (2 to 6 Core) | 0.14054 | 0.15193 | 0.17002
8261Hg | Control _ Fiber Optic Cable (7 to 12 Core) | 0.21805 | 0.23573 | 0.2638
8261Hh | Control _ Fiber Optic Cable (24 Core) | 0.24025 | 0.25973 | 0.29066
8261Hi | Control _ Fiber Optic Cable (36 Core) | 0.26245 | 0.28373 | 0.31752
8261Hj | Control _ Fiber Optic Cable (48 Core) |  |  | -
8261Hk | Control _ Fiber Optic Cable (60 Core) |  |  | -
8261Hl | Control _ Fiber Optic Cable (72 Core) |  |  | -
8263 | Cable (for when cable is installed and left coiled by other Subcontractors) |  |  | -
8263A | Low Voltage |  |  | -
8263Aa | 0.6/1kV _ Below 10sqmm | 0.21643 | 0.23398 | 0.26184
8263Ab | 0.6/1kV _ 10sqmm to below 50sqmm | 0.30522 | 0.32997 | 0.36926
8263Ac | 0.6/1kV _ 50sqmm to below 120sqmm | 0.5605 | 0.60595 | 0.6781
8263Ad | 0.6/1kV _ 120sqmm to below 300mm2 | 0.83799 | 0.90593 | 1.0138
8263Ae | 0.6/1kV _ 300sqmm and above |  |  | -
8263B | 1.8/3kV Cable |  |  | -
8263C | 3.6/6kV Cable |  |  | -
8263D | 6/10kV Cable |  |  | -
8263Da | 6/10kV Cable _ Below 70sqmm |  |  | -
8263Daa | 6/10kV Cable _ Below 70sqmm _ 3C | 0.57162 | 0.61797 | 0.69155
8263Dab | 6/10kV Cable _ Below 70sqmm _ 1C | 0.45431 | 0.49114 | 0.54962
8263Db | 6/10kV Cable _ 70sqmm to below 185sqmm |  |  | -
8263Dba | 6/10kV Cable _ 70sqmm to below 185sqmm _ 3C | 0.78253 | 0.84598 | 0.94671
8263Dbb | 6/10kV Cable _ 70sqmm to below 185sqmm _ 1C |  |  | -
8263Dc | 6/10kV Cable _ 185sqmm and above |  |  | -
8263Dca | 6/10kV Cable _ 185sqmm and above _ 3C | 1.3042 | 1.41 | 1.5778
8263Dcb | 6/10kV Cable _ 185sqmm and above _ 1C | 0.65406 | 0.70709 | 0.79128
8263E | 19/33kV Cable | 1.2044 | 1.3021 | 1.4571
8263F | 45 KV to 72.5 KV Cable |  |  | -
8263G | 76/132kV Cable |  |  | -
8263Ga | 76/132kV _ Below 800sqmm |  |  | -
8263Gb | 76/132kV _ 800sqmm and above |  |  | -
8263H | Control |  |  | -
8263Ha | Control _ less than 8C | 0.21643 | 0.23398 | 0.26184
8263Hb | Control _ 8C to less than 12C | 0.22753 | 0.24598 | 0.27527
8263Hc | Control _ 12C to less than 20C | 0.29415 | 0.318 | 0.35586
8263Hd | Control _ 20C and more | 0.36075 | 0.39 | 0.43643
8263He | Control _ RTD Cable (5T) | 0.26084 | 0.28199 | 0.31556
8263Hf | Control _ Fiber Optic Cable (2 to 6 Core) | 0.28304 | 0.30599 | 0.34243
8263Hg | Control _ Fiber Optic Cable (7 to 12 Core) |  |  | -
8263Hh | Control _ Fiber Optic Cable (24 Core) | 0.37188 | 0.40204 | 0.44991
8263Hi | Control _ Fiber Optic Cable (36 Core) |  |  | -
8263Hj | Control _ Fiber Optic Cable (48 Core) | 0.41628 | 0.45003 | 0.50362
8263Hk | Control _ Fiber Optic Cable (60 Core) |  |  | -
8263Hl | Control _ Fiber Optic Cable (72 Core) |  |  | -
8270 | Termination and Splicing of Cable |  |  | -
8271 | Termination of Cable (including Compound Filled Gland) |  |  | -
8271A | Low Voltage |  |  | -
8271Aa | 0.6/1kV _ Below 10sqmm | 1.4979 | 1.6194 | 1.8122
8271Ab | 0.6/1kV _ 10sqmm to below 50sqmm | 2.3312 | 2.5203 | 2.8203
8271Ac | 0.6/1kV _ 50sqmm to below 120sqmm | 5.6604 | 6.1194 | 6.848
8271Ad | 0.6/1kV _ 120sqmm to below 300mm2 | 11.2101 | 12.119 | 13.562
8271Ae | 0.6/1kV _ 300sqmm and above |  |  | -
8271B | 1.8/3kV Cable |  |  | -
8271C | 3.6/6kV Cable |  |  | -
8271D | 6/10kV Cable |  |  | -
8271Da | 6/10kV Cable _ Below 70sqmm |  |  | -
8271Daa | 6/10kV Cable _ Below 70sqmm _ 3C | 10.1022 | 10.9213 | 12.2217
8271Dab | 6/10kV Cable _ Below 70sqmm _ 1C | 3.4406 | 3.7196 | 4.1625
8271Db | 6/10kV Cable _ 70sqmm to below 185sqmm |  |  | -
8271Dba | 6/10kV Cable _ 70sqmm to below 185sqmm _ 3C |  |  | -
8271Dbb | 6/10kV Cable _ 70sqmm to below 185sqmm _ 1C |  |  | -
8271Dc | 6/10kV Cable _ 185sqmm and above |  |  | -
8271Dca | 6/10kV Cable _ 185sqmm and above _ 3C |  |  | -
8271Dcb | 6/10kV Cable _ 185sqmm and above _ 1C |  |  | -
8271E | 19/33kV Cable |  |  | -
8271F | 45 KV to 72.5 KV Cable |  |  | -
8271G | 76/132kV Cable |  |  | -
8271Ga | 76/132kV _ Below 800sqmm |  |  | -
8271Gb | 76/132kV _ 800sqmm and above |  |  | -
8271H | Control |  |  | -
8271Ha | Control _ less than 8C |  |  | -
8271Hb | Control _ 8C to less than 12C |  |  | -
8271Hc | Control _ 12C to less than 20C |  |  | -
8271Hd | Control _ 20C and more |  |  | -
8271He | Control _ RTD Cable (5T) |  |  | -
8271Hf | Control _ Fiber Optic Cable (2 to 6 Core) |  |  | -
8271Hg | Control _ Fiber Optic Cable (7 to 12 Core) |  |  | -
8271Hh | Control _ Fiber Optic Cable (24 Core) |  |  | -
8271Hi | Control _ Fiber Optic Cable (36 Core) |  |  | -
8271Hj | Control _ Fiber Optic Cable (48 Core) |  |  | -
8271Hk | Control _ Fiber Optic Cable (60 Core) |  |  | -
8271Hl | Control _ Fiber Optic Cable (72 Core) |  |  | -
8272 | Termination of Cable (including non-compound filled gland) |  |  | -
8272A | Low Voltage |  |  | -
8272Aa | 0.6/1kV _ Below 10sqmm | 1.2209 | 1.3199 | 1.4771
8272Ab | 0.6/1kV _ 10sqmm to below 50sqmm | 2.331 | 2.5199 | 2.82
8272Ac | 0.6/1kV _ 50sqmm to below 120sqmm | 4.5508 | 4.9197 | 5.5055
8272Ad | 0.6/1kV _ 120sqmm to below 300mm2 | 7.8808 | 8.5198 | 9.5342
8272Ae | 0.6/1kV _ 300sqmm and above | 11.2114 | 12.1204 | 13.5636
8272B | 1.8/3kV Cable |  |  | -
8272C | 3.6/6kV Cable | 13.4321 | 14.5212 | 16.2502
8272D | 6/10kV Cable |  |  | -
8272Da | 6/10kV Cable _ Below 70sqmm |  |  | -
8272Daa | 6/10kV Cable _ Below 70sqmm _ 3C | 7.8807 | 8.5197 | 9.5341
8272Dab | 6/10kV Cable _ Below 70sqmm _ 1C | 3.4413 | 3.7204 | 4.1633
8272Db | 6/10kV Cable _ 70sqmm to below 185sqmm |  |  | -
8272Dba | 6/10kV Cable _ 70sqmm to below 185sqmm _ 3C | 13.4308 | 14.5198 | 16.2487
8272Dbb | 6/10kV Cable _ 70sqmm to below 185sqmm _ 1C | 5.6614 | 6.1204 | 6.8492
8272Dc | 6/10kV Cable _ 185sqmm and above |  |  | -
8272Dca | 6/10kV Cable _ 185sqmm and above _ 3C | 17.3164 | 18.7204 | 20.9494
8272Dcb | 6/10kV Cable _ 185sqmm and above _ 1C | 6.7707 | 7.3196 | 8.1912
8272E | 19/33kV Cable | 8.9914 | 9.7204 | 10.8778
8272F | 45 KV to 72.5 KV Cable |  |  | -
8272G | 76/132kV Cable |  |  | -
8272Ga | 76/132kV _ Below 800sqmm | 56.6142 | 61.2045 | 68.4921
8272Gb | 76/132kV _ 800sqmm and above | 84.3665 | 91.207 | 102.0669
8272H | Control |  |  | -
8272Ha | Control _ less than 8C | 1.4984 | 1.6199 | 1.8128
8272Hb | Control _ 8C to less than 12C | 2.886 | 3.12 | 3.4915
8272Hc | Control _ 12C to less than 20C | 3.9959 | 4.3198 | 4.8342
8272Hd | Control _ 20C and more | 5.1063 | 5.5203 | 6.1776
8272He | Control _ RTD Cable (5T) | 2.886 | 3.12 | 3.4915
8272Hf | Control _ Fiber Optic Cable (2 to 6 Core) | 3.9962 | 4.3202 | 4.8346
8272Hg | Control _ Fiber Optic Cable (7 to 12 Core) | 7.9925 | 8.6406 | 9.6694
8272Hh | Control _ Fiber Optic Cable (24 Core) | 15.9854 | 17.2815 | 19.3392
8272Hi | Control _ Fiber Optic Cable (36 Core) |  |  | -
8272Hj | Control _ Fiber Optic Cable (48 Core) | 31.9705 | 34.5627 | 38.678
8272Hk | Control _ Fiber Optic Cable (60 Core) |  |  | -
8272Hl | Control _ Fiber Optic Cable (72 Core) |  |  | -
8273 | Splicing of cable |  |  | -
8273B | 1.8/3kV Cable |  |  | -
8273C | 3.6/6kV Cable |  |  | -
8273D | 6/10kV Cable |  |  | -
8273Da | 6/10kV Cable _ Below 70sqmm |  |  | -
8273Daa | 6/10kV Cable _ Below 70sqmm _ 3C |  |  | -
8273Dab | 6/10kV Cable _ Below 70sqmm _ 1C |  |  | -
8273Db | 6/10kV Cable _ 70sqmm to below 185sqmm |  |  | -
8273Dba | 6/10kV Cable _ 70sqmm to below 185sqmm _ 3C | 22.4224 | 24.2404 | 27.1267
8273Dbb | 6/10kV Cable _ 70sqmm to below 185sqmm _ 1C |  |  | -
8273Dc | 6/10kV Cable _ 185sqmm and above |  |  | -
8273Dca | 6/10kV Cable _ 185sqmm and above _ 3C |  |  | -
8273Dcb | 6/10kV Cable _ 185sqmm and above _ 1C |  |  | -
8273E | 19/33kV Cable | 22.4237 | 24.2419 | 27.1283
8273F | 45 KV to 72.5 KV Cable |  |  | -
8273G | 76/132kV Cable |  |  | -
8273Ga | 76/132kV _ Below 800sqmm |  |  | -
8273Gb | 76/132kV _ 800sqmm and above |  |  | -
8273H | Control |  |  | -
8273Hf | Control _ Fiber Optic Cable (2 to 6 Core) |  |  | -
8273Hg | Control _ Fiber Optic Cable (7 to 12 Core) |  |  | -
8273Hh | Control _ Fiber Optic Cable (24 Core) |  |  | -
8273Hi | Control _ Fiber Optic Cable (36 Core) |  |  | -
8273Hj | Control _ Fiber Optic Cable (48 Core) |  |  | -
8273Hk | Control _ Fiber Optic Cable (60 Core) |  |  | -
8273Hl | Control _ Fiber Optic Cable (72 Core) |  |  | -
8280 | Cable Way |  |  | -
8281 | Cable Ladder or Tray and Cover - Galvanised Steel |  |  | -
8281A | Perforated Cable Tray equal to or less than 200mm Width | 1.1228 | 1.2138 | 1.3584
8281B | Cable Ladder 300mm Width | 1.5864 | 1.7151 | 1.9193
8281C | Cable Ladder 600mm Width | 2.3208 | 2.509 | 2.8077
8281D | Cable Ladder 900mm Width | 2.6981 | 2.9169 | 3.2642
8281E | Perforated Cable Tray Cover equal to or less than 200mm Width |  |  | -
8281F | Cable Ladder Cover 300mm Width | 0.49953 | 0.54003 | 0.60433
8281G | Cable Ladder Cover 600mm Width | 0.58833 | 0.63603 | 0.71176
8281H | Cable Ladder Cover 900mm Width | 0.777 | 0.84 | 0.94002
8282 | Cable Ladder or Tray and Cover - Stainless Steel |  |  | -
8282A | Perforated Cable Tray equal to or less than 200mm Width | 1.8213 | 1.969 | 2.2034
8282B | Cable Ladder 300mm Width | 2.0675 | 2.2352 | 2.5013
8282C | Cable Ladder 600mm Width | 2.8067 | 3.0342 | 3.3955
8282D | Cable Ladder 900mm Width | 4.5393 | 4.9074 | 5.4917
8282E | Perforated Cable Tray Cover equal to or less than 200mm Width |  |  | -
8282F | Cable Ladder Cover 300mm Width | 0.58835 | 0.63605 | 0.71178
8282G | Cable Ladder Cover 600mm Width | 0.77706 | 0.84006 | 0.94009
8282H | Cable Ladder Cover 900mm Width |  |  | -
8283 | Removal and Reinstallation of MF Installed Ladder Cover |  |  | -
8283A | Cable Ladder Cover 300mm Width | 0.77704 | 0.84005 | 0.94007
8283B | Cable Ladder Cover 600mm Width | 0.95465 | 1.0321 | 1.1549
8283C | Cable Ladder Cover 900mm Width | 1.332 | 1.44 | 1.6114
8284 | Cable Transit |  |  | -
8284A | Cable Transit Frame |  |  | -
8284B | Cable Transit Block - Used | 0.33299 | 0.35999 | 0.40285
8284C | Cable Transit Block at LIR | 0.33301 | 0.36001 | 0.40288
8284D | Cable Transit Block at LIR - Spare | 0.111 | 0.12 | 0.13429
8285 | Grating Penetration (300mm X 300mm) | 3.4314 | 3.7096 | 4.1513
8290 | Other Work |  |  | -
8295 | Cable Trench |  |  | -
8295A | Excavation |  |  | -
8295Aa | Excavation of cable trench | 0.77256 | 0.8352 | 0.93464
8295Ab | Manual Excavation of buried coiled cables | 7.2998 | 7.8916 | 8.8313
8295Ac | Removal of Temporary Sand and Geofabric Material | 3.3303 | 3.6003 | 4.029
8295Ad | Excavation Under LER Buildings | 1.6754 | 1.8112 | 2.0269
8295B | Sand Filling |  |  | -
8295Ba | Sand Filling-under Building | 2.1446 | 2.3185 | 2.5945
8295Bb | Sand Filling-not under Building | 1.0956 | 1.1844 | 1.3254
8295Bc | Fluidised Thermal Backfill – under building | 2.1443 | 2.3182 | 2.5942
8295Bd | Fluidised Thermal Backfill – not under building | 1.0955 | 1.1843 | 1.3253
8295C | Backfilling | 0.9324 | 1.008 | 1.128
8295D | Polymeric Cable Protection Cover (to AS 4702) | 0.11056 | 0.11952 | 0.13375
8295E | Cable Marker Tape (to AS/NZS 2648.1) | 0.11099 | 0.11999 | 0.13428
8295F | Stub-up PVC conduit |  |  | -
8295Fa | 100 - 150mm dia 1500-2000mm radius bend | 0.77699 | 0.83998 | 0.94
8295Fb | 100 - 150mm dia 1000-1500mm radius bend | 1.0539 | 1.1393 | 1.275
8295Fc | 100 - 150mm dia 500-1000mm radius bend | 1.0546 | 1.1401 | 1.2758
8295Fd | 100 - 150mm dia up to 500mm radius bend |  |  | -
8295Fe | less than 100mm dia 500-1500mm radius bend |  |  | -
8295Ff | less than 100mm dia up to 500mm radius bend |  |  | -
8295Fg | 100-150mm dia straight stub up | 0.77693 | 0.83992 | 0.93993
8295Fh | less than 100mm dia straight stub up | 0.77693 | 0.83993 | 0.93993
8295G | Soil Disposal | 0.27972 | 0.3024 | 0.33841
8296 | Cable Route Markers | 1.11 | 1.1999 | 1.3428
8297 | Minor Foundations |  |  | -
8297A | Minor Foundations less than 0.1M3 | 1.11 | 1.2 | 1.3429
8297B | Minor Foundations 0.1 to 0.15M3 | 1.665 | 1.8 | 2.0144
8298 | Fabrication of Supports For Cableway and Cable Supports |  |  | -
8298A | Weight: below 1kg |  |  | -
8298B | Weight: 1kg to below 5kg | 2.2201 | 2.4001 | 2.6858
8298C | Weight: 5kg to below 15kg | 3.3302 | 3.6002 | 4.0289
8298D | Weight: 15kg to below 25kg | 4.1624 | 4.4999 | 5.0357
8298E | Weight: 25kg to below 35kg | 4.6623 | 5.0403 | 5.6404
8298F | Weight: 35kg to below 45kg | 5.9935 | 6.4794 | 7.2509
8298G | Weight: 190kg to 210kg approximately 200kg | 22.2019 | 24.0021 | 26.86
8298H | Weight: 290kg to 310kg approximately 300kg | 33.3002 | 36.0002 | 40.2867
8299 | Installation of Miscellaneous Support |  |  | -
8299A | Weight: below 1kg |  |  | -
8299B | Weight: 1kg to below 5kg | 1.9426 | 2.1001 | 2.3501
8299C | Weight: 5kg to below 15kg | 4.1621 | 4.4996 | 5.0353
8299D | Weight: 15kg to below 25kg | 6.938 | 7.5005 | 8.3936
8299E | Weight: 25kg to below 35kg | 7.7699 | 8.3998 | 9.4
8299F | Weight: 35kg to below 45kg | 9.9891 | 10.799 | 12.0849
8299G | Weight: 190kg to 210kg approximately 200kg | 23.3137 | 25.204 | 28.205
8299H | Weight: 290kg to 310kg approximately 300kg | 34.9653 | 37.8003 | 42.3011
8300 | LIGHTING |  |  | -
| Installation of equipment including:- |  |  | -
| · Collection of material from Contractor’s warehouse, staging area or laydown/storage area; |  |  | -
| · Temporary storage as required; |  |  | -
| · Provision of all required construction materials and consumables; |  |  | -
| · Installation in accordance with supplied drawings and specifications; |  |  | -
8320 | Lighting in Plant |  |  | -
8321 | Lighting Pole |  |  | -
8321A | Up to 3M Height | 3.7572 | 4.0619 | 4.5455
8321B | Above 3M Height up to 8M Height | 7.6818 | 8.3047 | 9.2935
8321C | Above 8M Height up to 15M Height | 11.8996 | 12.8645 | 14.3962
8322 | Lighting Mast |  |  | -
8322A | Up to 30M Height |  |  | -
8322B | Above 30M Height |  |  | -
8323 | Lighting Fixture with Cabling Works |  |  | -
8323A | Fluorescent | 17.2191 | 18.6152 | 20.8317
8323B | Metal Halide | 21.0587 | 22.7662 | 25.477
8323C | Flood Light | 13.1462 | 14.2121 | 15.9043
8324 | Single Phase Convenience Outlet with Cabling Works | 15.9179 | 17.2085 | 19.2575
8330 | Street, Fence, Security |  |  | -
8331 | Lighting Pole |  |  | -
8331B | Above 3M Height up to 8M Height | 6.9158 | 7.4766 | 8.3668
8331C | Above 8M Height up to 15M Height | 11.9554 | 12.9248 | 14.4637
8332 | Lighting Mast |  |  | -
8332A | Up to 30M Height |  |  | -
8332B | Above 30M Height |  |  | -
8333 | Lighting Fixture | 9.0061 | 9.7363 | 10.8956
8336 | Cabling - max 35mm2 | 0.12766 | 0.13801 | 0.15444
8337 | Termination | 1.7761 | 1.9201 | 2.1488
8338 | Cable Way |  |  | -
8338A | Conduit Piping | 1.4365 | 1.5529 | 1.7378
8338B | Perforated Cable Tray - Galvanised Steel |  |  | -
8338C | Perforated Cable Tray - Stainless Steel |  |  | -
8340 | Aircraft Obstacle Light |  |  | -
8343 | Lighting Fixture |  |  | -
8344 | Control Panel |  |  | -
8346 | Cabling |  |  | -
8347 | Termination |  |  | -
8348 | Cable Way |  |  | -
8348A | Conduit Piping |  |  | -
8348B | Perforated Cable Tray - Galvanised Steel |  |  | -
8348C | Perforated Cable Tray - Stainless Steel |  |  | -
8350 | Navigation Light |  |  | -
8353 | Lighting Fixture |  |  | -
8354 | Control Panel |  |  | -
8356 | Cabling |  |  | -
8357 | Termination |  |  | -
8358 | Cable Way |  |  | -
8358A | Conduit Piping | 1.4362 | 1.5526 | 1.7375
8358B | Perforated Cable Tray - Galvanised Steel |  |  | -
8358C | Perforated Cable Tray - Stainless Steel |  |  | -
8390 | Other Work |  |  | -
8395 | Cable Trench |  |  | -
8395A | Excavation |  |  | -
8395Aa | Excavation of cable trench | 0.77244 | 0.83508 | 0.93451
8395Ab | Manual Excavation of buried coiled cables | 7.2999 | 7.8918 | 8.8315
8395B | Sand Filling | 0.93245 | 1.0081 | 1.1281
8395C | Back Filling | 0.93247 | 1.0081 | 1.1281
8395D | Polymeric Cable Protection CoverTile (to AS 4702) |  |  | -
8395E | Cable Warning Marker Sheet (to AS/NZS 2648.1) | 0.111 | 0.12 | 0.13429
8395F | Soil Disposal | 0.23312 | 0.25202 | 0.28203
8396 | Cable Route Marker | 1.1098 | 1.1998 | 1.3427
8400 | EARTHING |  |  | -
| Installation of equipment including:- |  |  | -
| All earthing material, including cable, is to be supplied by Subcontractor |  |  | -
| · Temporary storage as required; |  |  | -
| · Provision of all required construction materials and consumables; |  |  | -
| · Installation in accordance with supplied drawings and specifications; |  |  | -
8410 | Wiring of Earthing |  |  | -
8410A | Wiring of Underground Earthing (25sqmm, bare copper) |  |  | -
8410B | Wiring of Underground Earthing (70sqmm, bare copper) | 0.12487 | 0.13499 | 0.15107
8410C | Wiring of Underground Earthing (120sqmm, bare copper) | 0.13597 | 0.14699 | 0.16449
8410D | Underground Thermoweld Connection | 0.94351 | 1.02 | 1.1415
8410E | Stub-up PVC conduit | 0.77701 | 0.84001 | 0.94003
8410F | Wiring of Earthing (35 sqmm and less, PVC Yellow / Green) | 0.061049 | 0.065998 | 0.073857
8410G | Wiring of Earthing (70sqmm, PVC Yellow / Green) | 0.083251 | 0.090001 | 0.10072
8410H | Wiring of Earthing (120sqmm and above, PVC Yellow / Green) | 0.10546 | 0.11401 | 0.12758
8410I | Aboveground "C" type compression clamp | 0.56218 | 0.60777 | 0.68013
8410J | Earthing Bar | 2.9848 | 3.2268 | 3.611
8410K | Earthing Boss | 1.1211 | 1.212 | 1.3563
8420 | Earthing Electrode | 5.6059 | 6.0604 | 6.782
8430 | Connection to Equipment | 1.11 | 1.2 | 1.3429
8440 | Air Terminal | 5.2169 | 5.6399 | 6.3114
8441 | Downconductor | 0.3145 | 0.34 | 0.38049
8490 | Other Work |  |  | -
8493 | Inspection Pit | 4.0344 | 4.3615 | 4.8809
8495 | Boring Depth | 2.2202 | 2.4002 | 2.686
8600 | Communication System |  |  | -
| Installation of equipment including:- |  |  | -
| · Collection of material from Contractor’s warehouse, staging area or laydown/storage area; |  |  | -
| · Temporary storage as required; |  |  | -
| · Provision of all required construction materials and consumables; |  |  | -
| · Installation in accordance with supplied drawings and specifications; |  |  | -
8610 | Wired System |  |  | -
8611 | Public Address and General Alarm System |  |  | -
8611A | Amplifier Cabinet | 23.0886 | 24.9606 | 27.9327
8611B | Intercom station |  |  | -
8611Ba | Intercom station (indoor unit) | 3.1079 | 3.3599 | 3.76
8611Bb | Intercom station (outdoor unit hazardous area) | 12.5508 | 13.5684 | 15.184
8611Bc | Intercom station (outdoor unit non hazardous area) | 12.5516 | 13.5693 | 15.185
8611C | Speaker |  |  | -
8611Ca | Speaker (Indoor) | 5.5576 | 6.0083 | 6.7237
8611Cb | Speaker (Outdoor unit hazardous area) | 8.4808 | 9.1684 | 10.2601
8611Cc | Speaker (Outdoor unit non hazardous area) | 8.481 | 9.1686 | 10.2603
8611Cd | Speaker Support | 6.3641 | 6.8801 | 7.6993
8611E | Junction Box |  |  | -
8611Ea | Junction Box (Hazardous Area) | 5.6445 | 6.1021 | 6.8287
8611Eb | Junction Box (Non Hazardous Area) | 5.3671 | 5.8022 | 6.4931
8611F | Beacon |  |  | -
8611Fa | Beacon (Hazardous Area) | 9.4462 | 10.2121 | 11.428
8611Fb | Beacon (Non Hazardous Area) |  |  | -
8611Fb | Beacon Support | 1.9237 | 2.0797 | 2.3273
8612 | Telephone System |  |  | -
8612A | IP PABX | 17.7632 | 19.2035 | 21.49
8612B | Attendant Console | 6.6606 | 7.2006 | 8.058
8612C | Telephone Handset |  |  | -
8612Ca | IP Telephone handset | 1.1101 | 1.2001 | 1.343
8612Cb | Analogue Telephone Handset w/ acoustic hood (Hazardous Area) | 6.8818 | 7.4398 | 8.3257
8612Cc | Analogue Telephone Handset (Hazardous Area) |  |  | -
8612Cd | Telephone Support | 4.9732 | 5.3764 | 6.0165
8612D | MDF/IDF |  |  | -
8612Da | MDF | 17.7632 | 19.2035 | 21.49
8612Db | IDF | 13.3192 | 14.3991 | 16.1136
8612E | Cat 6 Patch Panel | 3.1079 | 3.3599 | 3.76
8612F | Analogue Telephone Adaptor | 6.8815 | 7.4395 | 8.3253
8612G | UPS with Integral Battery |  |  | -
8612Ga | UPS with Integral Battery - 3KVA | 214.2495 | 231.6211 | 259.2
8612Gb | UPS with Integral Battery - 5KVA | 214.2495 | 231.6211 | 259.2
8612H | Single AC UPS | 35.7455 | 38.6437 | 43.245
8612I | Battery Rack | 176.0574 | 190.3323 | 212.995
8620 | Wireless System |  |  | -
8621 | Microwave System |  |  | -
8621A | Central Cabinet | 23.0905 | 24.9627 | 27.935
8621B | Outdoor Equipment |  |  | -
8621Ba | 65m Structure | 22.2019 | 24.0021 | 26.86
8621Bb | 30m Structure | 19.9784 | 21.5983 | 24.17
8621Bc | 10m Structure | 18.5299 | 20.0323 | 22.4175
8621C | Operation Console |  |  | -
8622 | UHF TETRA Radio |  |  | -
8622A | Central Cabinet | 23.0897 | 24.9618 | 27.934
8622B | Outdoor Equipment | 18.5307 | 20.0332 | 22.4186
8622C | TETRA Radio Console, Network Management Terminal and Set-up PC | 17.7616 | 19.2017 | 21.488
8622D | TETRA Desk Mounted Radio | 2.2235 | 2.4038 | 2.69
8622E | UHF Active Repeater for Indoor Coverage | 7.8828 | 8.522 | 9.5367
8622F | UHF Active Repeater for Outdoor Coverage | 15.2448 | 16.4808 | 18.4432
8622G | UHF Passive Repeater for Indoor Coverage | 7.8817 | 8.5207 | 9.5353
8623 | Satellite Phone System | 5.7695 | 6.2373 | 6.98
8624 | VHF and HF Radio |  |  | -
8624A | Central Cabinet | 22.2019 | 24.0021 | 26.86
8624B | Antenna System |  |  | -
8624Ba | VHF Antenna | 38.5567 | 41.6829 | 46.646
8624Bb | HF Antenna | 38.5558 | 41.682 | 46.645
8625 | Antenna Support Structure |  |  | -
8625A | Support Structure 65m | 3272.3145 | 3537.6373 | 3958.86
8625B | Support Structure 30m |  |  | -
8625C | Support Structure 10m | 794.8641 | 859.3126 | 961.63
8630 | LAN/WAN and Data Communication System |  |  | -
8631 | LAN/WAN |  |  | -
8631A | Central Cabinet | 23.0905 | 24.9627 | 27.935
8631B | Local Cabinet | 18.6488 | 20.1608 | 22.5614
8631C | Cat 6 Patch Panel | 3.1082 | 3.3602 | 3.7603
8631D | Central Console | 43.0731 | 46.5655 | 52.11
8631E | Access Swtich | 3.1079 | 3.3599 | 3.76
8631F | FO Media Converter with Chassis | 3.1079 | 3.3599 | 3.76
8632 | Mobile Data System |  |  | -
8632A | Central Cabinet | 23.0905 | 24.9627 | 27.935
8632B | Local Cabinet |  |  | -
8632C | Central Console | 43.0731 | 46.5655 | 52.11
8632D | Wi-Fi Access Point |  |  | -
8632Da | Wi-Fi Access Point (Indoor) | 1.332 | 1.44 | 1.6115
8632Db | Wi-Fi Access Point Outdoor (Weatherproof) | 13.8573 | 14.9809 | 16.7646
8632Dc | Wi-Fi Access Point Outdoor (Hazardous Area) | 19.3189 | 20.8853 | 23.3721
8640 | Other Communication System |  |  | -
8641 | CCTV System |  |  | -
8641A | Central Cabinet | 23.0897 | 24.9618 | 27.934
8641B | Local Cabinet | 18.6476 | 20.1596 | 22.56
8641C | Desk Top Type Operation Console | 6.4381 | 6.9602 | 7.7889
8641D | Monitor | 4.5436 | 4.9121 | 5.4969
8641E | Camera |  |  | -
8641Ea | CCTV Indoor Dome type Camera | 5.8425 | 6.3163 | 7.0683
8641Eb | CCTV Weatherproof Dome Type Camera | 12.1256 | 13.1087 | 14.6696
8641Ec | CCTV Weatherproof Dual Head Camera | 12.1255 | 13.1086 | 14.6694
8641Ed | CCTV Hazardous Area Camera - Pole Mounted | 16.5659 | 17.9091 | 20.0415
8641Ee | CCTV Hazardous Area Camera - Platform (Stick Built) | 16.5634 | 17.9064 | 20.0385
8641Ef | CCTV Hazardous Area Camera - Platform (MFY Installed) | 12.1234 | 13.1063 | 14.6669
8641F | Video Encoder | 6.4382 | 6.9603 | 7.789
8642 | Source Transfer Switch |  |  | -
8642A | Source Transfer Switch (Installation into Cabinet) | 2.2201 | 2.4001 | 2.6859
8642B | Power Wiring for Source Transfer Switch (Inside Cabinet) | 5.3278 | 5.7597 | 6.4456
8643 | Security System - RADAR |  |  | -
8643A | Central Cabinet |  |  | -
8643C | Monitor/Display/Control Unit | 4.5421 | 4.9103 | 5.495
8643D | RADAR Antenna and Rotating Equipment |  |  | -
8643F | Long Range CCTV Camera |  |  | -
8644 | Security System - Long Range Acoustic Device (LRAD) |  |  | -
8644A | Central Cabinet |  |  | -
8644B | LRAD Device | 28.6369 | 30.9588 | 34.645
8644C | LRAD Control Console | 43.0731 | 46.5655 | 52.11
8645 | Security System - Fence Intrusion Detection System (FIDS) |  |  | -
8645A | Central Cabinet | 23.0905 | 24.9627 | 27.935
8645B | Local Cabinet | 18.6476 | 20.1596 | 22.56
8645C | Fibre Optic Sensor Cable | 0.11656 | 0.12601 | 0.14101
8645D | Gate Isolation Unit | 21.6733 | 23.4306 | 26.2205
8645E | Operator Console | 19.7594 | 21.3615 | 23.905
8646 | Security System - Access Control System |  |  | -
8646A | Central Cabinet | 23.0905 | 24.9627 | 27.935
8646B | Local Cabinet | 18.6495 | 20.1616 | 22.5622
8646C | Badge Production PC with Camera | 2.2194 | 2.3993 | 2.685
8646D | Monitoring PC | 2.2194 | 2.3993 | 2.685
8646E | Manual Controller Remote Control Push Button | 9.2803 | 10.0328 | 11.2274
8646F | Biometric Reader Indoor Non-Hazardous Area | 2.6643 | 2.8804 | 3.2233
8646G | Security Gate |  |  | -
8646Ga | Double Sliding Gate (6 m opening) | 61.9935 | 67.02 | 75
8646Gb | Double Sliding Gate (9 m opening) | 73.0945 | 79.021 | 88.43
8646Gc | Outdoor Turnstile Gate | 56.4436 | 61.0201 | 68.2857
8646Gd | Rising Arm Gate | 50.8925 | 55.019 | 61.57
8646Ge | Fence Gate Access Control Equipment | 24.7623 | 26.77 | 29.9575
8646Gf | Crash Barrier (Main Gate) | 61.9935 | 67.02 | 75
8646Gg | Automatic Swing Gate | 61.9935 | 67.02 | 75
8647 | Security System - Intercom System |  |  | -
8647A | Central Cabinet | 23.0864 | 24.9582 | 27.93
8647B | Intercom Station | 3.1079 | 3.3599 | 3.76
8647C | Outdoor Intercom Station | 10.3305 | 11.1681 | 12.4979
8648 | Personnel Locator System (PLS) and E-Mustering System |  |  | -
8648A | Central Cabinet | 23.0905 | 24.9627 | 27.935
8648B | PLS Wi-Fi Access Point |  |  | -
8648Ba | PLS Wi-Fi Access Point (Hazardous Area) | 2.2201 | 2.4001 | 2.6859
8648Bb | PLS Wi-Fi Access Point (Non Hazardous Area) |  |  | -
8648C | Exciter and Location Receiver | 3.3301 | 3.6001 | 4.0288
8648D | Muster Point Equipment | 3.3302 | 3.6002 | 4.0289
8649 | Hotline System |  |  | -
8649A | Central Cabinet | 23.0905 | 24.9627 | 27.935
8649B | Fibre Optic Patch Panel | 2.22 | 2.4 | 2.6857
8649C | Media Converter | 4.4399 | 4.7999 | 5.3714
8649D | Master Station | 3.3295 | 3.5994 | 4.028
8649E | Hotline Terminal | 2.2207 | 2.4008 | 2.6867
8650 | Nurse Call /Distress System |  |  | -
8650A | Central Cabinet | 23.0864 | 24.9582 | 27.93
8650B | PC with Management and Call Logger |  |  | -
8650C | Address Console |  |  | -
8650D | Corridor Distress Light | 7.0673 | 7.6403 | 8.55
8650E | Call Unit | 14.5147 | 15.6916 | 17.56
8651 | Ship to Shore Link (SSL) |  |  | -
8651A | Central Cabinet | 23.0864 | 24.9582 | 27.93
8651B | Fibre Optic Cable Reel | 11.9854 | 12.9572 | 14.5
8651C | Electrical Cable Reel | 11.9882 | 12.9602 | 14.5033
8651D | Hotline Terminal | 2.2194 | 2.3993 | 2.685
8652 | Radio Emergency Shut Down (ESD) System |  |  | -
8652A | Radio SSL Fixed Station | 18.6476 | 20.1596 | 22.56
8652B | Radio SSL Antenna | 18.5319 | 20.0345 | 22.42
8652C | Radio SSL Remote Station |  |  | -
8653 | Video conferencing System |  |  | -
8653A | Large Terminal | 17.7604 | 19.2005 | 21.4867
8653B | Medium Terminal | 11.101 | 12.001 | 13.43
8653C | Small Terminal | 5.5505 | 6.0005 | 6.715
8653D | Personal System |  |  | -
8654 | Telecoms Network Management System |  |  | -
8654A | Central Cabinet | 22.2019 | 24.0021 | 26.86
8654B | Network Time Server | 8.8816 | 9.6017 | 10.745
8654C | PC with Alarm Monitoring | 4.4387 | 4.7986 | 5.37
8654D | RTU | 11.101 | 12.001 | 13.43
8660 | Cabling |  |  | -
8661 | Cable |  |  | -
8661A | Power Cable |  |  | -
8661Aa | 0.6/1kV _ Below 10sqmm | 0.11833 | 0.12792 | 0.14315
8661Ab | 0.6/1kV _ 10sqmm to below 50sqmm | 0.17428 | 0.18841 | 0.21084
8661B | Control Cable |  |  | -
8661Ba | Control _ less than 8C | 0.12943 | 0.13993 | 0.15659
8661Bb | Control _ 8C to less than 12C |  |  | -
8661Bc | Control _ 12C and more | 0.19585 | 0.21173 | 0.23694
8661C | Fiber Optic Cable |  |  | -
8661Ca | 12 Fibre Cable | 0.14053 | 0.15192 | 0.17001
8661Cb | 24 Fibre Cable | 0.18474 | 0.19972 | 0.2235
8661Cc | 48 Fibre Cable | 0.21802 | 0.2357 | 0.26376
8661Cd | 6 Fibre Cable | 0.11833 | 0.12793 | 0.14316
8661D | Copper Twisted Pair Cable |  |  | -
8661Da | CAT 3 Indoor |  |  | -
8661Db | CAT 6A indoor | 0.18871 | 0.20402 | 0.22831
8661Dc | CAT 3 Outdoor | 0.18472 | 0.1997 | 0.22347
8661E | Coaxial Cable |  |  | -
8661Ea | Low Density Foam Corrugated Copper with OD < or = 13 mm |  |  | -
8661Eb | Low Density Foam Corrugated Copper with OD > 13 mm | 0.18872 | 0.20402 | 0.22832
8661Ec | Shielded Cable with a OD < or = 10.5 mm |  |  | -
8661Ed | Shielded Cable with a OD > 10.5 mm |  |  | -
8661F | Fibre Optic Patch Cord |  |  | -
8661Fa | Fibre Optic Patch Cord - within single cabinet | 0.49948 | 0.53998 | 0.60427
8661Fb | Fibre Optic Patch Cord - between adjacent cabinets | 0.77699 | 0.83998 | 0.94
8661G | CAT 6A Patch Cabling |  |  | -
8661Ga | CAT 6A Patch Cabling - within single cabinet | 0.49943 | 0.53992 | 0.60421
8661Gb | CAT 6A Cabling - between adjacent cabinets | 0.77699 | 0.83998 | 0.94
8670 | Termination/Splicing of Cable |  |  | -
8671 | Termination - including Compound Filled Gland |  |  | -
8671A | Power Cable |  |  | -
8671Aa | 0.6/1kV - Below 10sqmm | 1.4986 | 1.6201 | 1.813
8671Ab | 0.6/1kV - 10sqmm to below 50sqmm | 2.6087 | 2.8202 | 3.156
8671B | Control Cable |  |  | -
8671Ba | Control - less than 8C | 2.0537 | 2.2202 | 2.4845
8671Bb | Control - 8C to less than 12C |  |  | -
8671Bc | Control - 12C and more | 4.5509 | 4.9199 | 5.5057
8671C | Fiber Optic Cable |  |  | -
8671Ca | 12 Fibre Cable | 7.9914 | 8.6393 | 9.668
8671Cb | 24 Fibre Cable |  |  | -
8671Cc | 48 Fibre Cable | 31.9655 | 34.5573 | 38.672
8671Cd | 6 Fibre Cable | 3.9963 | 4.3203 | 4.8347
8671D | Copper Twisted Pair Cable |  |  | -
8671Da | CAT 3 Indoor |  |  | -
8671Db | CAT 6A indoor | 1.2206 | 1.3195 | 1.4767
8671Dc | CAT 3 Outdoor | 1.2209 | 1.3199 | 1.477
8671E | Coaxial Cable |  |  | -
8671Ea | Low Density Foam Corrugated Copper with OD < or = 13 mm |  |  | -
8671Eb | Low Density Foam Corrugated Copper with OD > 13 mm | 1.2211 | 1.3201 | 1.4773
8671Ec | Shielded Cable with a OD < or = 10.5 mm |  |  | -
8671Ed | Shielded Cable with a OD > 10.5 mm |  |  | -
8672 | Termination - including Non Compound Filled Gland |  |  | -
8672A | Power Cable |  |  | -
8672Aa | 0.6/1kV _ Below 10sqmm | 1.2211 | 1.3201 | 1.4772
8672Ab | 0.6/1kV _ 10sqmm to below 50sqmm | 2.3312 | 2.5202 | 2.8203
8672B | Control Cable |  |  | -
8672Ba | Control _ less than 8C | 1.4986 | 1.6201 | 1.813
8672Bb | Control _ 8C to less than 12C |  |  | -
8672Bc | Control _ 12C and more | 3.9963 | 4.3203 | 4.8347
8672C | Fiber Optic Cable |  |  | -
8672Ca | 12 Fibre Cable | 7.9922 | 8.6402 | 9.669
8672Cb | 24 Fibre Cable | 15.9861 | 17.2822 | 19.34
8672Cc | 48 Fibre Cable | 31.9655 | 34.5573 | 38.672
8672Cd | 6 Fibre Cable | 3.9963 | 4.3203 | 4.8347
8672D | Copper Twisted Pair Cable |  |  | -
8672Da | CAT 3 Indoor |  |  | -
8672Db | CAT 6A indoor | 1.2211 | 1.3201 | 1.4773
8672Dc | CAT 3 Outdoor | 1.221 | 1.32 | 1.4771
8672E | Coaxial Cable |  |  | -
8672Ea | Low Density Foam Corrugated Copper with OD < or = 13 mm |  |  | -
8672Eb | Low Density Foam Corrugated Copper with OD > 13 mm | 1.2211 | 1.3201 | 1.4773
8672Ec | Shielded Cable with a OD < or = 10.5 mm |  |  | -
8672Ed | Shielded Cable with a OD > 10.5 mm |  |  | -
8673 | Splicing of Fibre Optic Cable |  |  | -
8673A | Fiber Optic Cable |  |  | -
8673Aa | 12 Fibre Cable |  |  | -
8673Ab | 24 Fibre Cable | 31.9704 | 34.5626 | 38.6779
8673Ac | 48 Fibre Cable |  |  | -
8673Ad | 6 Fibre Cable |  |  | -
8674 | FO Cabinet With Distribution Trays | 11.101 | 12.001 | 13.43
8675 | Yellow Cable Duct for FO Cabling | 2.2201 | 2.4002 | 2.6859
8680 | Cable Way |  |  | -
8681 | Cable Ladder or Tray and Cover |  |  | -
8681A | Perforated Cable Tray 150mm Width | 1.7738 | 1.9176 | 2.1459
8681B | Cable Ladder 300mm Width | 2.0675 | 2.2352 | 2.5013
8681C | Cable Ladder 600mm Width |  |  | -
8681D | Cable Ladder 900mm Width |  |  | -
8681E | Perforated Cable Tray Cover 150mm Width |  |  | -
8681F | Cable Ladder Cover 300mm Width | 0.58834 | 0.63604 | 0.71177
8681G | Cable Ladder Cover 600mm Width |  |  | -
8681H | Cable Ladder Cover 900mm Width |  |  | -
8682 | Conduit Piping for Conduit Wiring System |  |  | -
8682A | Rigid Metal Conduit | 1.3266 | 1.4341 | 1.6049
8682B | Rigid PVC Conduit | 0.9101 | 0.98389 | 1.101
8683 | Stub-up PVC conduit |  |  | -
8683A | 100 - 150mm dia 1500-2000mm radius bend |  |  | -
8683B | 100 - 150mm dia 1000-1500mm radius bend | 1.0543 | 1.1397 | 1.2755
8683C | 100 - 150mm dia 500-1000mm radius bend |  |  | -
8683D | 100 - 150mm dia up to 500mm radius bend |  |  | -
8683E | less than 100mm dia 500-1500mm radius bend |  |  | -
8683F | less than 100mm dia up to 500mm radius bend |  |  | -
8683G | 100-150mm dia straight stub up | 0.77699 | 0.83998 | 0.94
8683H | less than 100mm dia straight stub up | 0.77699 | 0.83998 | 0.94
8684 | Removal and Reinstallation of MF Installed Ladder Cover |  |  | -
8684A | Cable Ladder Cover 300mm Width |  |  | -
8684B | Cable Ladder Cover 600mm Width |  |  | -
8684C | Cable Ladder Cover 900mm Width |  |  | -
8690 | Other Work |  |  | -
8695 | Cable Trench |  |  | -
8695A | Excavation of Cable Trench | 0.77247 | 0.8351 | 0.93454
8695B | Manual Excavation of buried coiled cables | 7.2999 | 7.8918 | 8.8314
8695C | Sand Filling | 0.93246 | 1.0081 | 1.1281
8695D | FTB (instead of sand filling) |  |  | -
8695E | Back Filling | 0.93244 | 1.008 | 1.1281
8695F | Polymeric Cable Protection CoverTile (to AS 4702) |  |  | -
8695G | Cable Warning Marker Sheet (to AS/NZS 2648.1) | 0.11095 | 0.11994 | 0.13423
8695H | Soil Disposal | 0.23313 | 0.25203 | 0.28204
8696 | Cable Route Marker | 1.1099 | 1.1999 | 1.3428
8697 | Pole and Mast |  |  | -
8697A | Pole (up to 5M) | 7.3654 | 7.9626 | 8.9107
8697B | Pole (up to 8M) | 12.0515 | 13.0287 | 14.58
8697C | Pole (up to 15M) | 16.4903 | 17.8273 | 19.95
8697D | Mast (above 15M) |  |  | -
8700 | Cathodic Protection |  |  | -
| Installation of equipment including:- |  |  | -
| · Collection of material from Contractor’s warehouse, staging area or laydown/storage area; |  |  | -
| · Temporary storage as required; |  |  | -
| · Provision of all required construction materials and consumables; |  |  | -
| · Installation in accordance with supplied drawings and specifications; |  |  | -
8710 | Impressed current cathodic protection |  |  | -
8711 | Transformer-Rectifier | 30.5536 | 33.0309 | 36.9638
8712 | Test Box and Bond Box | 6.9411 | 7.5039 | 8.3974
8713 | Anode |  |  | -
8713A | Rod Type | 3.4882 | 3.771 | 4.22
8713B | Ribbon/Line Type |  |  | -
8714 | Reference Electrode |  |  | -
8716 | Cabling - Low Voltage | 0.17202 | 0.18596 | 0.20811
8717 | Splicing and Connection |  |  | -
8717A | U/G Splicing |  |  | -
8717B | Connection to Piping/Equipment | 2.3312 | 2.5202 | 2.8203
8719 | Boring | 3.3303 | 3.6003 | 4.029
8720 | Sacrificial Anode System |  |  | -
8722 | Test Box and Bond Box | 6.9414 | 7.5042 | 8.3978
8723 | Anode | 3.4898 | 3.7727 | 4.222
8724 | Reference Electrode | 3.4893 | 3.7723 | 4.2214
8726 | Cabling - Low Voltage | 0.17206 | 0.18601 | 0.20816
8727 | Splicing and Connection |  |  | -
8727A | U/G Splicing |  |  | -
8727B | Connection to Piping/Equipment | 2.331 | 2.52 | 2.82
8790 | Other Works |  |  | -
8793 | Soil Access Box |  |  | -
8795 | Cable Trench |  |  | -
8795Aa | Excavatiom |  |  | -
8795Ab | Manual Excavation of buried coiled cables |  |  | -
8795B | Sand Filling |  |  | -
8795C | Back Filling |  |  | -
8795D | Cable Protection Tile (to AS 4702) |  |  | -
8795E | Cable Warning Marker Sheet (to AS/NZS 2648.1) |  |  | -
8796 | Cable Route Marker |  |  | -
8800 | ELECTRICAL HEAT TRACING |  |  | -
| Installation of equipment including:- |  |  | -
| · Collection of material from Contractor’s warehouse, staging area or laydown/storage area; |  |  | -
| · Temporary storage as required; |  |  | -
| · Provision of all required construction materials and consumables; |  |  | -
| · Installation in accordance with supplied drawings and specifications; |  |  | -
8810 | Heater Panel |  |  | -
8820 | Heating Element |  |  | -
8821 | Self Regulating Type | 0.19646 | 0.21239 | 0.23768
8860 | Cabling - Low Voltage | 0.22186 | 0.23985 | 0.26841
8870 | Termination of Cable | 1.4984 | 1.6199 | 1.8127
8900 | PRECOMMISSIONING CHECKS AND FUNCTION TESTING |  |  | -
8910 | Precommissioning Checks |  |  | -
8910AAa | XP01 Hazardous Area | 4.4399 | 4.7999 | 5.3714
8910AAb | XP03 Hazardous Area | 4.4397 | 4.7996 | 5.3711
8910AB | EP01 LV (OPERATIONAL VOLTAGE <1.0 KV) CABLE | 1.11 | 1.2 | 1.3429
8910AC | EP02 LV (OPERATIONAL VOLTAGE <1.0 KV) MOTOR | 2.2201 | 2.4001 | 2.6858
8910ADm | EP03 CONTROL PANEL / CONSOLE | 6.6596 | 7.1996 | 8.0569
8910ADs | EP03 CONTROL PANEL / CONSOLE | 6.6602 | 7.2002 | 8.0575
8910AEm | EP04 CHARGER / INVERTER | 6.6599 | 7.1998 | 8.0571
8910AEs | EP04 CHARGER / INVERTER | 6.6607 | 7.2008 | 8.0582
8910AF | EP05 LIGHT FITTING | 1.11 | 1.2 | 1.3429
8910AG | EP06 SOCKET OUTLET | 1.11 | 1.2 | 1.3429
8910AH | EP07 JUNCTION BOX | 1.11 | 1.2 | 1.3429
8910AI | EP08 EARTHING SYSTEMS | 0.55505 | 0.60006 | 0.67151
8910AJ | EP09 CONTROL STATION | 1.11 | 1.2 | 1.3429
8910AK | EP10 CABLE TRAY AND LADDER | 0.55504 | 0.60004 | 0.67149
8910ALm | EP11 DISTRIBUTION BOARD | 4.4401 | 4.8002 | 5.3717
8910ALs | EP11 DISTRIBUTION BOARD | 4.4403 | 4.8003 | 5.3719
8910AMm | EP12 LV (OPERATIONAL VOLTAGE <1.0 KV) SWITCHGEAR | 6.6603 | 7.2003 | 8.0577
8910AMs | EP12 LV (OPERATIONAL VOLTAGE <1.0 KV) SWITCHGEAR |  |  | -
8910ANm | EP13 HV (OPERATIONAL VOLTAGE ≥1.0 KV) SWITCHGEAR | 6.6595 | 7.1995 | 8.0567
8910ANs | EP13 HV (OPERATIONAL VOLTAGE ≥1.0 KV) SWITCHGEAR |  |  | -
8910AO | EP14 MISCELLANEOUS EQUIPMENT | 2.22 | 2.4 | 2.6857
8910AP | EP15 INSTALLATION ON SKID | 6.6602 | 7.2002 | 8.0575
8910AQ | EP16 EARTH BOSS ON SKID / MODULE | 0.555 | 0.6 | 0.67145
8910AR | EP17 COILED CABLE |  |  | -
8910AS | EP18 GENERATOR | 6.6609 | 7.2009 | 8.0583
8910AT | EP19 POWER TRANSFORMER | 6.6598 | 7.1998 | 8.0571
8910AUm | EP20 HV (OPERATIONAL VOLTAGE ≥1.0 KV) SWITCHBOARD / MFY | 6.66 | 7.2 | 8.0573
8910AUs | EP20 HV (OPERATIONAL VOLTAGE ≥1.0 KV) SWITCHBOARD |  |  | -
8910AVm | EP21 LV (OPERATIONAL VOLTAGE <1.0 KV) SWITCHBOARD / MFY | 6.6597 | 7.1996 | 8.0569
8910AVs | EP21 LV (OPERATIONAL VOLTAGE <1.0 KV) SWITCHBOARD | 6.6622 | 7.2024 | 8.06
8910AW | EP22 HV (OPERATIONAL VOLTAGE ≥1.0 KV) BUS DUCT | 2.2201 | 2.4001 | 2.6859
8910AX | EP23 LV (OPERATIONAL VOLTAGE <1.0 KV) BUS DUCT | 2.2198 | 2.3998 | 2.6855
8910AY | EP24 HV (OPERATIONAL VOLTAGE ≥1.0 KV) CABLE | 2.22 | 2.4 | 2.6857
8910AZ | EP25 HV (OPERATIONAL VOLTAGE ≥1.0 KV) MOTOR | 2.22 | 2.4 | 2.6857
8910BA | EP26 BATTERY | 4.44 | 4.8 | 5.3716
8910BB | EP27 ELECTRIC HEATER | 1.1099 | 1.1999 | 1.3428
8910BC | EP28 NEUTRAL EARTHING RESISTOR | 1.1101 | 1.2002 | 1.3431
8910BD | EP29 EARTH BAR | 1.11 | 1.2 | 1.3429
8910BE | EP30 EARTH ROD | 1.1101 | 1.2001 | 1.343
8910BF | EP31 METERING TRANSFORMER | 1.11 | 1.2 | 1.3429
8910BG | EP32 AUXILIARY TRANSFORMER | 1.11 | 1.2 | 1.3429
8910BH | EP33 Heat Tracing (Pre-insulation) | 2.22 | 2.4 | 2.6857
8910CB | EP34 Heat Tracing (Post-insulation) | 2.2198 | 2.3998 | 2.6855
8910CC | EP35 Cathodic Protection | 1.1102 | 1.2003 | 1.3432
8910CD | EP36 Lightning Protection | 1.1099 | 1.1999 | 1.3428
8910BI | TP01 TELECOMMUNICATIONS PA/GA LOUDSPEAKER | 1.1101 | 1.2001 | 1.343
8910BJ | TP02 TELECOMMUNICATIONS BEACON | 1.11 | 1.2 | 1.3429
8910BK | TP03 TELECOMMUNICATIONS ACCESS CONTROL EQUIPMENT | 4.4404 | 4.8005 | 5.372
8910BL | TP04 TELECOMMUNICATIONS NETWORK EQUIPMENT | 6.66 | 7.2 | 8.0573
8910BM | TP05 TELECOMMUNICATIONS TELEPHONE UNIT | 1.11 | 1.2001 | 1.3429
8910BN | TP06 TELECOMMUNICATIONS TELECOMS CABINET | 6.6604 | 7.2004 | 8.0578
8910BO | TP07 TELECOMMUNICATIONS RADIO EQUIPMENT | 6.6607 | 7.2008 | 8.0582
8910BP | TP08 TELECOMMUNICATIONS METEOROLOGICAL SENSOR |  |  | -
8910BQ | TP09 TELECOMMUNICATIONS CONTROLLER UNITS | 2.2201 | 2.4001 | 2.6859
8910BR | TP10 TELECOMMUNICATIONS WORKSTATION / CONSOLES | 4.4402 | 4.8002 | 5.3717
8910BS | TP11 TELECOMMUNICATIONS MISCELLANEOUS EQUIPMENT | 4.4402 | 4.8003 | 5.3718
8910BT | TP12 TELECOMMUNICATIONS FOBOT / PATCH PANEL | 2.2201 | 2.4001 | 2.6859
8910BU | TP13 TELECOMMUNICATIONS CCTV CAMERA | 1.1101 | 1.2001 | 1.3429
8910BV | TP14 TELECOMMUNICATIONS JUNCTION BOX | 1.1101 | 1.2001 | 1.3429
8910BW | TP15 TELECOMMUNICATIONS TELECOMS CABLE | 1.1101 | 1.2001 | 1.343
8910BX | TP16 TELECOMMUNICATIONS CAT 6A CABLE | 1.1101 | 1.2001 | 1.343
8910BY | TP17 TELECOMMUNICATIONS FIBRE OPTIC CABLE | 1.1101 | 1.2001 | 1.343
8910BZ | TP18 TELECOMMUNICATIONS ANTENNA / DISH | 2.2204 | 2.4004 | 2.6862
8910CA | TP19 TELECOMMUNICATIONS COAXIAL CABLE | 1.1101 | 1.2001 | 1.343
8920 | Function Testing |  |  | -
| NOTE: Sample forms issued with the ITT are numbered ‘ETXX’. |  |  | -
8920AA | EC01 LIGHTING CIRCUIT | 2.22 | 2.3999 | 2.6857
8920AB | EC02 SWITCHGEAR AND CUBICLE | 4.4399 | 4.7999 | 5.3715
8920AC | EC03 HEATER | 2.22 | 2.4 | 2.6858
8920AD | EC04 MOTOR CONTROL CENTER (MCC) / STARTER | 4.4398 | 4.7998 | 5.3713
8920AE | EC05 CONTROL PANEL | 4.4398 | 4.7998 | 5.3713
8920AF | EC06 BATTERY CHARGER | 2.22 | 2.4 | 2.6857
8920AG | EC07 BATTERY | 4.44 | 4.8 | 5.3716
8920AH | EC09 GENERATOR, LOW VOLTAGE (LV) (not used) |  |  | -
8920AI | EC08 GENERATOR, HIGH VOLTAGE (HV) (not used) | 11.101 | 12.001 | 13.43
8920AJ | EC10 POWER TRANSFORMER | 4.4398 | 4.7998 | 5.3713
8920AK | EC11 MOTOR | 2.2199 | 2.3999 | 2.6856
8920AL | EC12 MOTOR RUN TEST, NO LOAD | 2.2199 | 2.3999 | 2.6856
8920AM | EC13 MOTOR LOAD RUN TEST, ONE (1) HOUR (not used) |  |  | -
8920AN | EC14 MOTOR LOAD RUN TEST, FOUR (4) HOUR (not used) |  |  | -
8920AO | EC15 SWITCHBOARD | 2.2199 | 2.3999 | 2.6857
8920AP | EC16 DISTRIBUTION BOARD | 2.2199 | 2.3999 | 2.6856
8920AQ | EC17 CURRENT TRANSFORMER (CT) | 1.11 | 1.2 | 1.3429
8920AR | EC18 METERING TRANSFORMER, HIGH VOLTAGE (HV) | 1.11 | 1.2 | 1.3429
8920AS | EC19 METERING TRANSFORMER, LOW VOLTAGE (LV) | 1.11 | 1.2 | 1.3428
8920ATa | EC20 PROTECTION RELAY (not used) | 4.4399 | 4.7999 | 5.3714
8920ATb | EC41 PROTECTION RELAY（REF630) | 4.44 | 4.8 | 5.3716
8920ATc | EC42 PROTECTION RELAY（UNDERVOLTAGE） (not used) |  |  | -
8920ATd | EC43 PROTECTION RELAY（PR122） | 4.4402 | 4.8002 | 5.3718
8920ATe | EC44 PROTECTION RELAY（REF610） | 4.4401 | 4.8001 | 5.3717
8920ATf | EC45 PROTECTION RELAY（REF615） | 4.4399 | 4.7999 | 5.3714
8920ATg | EC46 PROTECTION RELAY（REM615） | 4.4398 | 4.7998 | 5.3713
8920ATh | EC47 PROTECTION RELAY（REM630） | 4.4398 | 4.7998 | 5.3713
8920ATi | EC48 PROTECTION RELAY（SIPROTEC 7SD6101） | 4.4402 | 4.8002 | 5.3717
8920ATj | EC49 PROTECTION RELAY（RIO600） | 4.44 | 4.8 | 5.3716
8920ATk | EC50 PROTECTION RELAY（SIPROTEC 7SJ63） (not used) | 4.4403 | 4.8004 | 5.372
8920ATl | EC51 PROTECTION RELAY（SIPROTEC 7SJ64） (not used) | 4.4404 | 4.8004 | 5.372
8920ATm | EC52 PROTECTION RELAY（SIPROTEC 7UT61） (not used) | 4.4408 | 4.8009 | 5.3725
8920ATn | EC53 PROTECTION RELAY（SIPROTEC 7SS5251） (not used) | 4.4404 | 4.8004 | 5.372
8920ATo | EC54 PROTECTION RELAY（SIPROTEC 7SS5220） (not used) | 4.4387 | 4.7986 | 5.37
8920AU | EC21 UNINTERRUPTIBLE POWER SUPPLY (UPS) SYSTEM | 4.4401 | 4.8001 | 5.3717
8920AV | EC22 INSTALLATION ON SKID (not used) | 4.4408 | 4.8009 | 5.3725
8920AW | EC23 SOCKET OUTLET CIRCUIT | 2.2199 | 2.3999 | 2.6856
8920AX | EC24 PANEL INSTRUMENT | 4.44 | 4.8 | 5.3715
8920AY | EC25 HEAT TRACING CIRCUIT | 2.2198 | 2.3998 | 2.6856
8920AZa | EC26 VARIABLE SPEED DRIVE (VSD), LOW VOLTAGE (LV) | 4.4398 | 4.7997 | 5.3712
8920AZb | EC35 VARIABLE SPEED DRIVE (VSD), HIGH VOLTAGE HV) | 4.4401 | 4.8001 | 5.3717
8920BA | ETXX Earth Loop Impedance Test | 2.2201 | 2.4001 | 2.6859
8920BBa | EC34 PDCS COMMUNICATION & I/O TEST (Hard Wire and Modbus) | 0.55498 | 0.59998 | 0.67142
8920BBb | EC38 PDCS COMMUNICATION & I/O TEST(IEC61850) | 0.555 | 0.6 | 0.67144
8920BBc | EC33 PDCS FUNCTION TEST | 2.2201 | 2.4001 | 2.6859
8920BC | EC27 HEATER CONTROL PANEL | 2.2207 | 2.4008 | 2.6867
8920BD | EC29 POWER TRANSFORMER DIFFERENTIAL PROTECTION | 2.2199 | 2.3999 | 2.6856
8920BE | EC31 LINE DIFFERENTIAL PROTECTION TEST | 2.2201 | 2.4001 | 2.6859
8920BF | EC32 INTERFACE TEST BETWEEN SWITCHGEAR | 2.2198 | 2.3998 | 2.6856
8920BG | EC37 CATHODIC PROTECTION | 2.2202 | 2.4002 | 2.686
7110 | Panel, Rack and Cabinet |  |  | -
7111 | Floor Mount Type Panels, Rack and Cabinet including |  |  | -
| Marshalling, System, Network, Server and PLC cabinets |  |  | -
7111A | - 2.0m W x 1.0m D x 2.1m H (approx) |  |  | -
7111B | - 1.0m W x 0.8m D x 2.1m H (approx) | 31.5265 | 34.0827 | 38.1408
7111C | - 0.8m W x 0.8m D x 2.1m H (approx) | 31.5264 | 34.0826 | 38.1408
7111D | - 0.8m W x 0.5m D x 2.1m H (approx) ( PDP ) | 31.5266 | 34.0828 | 38.141
7112 | Wall Mount Type |  |  | -
7112A | - 1.0m W x 0.4m D x 1.0m H (approx) |  |  | -
7112B | - 0.6m W x 0.4m D x 0.8m H (approx) (FAP, HSSD) |  |  | -
7112C | - 0.6m W x 0.4m D x 1.8m H (approx) |  |  | -
7120 | Control Systems / Computer System |  |  | -
7121 | Operator Station |  |  | -
7121A | - Console Type ( Typ. 1,65m W x 1.4m D x 0.75m H ) (OPC) | 43.0715 | 46.5637 | 52.108
7121B | - Desk mount type | 15.5412 | 16.8013 | 18.8018
7121C | - Cabinet Type ( 0.8m W x 0.8m D x 2.1m H ) (OPC) |  |  | -
7121D | - Console Type ( Typ. 0.55m W x 1.15m D x 1.45m H ) (OPC) | 26.4203 | 28.5624 | 31.9633
7122 | Printers and peripherals |  |  | -
7122A | Printer, Fax, Scanner | 2.2202 | 2.4002 | 2.686
7122B | Network Switch / Router/ Converters |  |  | -
7123 | ICSS Large Display |  |  | -
7123A | ICSS LARGE DISPLAY (Screen & Projector) | 23.9791 | 25.9233 | 29.01
7123B | ICSS LARGE DISPLAY (Approx 60" Display) |  |  | -
7150 | Cable Way |  |  | -
7151 | Cable Ladder - Galvanised Steel |  |  | -
7151A | 150mm Cable Ladder |  |  | -
7151B | 300mm Cable Ladder | 2.3405 | 2.5302 | 2.8315
7151C | 450mm Cable Ladder | 2.9932 | 3.2359 | 3.6212
7151D | 900mm Cable Ladder | 4.0099 | 4.3351 | 4.8512
7152 | Perforated Tray - Galvanised Steel |  |  | -
7152A | 100mm Perforated Tray | 1.6633 | 1.7981 | 2.0123
7152B | 150mm Perforated Tray | 1.9425 | 2.1 | 2.35
7152C | 300mm Perforated Tray |  |  | -
7160 | Cable |  |  | -
7161 | Plug-in Type Prefabricated System Cable |  |  | -
7161A | 10Pr or 20c and below |  |  | -
7161B | 20Pr or 40c | 6.4385 | 6.9605 | 7.7893
7162 | Hard wired Cable |  |  | -
7162A | 2-9 Cores | 7.6596 | 8.2806 | 9.2666
7162B | 10-20 Cores |  |  | -
7162C | 21-40 Cores | 14.6531 | 15.8412 | 17.7274
7162D | 41 Cores |  |  | -
7163 | FO Patch cord with connectors | 5.1064 | 5.5205 | 6.1778
7164 | Coaxial Cable | 5.1083 | 5.5224 | 6.18
7165 | Network (LAN) Cables | 5.1064 | 5.5204 | 6.1777
7170 | Cable Entry Sealing |  |  | -
7171 | Cable Transit |  |  | -
7171A | Cable Transit Frame |  |  | -
7171Ba | Transit Block with Cable | 0.33299 | 0.35999 | 0.40286
7171Bb | Transit Block Spare | 0.111 | 0.12 | 0.13429
7171C | Cable Gland | 1.2214 | 1.3205 | 1.4777
7300 | Local Instrument and/or Panel Installation |  |  | -
| Installation of field instruments and panels including:- |  |  | -
| · Collection from Contractor's warehouse, staging area or laydown/storage area; |  |  | -
| · Temporary storage as necessary; |  |  | -
| · Installation in accordance with supplied drawings and specifications; |  |  | -
| · Provision of all necessary construction material and consumables; |  |  | -
7310 | Local Instrument |  |  | -
7311 | Pipe Stanchion Mount Type Instrument |  |  | -
7311F | Flow Instruments |  |  | -
7311Fa | Instrument without Capillary Tube | 4.44 | 4.8 | 5.3715
7311Fb | Instrument with Capillary Tube |  |  | -
7311Fc | Flow Transmitter; Vortex (Remote) | 4.4408 | 4.8009 | 5.3725
7311Fd | Flow Transmitter; Ultrasonic (Remote) | 4.4404 | 4.8004 | 5.372
7311L | Level Instruments |  |  | -
7311La | Instrument without Capillary Tube | 4.4402 | 4.8003 | 5.3718
7311Lb | Instrument with Capillary Tube | 13.7646 | 14.8807 | 16.6525
7311P | Pressure Instruments |  |  | -
7311Pa | Instrument without Capillary Tube | 4.44 | 4.8 | 5.3715
7311Pb | Instrument with Capillary Tube |  |  | -
7311Pc | Differential Pressure Transmitter / Indicator | 4.4397 | 4.7997 | 5.3712
7311T | Temperature Instruments |  |  | -
7311Ta | Instrument without Capillary Tube | 4.4403 | 4.8004 | 5.372
7311Tb | Instrument with Capillary Tube |  |  | -
7311Tc | Temperature Transmitter / Indicator (Remote) | 4.4398 | 4.7998 | 5.3713
7311Td | Skin-mount Temperature Element |  |  | -
7311X | Other Instrument / Device |  |  | -
7311Xa | AFC Vibration SW |  |  | -
7311Xb | AFC CPMS (TIM) Acceler Meter w/Cable |  |  | -
7311Xc | AFC CPMS (TIM) TIM Housing |  |  | -
7311Xd | AFC CPMS (TIM) Pro-TIM-R |  |  | -
7311Xe | Hand Switch | 4.4407 | 4.8008 | 5.3724
7312 | Direct Mount Type Instrument | 1.7762 | 1.9202 | 2.1488
7313 | Bracket or Wall Mount Type Instrument |  |  | -
7315 | Fire and Gas Field Device |  |  | -
7315FD | IR Flame Detector | 6.6375 | 7.1757 | 8.0301
7315HD | Heat Detector | 5.2087 | 5.6311 | 6.3015
7315SD | Smoke Detector |  |  | -
7315MC | Manual Alarm Call Point (MAC) | 4.4401 | 4.8001 | 5.3716
7315TD | Low Temperature Spill Detector |  |  | -
7315GD | Flammable Gas Detector | 6.6374 | 7.1756 | 8.03
7315GL | Open Path type Flammable Gas Detector | 6.6375 | 7.1757 | 8.0301
7315GT | Toxic Gas Detector | 6.6377 | 7.1759 | 8.0304
7315GC | CO2 Gas Detector |  |  | -
7315FA | Fire Audible Alarm (Horn) |  |  | -
7315FB | Fire Alarm beacon | 9.9672 | 10.7753 | 12.0583
7315GA | Gas Audible Alarm (Horn) | 9.9689 | 10.7771 | 12.0604
7315GB | Gas Alarm Beacon | 9.9689 | 10.7771 | 12.0604
7319 | Other Mount type Instrument |  |  | -
7320 | Local Panel and Enclosure | 50.9452 | 55.0759 | 61.6338
7500 | Analyser Installation |  |  | -
| Installation of analyser and ancillaries including:- |  |  | -
| · Collection from Contractor's warehouse, staging area or laydown/storage area; |  |  | -
| · Temporary storage as necessary, |  |  | -
| · Installation in accordance with provided drawings and specifications |  |  | -
| · Provision of all necessary construction material and consumables; |  |  | -
7510 | Pipe Mount Type | 5.1354 | 5.5518 | 6.2129
7520 | Self-Standing Type |  |  | -
7521 | Loose Shipment Item assembly of Self-Standing Analyser | 35.9175 | 38.8297 | 43.4531
7522 | Self standing type – non-module | 41.1967 | 44.537 | 49.84
7530 | Analyser 3-Side Shelter | 149.196 | 161.293 | 180.498
7540 | Analyser House | 67.9821 | 73.4941 | 82.245
7550 | Sample Conditioning Rack | 19.1473 | 20.6997 | 23.1644
7800 | Cabling and Piping |  |  | -
| Installation of cable and instrument tubing in accordance with typical hook-up and standard drawings including:- |  |  | -
| · Collection from Contractor's warehouse, staging area or laydown/storage area; |  |  | -
| · Temporary storage as required; |  |  | -
| · Cable laying, fixing, dressing; |  |  | -
| · Installation work including brackets, supports etc; |  |  | -
| · Provision of all necessary construction material and consumables; |  |  | -
| · Routing of branch cabling; |  |  | -
7810 | Main Cable |  |  | -
7811 | Cable Way |  |  | -
7811A | Cable Ladder - Galvanised Steel |  |  | -
7811Aa | 150mm Cable Ladder | 1.6909 | 1.8281 | 2.0457
7811Ab | 300mm Cable Ladder | 2.3404 | 2.5301 | 2.8314
7811Ac | 450mm Cable Ladder | 2.9251 | 3.1623 | 3.5388
7811Ad | 600mm Cable Ladder | 3.5318 | 3.8182 | 4.2728
7811Ae | 900mm Cable Ladder | 4.0087 | 4.3337 | 4.8497
7811Af | 150mm Cable Ladder - Stainless Steel |  |  | -
7811Ag | 300mm Cable Ladder - Stainless Steel | 2.8585 | 3.0903 | 3.4582
7811Ah | 450mm Cable Ladder - Stainless Steel |  |  | -
7811Ai | 600mm Cable Ladder - Stainless Steel | 4.7299 | 5.1134 | 5.7222
7811Aj | 900mm Cable Ladder - Stainless Steel | 5.8874 | 6.3647 | 7.1226
7811B | Conduit Stub Up |  |  | -
7811Ba | Less than 100mm Diameter, 600 mm radius bend | 0.99903 | 1.08 | 1.2086
7811Bb | 100-150mm Diameter, 600 mm radius bend |  |  | -
7811C | Cable Ladder Cover |  |  | -
7811Ca | 150mm Cable Ladder |  |  | -
7811Cb | 300mm Cable Ladder | 0.6475 | 0.7 | 0.78335
7811Cc | 450mm Cable Ladder | 0.70307 | 0.76007 | 0.85058
7811Cd | 600mm Cable Ladder | 0.73631 | 0.79601 | 0.89079
7811Ce | 900mm Cable Ladder | 0.92492 | 0.99992 | 1.119
7811D | Removal and Reinstallation of MF Installed Ladder Cover |  |  | -
7811Da | 150mm Cable Ladder |  |  | -
7811Db | 300mm Cable Ladder | 0.92498 | 0.99998 | 1.119
7811Dc | 450mm Cable Ladder |  |  | -
7811Dd | 600mm Cable Ladder | 1.1027 | 1.1921 | 1.334
7811De | 900mm Cable Ladder | 1.48 | 1.6 | 1.7905
7812 | Cable Laying |  |  | -
7812A | Armoured Metal Cable |  |  | -
7812Aa | Cable |  |  | -
7812Aaa | 2-10 cores | 0.11877 | 0.1284 | 0.14369
7812Aab | 11-20 cores | 0.14097 | 0.1524 | 0.17055
7812Aac | 21-40 cores | 0.17427 | 0.1884 | 0.21083
7812Aad | 41 cores over | 0.25253 | 0.27301 | 0.30551
7812Ab | Cable(for when cable is installed and left coiled by other subcontractors) |  |  | -
7812Aba | 2-10 cores | 0.19647 | 0.21239 | 0.23768
7812Abb | 11-20 cores | 0.26306 | 0.28438 | 0.31825
7812Abc | 21-40 cores | 0.30746 | 0.33239 | 0.37197
7812Abd | 41 cores over | 0.45229 | 0.48897 | 0.54719
7812B | Non-armored Metal cable(not for when cable is installed and left coiled by other subcontractors) |  |  | -
7812Ba | 2-10 cores |  |  | -
7812Bb | 11-20 cores |  |  | -
7812Bc | 21-40 cores |  |  | -
7812Bd | 41 cores over |  |  | -
7812C | Armored Fibre Optic Cable |  |  | -
7812Ca | Cable |  |  | -
7812Caa | 2-6 Cores | 0.17231 | 0.18628 | 0.20846
7812Cab | 7 Cores and over | 0.20551 | 0.22217 | 0.24863
7812Cac | 24 Cores and over | 0.22771 | 0.24617 | 0.27548
7812Cad | 48 Cores and over | 0.27214 | 0.2942 | 0.32923
7812Cb | Cable(for when cable is installed and left coiled by other subcontractors) |  |  | -
7812Cba | 2-6 Cores |  |  | -
7812Cbb | 7-23 Cores |  |  | -
7812Cbc | 24 Cores | 0.37198 | 0.40214 | 0.45002
7812Cbd | 48 Cores | 0.4164 | 0.45016 | 0.50376
7812D | Non-armored Metal cable(not for when cable is installed and left coiled by other subcontractors) |  |  | -
7812Da | 2-6 Cores |  |  | -
7812Db | 7 Cores and over |  |  | -
7812Dc | 24 Cores and over |  |  | -
7812Dd | 48 Cores and over |  |  | -
7813 | Termination and Cable Gland Installation for Main Cable |  |  | -
7813A | Metal cable | 0.27749 | 0.29999 | 0.33571
7813B | Fibre Optic Cable | 0.55501 | 0.60001 | 0.67145
7813C | Cable gland installation |  |  | -
7813Ca | Compound Type Cable Gland | 2.6779 | 2.895 | 3.2397
7813Cb | Non-Compound Type Cable Gland | 2.0812 | 2.2499 | 2.5178
7815 | Junction Box |  |  | -
7815A | 40 Terminals or less | 6.9265 | 7.4881 | 8.3797
7815B | 41 to 80 Terminals | 8.8024 | 9.5161 | 10.6491
7815C | 81 Terminals and over |  |  | -
7820 | Branch Cable |  |  | -
7821 | Cable Way |  |  | -
7821A | Perforated Tray - Galvanised Steel / SS for D000 |  |  | -
7821Aa | 100mm CableTray | 2.34 | 2.5297 | 2.8309
7821Ab | 150mm Cable Tray | 2.6323 | 2.8457 | 3.1845
7821Ac | 300mm Cable Tray |  |  | -
7821Ad | 200mm Cable Tray | 3.1147 | 3.3673 | 3.7682
7821C | Perforated Angle - Galvanised Steel / SS for D000 (max. 50 x 50mm) | 1.0915 | 1.18 | 1.3205
7822 | Branch Cabling and Cable Gland Installation |  |  | -
7822A | Armoured Metel Cable (approx. 40m in length) | 5.4389 | 5.8799 | 6.58
7822B | Non-armored Metal cable (approx. 40m in length) |  |  | -
7822C | Armored Fiber Optic Cable (approx. 40m in length) |  |  | -
7822D | Non-armored Fiber Optic Cable (approx. 40m in length) |  |  | -
7822E | Cable gland installation |  |  | -
7822Ea | Compound Type Cable Gland | 1.4985 | 1.62 | 1.8129
7822Eb | Non-Compound Type Cable Gland | 1.221 | 1.32 | 1.4771
7830 | Impulse Tubing and Tracing |  |  | -
| Installation and assembly of instrument tubing in accordance with hook-up and standard drawings. Work includes:- |  |  | -
| · Collection of material from Contractor's warehouse, staging area or laydown/storage area, |  |  | -
| · Temporary storage as required, |  |  | -
| · Installation work including brackets, supports. |  |  | -
| · Provision of all necessary construction material and consumables. |  |  | -
7832 | Tubing |  |  | -
7832A | For Differential Pressure Instrument |  |  | -
7832Aa | Pedestal Mount Type (15m tubing) | 18.1531 | 19.625 | 21.9617
7832Ab | Line Mount Type (2m tubing) |  |  | -
7832B | Pressure Instrument (6m tubing) | 9.1128 | 9.8517 | 11.0247
7832C | Analyser Sample Line (60m tubing) | 67.7532 | 73.2467 | 81.9681
7832D | Other Sensing Line (6m tubing) | 9.1139 | 9.8529 | 11.0261
7833 | Pre-traced Bundle Tube |  |  | -
7833A | For Differential Pressure Instrument |  |  | -
7833Aa | Pedestal Mount Type (15m tubing) | 20.0009 | 21.6226 | 24.1971
7833Ab | Line Mount Type (2m tubing) |  |  | -
7833B | Pressure Instrument (6m tubing) | 11.2768 | 12.1911 | 13.6427
7833C | Analyser Sample Lines (60m tubing) | 76.4115 | 82.6071 | 92.443
7833D | Other Sensing Line (6m tubing) |  |  | -
7834 | Heat Tracing |  |  | -
7834B | Electrical heat Tracing |  |  | -
7834Ba | Differential Pressure Instrument (15m tubing) |  |  | -
7834Bb | Pressure Instrument (6m tubing) |  |  | -
7834Bc | Analyser Sample Line (60m tubing) |  |  | -
7834Bd | Other Sensing Line (6m tubing) |  |  | -
7840 | Air Piping and Tubing |  |  | -
7841 | Air Supply System |  |  | -
7841A | Tubing System | 12.9416 | 13.9909 | 15.6567
7841B | Manifold Header System |  |  | -
7841C | Air Supply Piping and tubing system | 47.9362 | 51.8229 | 57.9934
7842 | Pneumatic Signal Tubing |  |  | -
7842A | For Converter Signal (I/P, P/I) |  |  | -
7842B | For Transmitter/Controller Signal |  |  | -
7842C | For Fire Detection Signal |  |  | -
7850 | Support Fabrication |  |  | -
7851 | Stanchion |  |  | -
7851A | Pedestal Mount Type |  |  | -
7851Aa | DN50 x 1500mmL, sch40, CS |  |  | -
7851Ab | DN50 x 1700mmL, sch40, CS | 5.184 | 5.6044 | 6.2717
7851Ac | DN50 x 600mmL, sch40, CS |  |  | -
7851Ad | DN150 x 3000mmL, sch40, CS | 10.729 | 11.5989 | 12.98
7851B | Line Mount Type |  |  | -
7852 | Frame / Bracket |  |  | -
7852A | For Junction Box | 0.38849 | 0.41999 | 0.47
7852B | For Auxiliary Instrument |  |  | -
7853 | Cable Duct/Ladder support for Main Cable |  |  | -
7853A | Weight : under 5kg | 2.7751 | 3.0001 | 3.3574
7853B | Weight : 5 to 15kg | 5.8276 | 6.3001 | 7.0502
7853C | Weight : above 15kg | 6.938 | 7.5006 | 8.3937
7854 | Grating Penetrations (300mm X 300mm) | 3.4313 | 3.7095 | 4.1511
7860 | Miscellaneous Installation |  |  | -
7861 | Supply and Install Tag No. Plate / Labels |  |  | -
7861A | Name plate for instruments, Type A | 0.52309 | 0.5655 | 0.63283
7861B | Name plate for instruments, Type B | 0.31786 | 0.34363 | 0.38455
7863 | Polymeric Cable Protection Cover (to AS 4702) | 0.11101 | 0.12001 | 0.1343
7864 | Instrument Protection |  |  | -
7864A | Sun Shade | 1.769 | 1.9125 | 2.1402
7865 | Cable Route Marker | 1.1101 | 1.2001 | 1.343
7866 | Cable Marker (to AS/NZS 2648.1) | 0.11101 | 0.12001 | 0.1343
7867 | Excavation |  |  | -
7867A | Excavation of Cable Trench |  |  | -
7867Aa | Excavation of Cable Trench-under Building | 5.9945 | 6.4805 | 7.2521
7867Ab | Excavation of Cable Trench-not under Building | 2.0778 | 2.2463 | 2.5138
7867C | Manual Excavation of buried coiled cables | 7.2988 | 7.8906 | 8.8301
7868 | Back Filling |  |  | -
7868A | Back filling by Soil | 0.93234 | 1.0079 | 1.1279
7868B | Sand Filling |  |  | -
7868Ba | Sand Filling-under Building | 2.1447 | 2.3186 | 2.5947
7868Bb | Sand Filling-not under Building | 1.0955 | 1.1844 | 1.3254
7868C | Disposal | 0.27974 | 0.30242 | 0.33843
7869 | Minor Foundations |  |  | -
7869A | Minor Foundations Less Than 0.05M3 | 1.1101 | 1.2001 | 1.343
7869B | Minor Foundations 0.05 to 0.15M3 | 3.3297 | 3.5997 | 4.0283
7870 | Support for Piping Flushing Activities |  |  | -
7871 | Cable Removal/Re-installation | 2.553 | 2.76 | 3.0886
7872 | Air Supply Removal/Re-installation | 2.664 | 2.88 | 3.2229
7900 | Inspections, Precommissioning Checks and Function Testing |  |  | -
7920 | Function Testing |  |  | -
7920AA | JC01 – INSTRUMENT PANEL, ENERGISATION | 6.66 | 7.2 | 8.0573
7920AB | JC02 – SERIAL LINK | 2.2201 | 2.4001 | 2.6859
7920AC | JC03 – ACTUATED VALVE, MODULATING | 4.44 | 4.8 | 5.3716
7920AD | JC04 – ACTUATED VALVE, SWITCHING (ON/OFF) | 4.4398 | 4.7997 | 5.3712
7920AE | JC05 – DAMPER | 3.3298 | 3.5998 | 4.0284
7920AF | JC06 – TRANSMITTER | 3.3299 | 3.5999 | 4.0285
7920AG | JC07 – ANALOG OUTPUT | 3.3301 | 3.6001 | 4.0288
7920AH | JC08 – REMOTE INDICATOR | 3.3302 | 3.6002 | 4.0289
7920AI | JC09 – DISCRETE INPUT | 3.3301 | 3.6001 | 4.0288
7920AJ | JC10 – DISCRETE OUTPUT | 3.33 | 3.6 | 4.0287
7920AK | JC11 – ANALYSER / COMPLEX INSTRUMENT | 11.1004 | 12.0004 | 13.4293
7920AL | JC12 – PUSHBUTTON | 3.3302 | 3.6002 | 4.0288
7920AM | JC13 – GAS / FLAME DETECTOR | 3.3299 | 3.5999 | 4.0286
7920AN | JC14 – SMOKE / HEAT DETECTOR (Not Used) |  |  | -
7920AO | JC15 – MCC / ICSS Signals | 3.3299 | 3.5998 | 4.0285
7920AP | JC16 – MOV | 3.3304 | 3.6004 | 4.0291
7920AQ | JC17 – CONDITION AND PERFORMANCE MONITORING SYSTEM | 3.3298 | 3.5998 | 4.0284
7920AR | JC18 – TRENDMASTER SYSTEM - ACCELEROMETER | 3.3297 | 3.5997 | 4.0283
7930 | Precommissioning Checks |  |  | -
7930AAA | XP01 - Hazardous Area - Consolidated | 4.4398 | 4.7998 | 5.3713
7930AAB | XP03 - Hazardous Area - Site | 4.4401 | 4.8001 | 5.3716
7930AB | JP01 - Miscellaneous Equipment |  |  | -
7930AC | JP02 - Caliabration | 4.4402 | 4.8003 | 5.3718
7930ACA | JP02 - Calibration - Pressure / Temperature Gauge | 4.4404 | 4.8004 | 5.372
7930ACB | JP02 - Calibration - Transmitters | 4.44 | 4.8 | 5.3716
7930ACC | JP02 - Calibration - Pressure / Temperature Switch |  |  | -
7930ACD | JP02 - Calibration - Control Valve | 4.4403 | 4.8003 | 5.3719
7930ACE | JP02 - Calibration - On-Off Valve | 4.4403 | 4.8004 | 5.3719
7930AD | JP03 - Local Gauge | 1.1099 | 1.1999 | 1.3428
7930AE | JP04 - Instrument Installation | 1.11 | 1.2 | 1.3429
7930AF | JP05 - Bursting Disk |  |  | -
7930AG | JP06 - Actuated Valve Assembly | 2.2201 | 2.4001 | 2.6859
7930AH | JP07 - Temperatuere Element | 1.11 | 1.2 | 1.3429
7930AI | JP08 - Instrument Installation On Skid |  |  | -
7930AJ | JP09 - Control Panel/Console | 6.6605 | 7.2006 | 8.0579
7930AK | JP10 - Junction Box | 1.11 | 1.2 | 1.3428
7930AL | JP11 - Instrument Cable | 1.11 | 1.2 | 1.3428
7930AM | JP12 - Annunciator Panel |  |  | -
7930AN | JP13 - Fire and Gas Device | 1.11 | 1.2 | 1.3428
7930AO | JP14 - Frangible Bulb/Pneumatic Detection and Deluge System | 2.2201 | 2.4001 | 2.6859
7930AP | JP15 - Earthing System | 4.4403 | 4.8004 | 5.3719
7930AQ | JP16 - Flow Orifice |  |  | -
7930AR | JP17 - Relief Valve |  |  | -
7930AS | JP18 - Instrument Tubing Cleaning and Testing | 1.11 | 1.2 | 1.3429
7930AT | JP19 - CAT 6 Cable | 6.6605 | 7.2006 | 8.0579
7930AU | JP20 - CAT6A Cable | 6.6605 | 7.2006 | 8.0579
7930AV | JP21 - Fibre Optic Cable | 6.6603 | 7.2003 | 8.0577
7930AW | JP22 - Earth Bar |  |  | -

## FWBS activities
List of FWBS Activities
7110 - Panel, Rack and Cabinet
7120 - Control Systems / Computer System
7150 - Cable Way
7160 - Cable
7170 - Cable Entry Sealing
7310 - Local Instrument
7320 - Local Panel and Enclosure
7510 - Pipe Mount Type
7520 - Self-Standing Type
7530 - Analyser 3-Side Shelter
7540 - Analyser House
7550 - Sample Conditioning Rack
7811 - Cable Way
7812 - Cable Laying
7813 - Termination and Cable Gland Installation for Main Cable
7815 - Junction Box
7821 - Cable Way
7822 - Branch Cabling and Cable Gland Installation
7830 - Impulse Tubing and Tracing
7840 - Air Piping and Tubing
7850 - Support Fabrication
7861 - Supply and Install Tag No. Plate / Labels
7863 - Polymeric Cable Protection Cover (to AS 4702)
7864 - Instrument Protection
7865 - Cable Route Marker
7866 - Cable Marker (to AS/NZS 2648.1)
7867 - Excavation
7868 - Backfilling
7869 - Minor Foundations
7870 - Support For Piping Flushing Activities
7920 - Function Testing
7930 - Precommissioning Checks
8110 - Generator & Associated Equipment
8120 - Transformer, Harmonic Filter and Neutral Earthing Resistor
8130 - Gas Insulated Switchgear (GIS) installed inside LER by Module Fabricator
8140 - SWITCHGEAR AND MCC
8150 - UPS system
8160 - Bus Duct
8170 - Control, Distribution & Misc Panels
8180 - Power Distribution Control System (PDCS)
8191 - LER Receipt
8192 - LIR Receipt
8220 - Local Equipment (Outside)
8260 - Power and Control Cabling
8271 - Termination of Cable (including Compound Filled Gland)
8272 - Termination of Cables (including Non Compound Filled Gland)
8273 - Splicing of cable
8280 - Cable Way
8295A - Excavation
8295B - Sand Filling
8295C - Back Filling
8295D - Polymeric Cable Protection Cover (to AS 4702)
8295E - Cable Marker (to AS/NZS 2648.1)
8295F - Stub-up PVC conduit
8295G - Disposal
8296 - Cable Route Markers
8297 - Minor Foundations
8298 - Fabrication of Supports For Cableway and Cable Supports
8299 - Installation of Miscellaneous Supports
8320 - Lighting in Plant
8330 - Street, Fence, Security
8340 - Aircraft Obstacle Light
8350 - Navigation Light
8395A - Excavation
8395B - Sand Filling
8395C - Back Filling
8395D - Polymeric Cable Protection CoverTile (to AS 4702)
8395E - Cable Warning Marker Sheet (to AS/NZS 2648.1)
8395F - Disposal
8396 - Cable Route Marker
8410 - Wiring of Earthing
8420 - Earthing Electrode
8430 - Connection to Equipment
8440 - Air Terminal
8490 - Other Work
8610 - Wired System
8620 - Wireless System
8630 - LAN/WAN & Data Communication System
8640 - Other Communication System
8650 - Nurse Call /Distress System
8660 - Cabling
8670 - Termination/Splicing of Cable
8680 - Cable Way
8695A - Excavation of Cable Trench
8695B - Manual Excavation of buried coiled cables
8695C - Sand Filling
8695E - Back Filling
8695F - Polymeric Cable Protection CoverTile (to AS 4702)
8695G - Cable Warning Marker Sheet (to AS/NZS 2648.1)
8695H - Disposal
8696 - Cable Route Marker
8697 - Pole and Mast
8710 - Impressed current cathodic protection
8720 - Sacrificial Anode System
8793 - Soil Access Box
8795Aa - Excavation
8795Ab - Manual Excavation of buried coiled cables
8795B - Sand Filling
8795C - Back Filling
8795D - Cable Protection Tile
8795E - Cable Warning Sheet (Polymeric cable tile)
8796 - Cable Route Marker
8810 - Heater Panel
8820 - Heating Element
8860 - Cabling - Low Voltage
8870 - Termination
8910 - Precommissioning Checks
8920 - Function Testing
FMIT - QAQC Field Material Inspections & Testing
Bill No. 4 - ELE-1 Preservation Tabulation
Bill No. 5 - ELE-1 Commissioning Support Tabulation
IPCQ - Minor Subcontract Works
CBI - Minor Subcontract Works
KAEFER - Minor Subcontract Works
MEC-1 - Minor Subcontract Works
Maintenance crew for plant and electrics
Driver / operators for sundry plant and equipment
Training
Material Control / Stores Personnel
Peggys
Site Facilities & Services
SI #
EV #

## Constraint 1 Code Reporting
[9 empty] | List of Constraint Codes |  | PCWBS Codes | FWBS Codes
[9 empty] | Code | Type of Constraint - Daily Timesheet Reporting (DRS) | A100 | 7000
[9 empty] | S1 | Wet Weather / Lightning Stoppages | A200 | 7100
[9 empty] | S2 | Permit Not Available (Be Specific) | A300 | 7300
CONSTRAINT DETAILS | [8 empty] | S3 | Scaffolding Not Available (Refer to and Attach Specific Scaff Request) | B400 | 7700
[9 empty] | S4 | Free Issue Materials Not Available (Refer to and Attach Specific CMIV) | B500 | 7800
CONTACT INFORMATION: | [8 empty] | S5 | Unnamed Cyclone (Tie down and clean up)(BEFORE/AFTER Red Alert Event) | B600 | 7900
Raised By: | Ref No.: | [7 empty] | S6 | Priority given to other Contractors / Redirection by JKC/others (Instructed to cease work and relocate resources) E.G. Hydrotesting in the area, lifting operations in the area etc. | C100 | 8000
[9 empty] | S7 | Cranage Not Available (Beyond Kentz obligation(<50T))
Superintendent Details: | Date Raised: | [7 empty] | S8 | Waiting on Client QA/QC (For Hold Points Only, Refer to and Attach Specific RFI) | C200 | 8100
[9 empty] | S9 | Vendor Service Person Not Available | C600 | 8800
WILL THE MATTER REFERRED TO BELOW POTENTIALLY: (PLEASE CHECK BOX) | PCWBS Code: | [7 empty] | S10 | High Winds | C700 | 8900
[9 empty] | S11 | Stop Work Authority Enacted | D100 | Temps
Constraint Type: | Crew | [7 empty] | S12 | Crew Stand Down - Compassionate | E300
[9 empty] | S13 | Emergency Evacuation / Drill (JKC or Kentz) | E400
Increase Cost | [8 empty] | S14 | SIMOPS with Commissioning (Specific instances where works are impacted and Kentz Construction are required to cease and relocate resources) | E500
[9 empty] | S15 | Kentz Rework | E600
Delay Completion/Progress: | [8 empty] | S16 | Communications Drop Out (E.g. Cable Pulling Work Temp. Suspended) | OFFSITE
[9 empty] | S17 | Downtime for rehydration breaks | SITEWIDE
Disruption to Normal Operations | [8 empty] | S18 | Spare
[9 empty] | S19 | Plant/Equipment Breakdowns (unforseen)
DESCRIPTION OF CONSTRAINT: | [8 empty] | S20 | Spare
(E.g Include details on time constraint commenced and finished, who gave a direction, what happened or what led to the occurrence of the constraint. | [8 empty] | S21 | Spare
If constraint is relating to unavailability of permits, scaffolding, FI materials, QA/QC inspections etc please attach details of Kentz advance requests) | [8 empty] | S22 | Spare
Description of First Occourance for Constraint Type Identified Above | [8 empty] | S23 | Spare
| FWBS | Hrs | FWBS | Hrs | FWBS | Hrs | FWBS | Hrs | S24 | Spare
[9 empty] | P1 | Disruption to Works caused by Client and/or Other Subcontractor (Note: We can continue to work in this instance)
[9 empty] | P2 | Spare
| Cumulative Hours for Constraint 1 | [7 empty] | P3 | Spare
Description of Second Occourance for Constraint Type Identified Above | [8 empty] | P4 | Spare
| FWBS | Hrs | FWBS | Hrs | FWBS | Hrs | FWBS | Hrs | P5 | Spare
[9 empty] | K1 | Plant/Equipment Breakdowns (unforseen)
[9 empty] | K2 | Material Not Available
| Cumulative Hours for Constraint2 | [7 empty] | K3 | Equipment Unavailable
Description of Third Occourance for Constraint Type Identified Above | [8 empty] | K4 | Transport Unavailable
| FWBS | Hrs | FWBS | Hrs | FWBS | Hrs | FWBS | Hrs | K5 | QA/QC Not Available for inspections
[9 empty] | K6 | Spare
[9 empty] | K7 | Spare
[9 empty] | K8 | Spare
| Cumulative Hours for Constraint 3 | [7 empty] | K9 | Spare
Description of Fourth Occourance for Constraint Type Identified Above | [8 empty] | K10 | Spare
| FWBS | Hrs | FWBS | Hrs | FWBS | Hrs | FWBS | Hrs
Cumulative Hours for Constraint 4
Description of Fifth Occourance for Constraint Type Identified Above
| FWBS | Hrs | FWBS | Hrs | FWBS | Hrs | FWBS | Hrs
Cumulative Hours for Constraint 5
Description of Sixth Occourance for Constraint Type Identified Above
| FWBS | Hrs | FWBS | Hrs | FWBS | Hrs | FWBS | Hrs
Cumulative Hours for Constraint 6
DESCRIPTION OF ANY ACTIONS TAKEN TO MINIMISE IMPACT OF CONSTRAINT:
ACTION OWNER:
ACTION REQUIRED BY:
(Fill in the above if there is a specific action required to remove the constraint)
ATTACHMENTS:
Double-click to Add Image

## Constraint 2 Code Reporting
[6 empty] | List of Constraint Codes |  | PCWBS Codes | FWBS Codes
[6 empty] | Code | Type of Constraint - Daily Timesheet Reporting (DRS) | A100 | 7000
[6 empty] | S1 | Wet Weather / Lightning Stoppages | A200 | 7100
[6 empty] | S2 | Permit Not Available (Be Specific) | A300 | 7300
[6 empty] | S3 | Scaffolding Not Available (Refer to and Attach Specific Scaff Request) | B100 | 7400
[6 empty] | S4 | Free Issue Materials Not Available (Refer to and Attach Specific CMIV) | B300 | 7500
CONSTRAINT DETAILS | [5 empty] | S5 | Unnamed Cyclone (Tie down and clean up)(BEFORE/AFTER Red Alert Event) | B400 | 7700
[6 empty] | S6 | Priority given to other Contractors / Redirection by JKC/others (Instructed to cease work and relocate resources) E.G. Hydrotesting in the area, lifting operations in the area etc. | B500 | 7800
CONTACT INFORMATION: | [5 empty] | S7 | Cranage Not Available (Beyond Kentz obligation(<50T)) | B600 | 7900
Raised By: | d |  | Date Raised: | Ref No.: | (Area No./Supervisor/0001) | S8 | Waiting on Client QA/QC (For Hold Points Only, Refer to and Attach Specific RFI) | C100 | 8000
Superintendent Details: | [5 empty] | S9 | Vendor Service Person Not Available | C200 | 8100
[6 empty] | S10 | High Winds | C300 | 8200
PROJECT CONTROL CODES: | [5 empty] | S11 | Stop Work Authority Enacted | C400 | 8300
FWBS Code: | [5 empty] | S12 | Crew Stand Down - Compassionate | C500 | 8400
[6 empty] | S13 | Emergency Evacuation / Drill (JKC or Kentz) | C600 | 8600
PCWBS Code: | [5 empty] | S14 | SIMOPS with Commissioning (Specific instances where works are impacted and Kentz Construction are required to cease and relocate resources) | C700 | 8700
[6 empty] | S15 | Kentz Rework | D100 | 8800
Constraint Type: | [5 empty] | S16 | Communications Drop Out (E.g. Cable Pulling Work Temp. Suspended) | D200 | 8900
[6 empty] | S17 | Downtime for rehydration breaks | E000
[6 empty] | S18 | Spare | E100
WILL THE MATTER REFERRED TO BELOW POTENTIALLY: (PLEASE CHECK BOX) | [5 empty] | S19 | Spare | E300
[6 empty] | S20 | Spare | E400
Increase Cost | [7 empty] | E500
[6 empty] | P1 | Disruption to Works caused by Client and/or Other Subcontractor (Note: We can continue to work in this instance) | E600
Delay Completion/Progress: | [5 empty] | P2 | Spare | OFFSITE
[6 empty] | P3 | Spare | SITEWIDE
Cause Disruption to Normal Operations | [5 empty] | P4 | Spare
[6 empty] | P5 | Spare
DESCRIPTION OF CONSTRAINT:
(E.g Include details on time constraint commenced and finished, who gave a direction, what happened or what led to the occurrence of the constraint.
If constraint is relating to unavailability of permits, scaffolding, FI materials, QA/QC inspections etc please attach details of Kentz advance requests)
DESCRIPTION OF ACTIONS TAKEN TO MINIMISE IMPACT OF CONSTRAINT:
ACTION OWNER:
ACTION REQUIRED BY:
(Fill in the above if there is a specific action required to remove the constraint)
ATTACHMENTS:
Double-click to Add Image

## Constraint 3 Code Reporting
[6 empty] | List of Constraint Codes |  | PCWBS Codes | FWBS Codes
[6 empty] | Code | Type of Constraint - Daily Timesheet Reporting (DRS) | A100 | 7000
[6 empty] | S1 | Wet Weather / Lightning Stoppages | A200 | 7100
[6 empty] | S2 | Permit Not Available (Be Specific) | A300 | 7300
[6 empty] | S3 | Scaffolding Not Available (Refer to and Attach Specific Scaff Request) | B100 | 7400
[6 empty] | S4 | Free Issue Materials Not Available (Refer to and Attach Specific CMIV) | B300 | 7500
CONSTRAINT DETAILS | [5 empty] | S5 | Unnamed Cyclone (Tie down and clean up)(BEFORE/AFTER Red Alert Event) | B400 | 7700
[6 empty] | S6 | Priority given to other Contractors / Redirection by JKC/others (Instructed to cease work and relocate resources) E.G. Hydrotesting in the area, lifting operations in the area etc. | B500 | 7800
CONTACT INFORMATION: | [5 empty] | S7 | Cranage Not Available (Beyond Kentz obligation(<50T)) | B600 | 7900
Raised By: | d |  | Date Raised: | Ref No.: | (Area No./Supervisor/0001) | S8 | Waiting on Client QA/QC (For Hold Points Only, Refer to and Attach Specific RFI) | C100 | 8000
Superintendent Details: | [5 empty] | S9 | Vendor Service Person Not Available | C200 | 8100
[6 empty] | S10 | High Winds | C300 | 8200
PROJECT CONTROL CODES: | [5 empty] | S11 | Stop Work Authority Enacted | C400 | 8300
FWBS Code: | [5 empty] | S12 | Crew Stand Down - Compassionate | C500 | 8400
[6 empty] | S13 | Emergency Evacuation / Drill (JKC or Kentz) | C600 | 8600
PCWBS Code: | [5 empty] | S14 | SIMOPS with Commissioning (Specific instances where works are impacted and Kentz Construction are required to cease and relocate resources) | C700 | 8700
[6 empty] | S15 | Kentz Rework | D100 | 8800
Constraint Type: | [5 empty] | S16 | Communications Drop Out (E.g. Cable Pulling Work Temp. Suspended) | D200 | 8900
[6 empty] | S17 | Downtime for rehydration breaks | E000
[6 empty] | S18 | Spare | E100
WILL THE MATTER REFERRED TO BELOW POTENTIALLY: (PLEASE CHECK BOX) | [5 empty] | S19 | Spare | E300
[6 empty] | S20 | Spare | E400
Increase Cost | [7 empty] | E500
[6 empty] | P1 | Disruption to Works caused by Client and/or Other Subcontractor (Note: We can continue to work in this instance) | E600
Delay Completion/Progress: | [5 empty] | P2 | Spare | OFFSITE
[6 empty] | P3 | Spare | SITEWIDE
Cause Disruption to Normal Operations | [5 empty] | P4 | Spare
[6 empty] | P5 | Spare
DESCRIPTION OF CONSTRAINT:
(E.g Include details on time constraint commenced and finished, who gave a direction, what happened or what led to the occurrence of the constraint.
If constraint is relating to unavailability of permits, scaffolding, FI materials, QA/QC inspections etc please attach details of Kentz advance requests)
DESCRIPTION OF ACTIONS TAKEN TO MINIMISE IMPACT OF CONSTRAINT:
ACTION OWNER:
ACTION REQUIRED BY:
(Fill in the above if there is a specific action required to remove the constraint)
ATTACHMENTS:
Double-click to Add Image

## Constraint 4 Code Reporting
[6 empty] | List of Constraint Codes |  | PCWBS Codes | FWBS Codes
[6 empty] | Code | Type of Constraint - Daily Timesheet Reporting (DRS) | A100 | 7000
[6 empty] | S1 | Wet Weather / Lightning Stoppages | A200 | 7100
[6 empty] | S2 | Permit Not Available (Be Specific) | A300 | 7300
[6 empty] | S3 | Scaffolding Not Available (Refer to and Attach Specific Scaff Request) | B100 | 7400
[6 empty] | S4 | Free Issue Materials Not Available (Refer to and Attach Specific CMIV) | B300 | 7500
CONSTRAINT DETAILS | [5 empty] | S5 | Unnamed Cyclone (Tie down and clean up)(BEFORE/AFTER Red Alert Event) | B400 | 7700
[6 empty] | S6 | Priority given to other Contractors / Redirection by JKC/others (Instructed to cease work and relocate resources) E.G. Hydrotesting in the area, lifting operations in the area etc. | B500 | 7800
CONTACT INFORMATION: | [5 empty] | S7 | Cranage Not Available (Beyond Kentz obligation(<50T)) | B600 | 7900
Raised By: | d |  | Date Raised: | Ref No.: | (Area No./Supervisor/0001) | S8 | Waiting on Client QA/QC (For Hold Points Only, Refer to and Attach Specific RFI) | C100 | 8000
Superintendent Details: | [5 empty] | S9 | Vendor Service Person Not Available | C200 | 8100
[6 empty] | S10 | High Winds | C300 | 8200
PROJECT CONTROL CODES: | [5 empty] | S11 | Stop Work Authority Enacted | C400 | 8300
FWBS Code: | [5 empty] | S12 | Crew Stand Down - Compassionate | C500 | 8400
[6 empty] | S13 | Emergency Evacuation / Drill (JKC or Kentz) | C600 | 8600
PCWBS Code: | [5 empty] | S14 | SIMOPS with Commissioning (Specific instances where works are impacted and Kentz Construction are required to cease and relocate resources) | C700 | 8700
[6 empty] | S15 | Kentz Rework | D100 | 8800
Constraint Type: | [5 empty] | S16 | Communications Drop Out (E.g. Cable Pulling Work Temp. Suspended) | D200 | 8900
[6 empty] | S17 | Downtime for rehydration breaks | E000
[6 empty] | S18 | Spare | E100
WILL THE MATTER REFERRED TO BELOW POTENTIALLY: (PLEASE CHECK BOX) | [5 empty] | S19 | Spare | E300
[6 empty] | S20 | Spare | E400
Increase Cost | [7 empty] | E500
[6 empty] | P1 | Disruption to Works caused by Client and/or Other Subcontractor (Note: We can continue to work in this instance) | E600
Delay Completion/Progress: | [5 empty] | P2 | Spare | OFFSITE
[6 empty] | P3 | Spare | SITEWIDE
Cause Disruption to Normal Operations | [5 empty] | P4 | Spare
[6 empty] | P5 | Spare
DESCRIPTION OF CONSTRAINT:
(E.g Include details on time constraint commenced and finished, who gave a direction, what happened or what led to the occurrence of the constraint.
If constraint is relating to unavailability of permits, scaffolding, FI materials, QA/QC inspections etc please attach details of Kentz advance requests)
DESCRIPTION OF ACTIONS TAKEN TO MINIMISE IMPACT OF CONSTRAINT:
ACTION OWNER:
ACTION REQUIRED BY:
(Fill in the above if there is a specific action required to remove the constraint)
ATTACHMENTS:
Double-click to Add Image

## Constraint 5 Code Reporting
[6 empty] | List of Constraint Codes |  | PCWBS Codes | FWBS Codes
[6 empty] | Code | Type of Constraint - Daily Timesheet Reporting (DRS) | A100 | 7000
[6 empty] | S1 | Wet Weather / Lightning Stoppages | A200 | 7100
[6 empty] | S2 | Permit Not Available (Be Specific) | A300 | 7300
[6 empty] | S3 | Scaffolding Not Available (Refer to and Attach Specific Scaff Request) | B100 | 7400
[6 empty] | S4 | Free Issue Materials Not Available (Refer to and Attach Specific CMIV) | B300 | 7500
CONSTRAINT DETAILS | [5 empty] | S5 | Unnamed Cyclone (Tie down and clean up)(BEFORE/AFTER Red Alert Event) | B400 | 7700
[6 empty] | S6 | Priority given to other Contractors / Redirection by JKC/others (Instructed to cease work and relocate resources) E.G. Hydrotesting in the area, lifting operations in the area etc. | B500 | 7800
CONTACT INFORMATION: | [5 empty] | S7 | Cranage Not Available (Beyond Kentz obligation(<50T)) | B600 | 7900
Raised By: | d |  | Date Raised: | Ref No.: | (Area No./Supervisor/0001) | S8 | Waiting on Client QA/QC (For Hold Points Only, Refer to and Attach Specific RFI) | C100 | 8000
Superintendent Details: | [5 empty] | S9 | Vendor Service Person Not Available | C200 | 8100
[6 empty] | S10 | High Winds | C300 | 8200
PROJECT CONTROL CODES: | [5 empty] | S11 | Stop Work Authority Enacted | C400 | 8300
FWBS Code: | [5 empty] | S12 | Crew Stand Down - Compassionate | C500 | 8400
[6 empty] | S13 | Emergency Evacuation / Drill (JKC or Kentz) | C600 | 8600
PCWBS Code: | [5 empty] | S14 | SIMOPS with Commissioning (Specific instances where works are impacted and Kentz Construction are required to cease and relocate resources) | C700 | 8700
[6 empty] | S15 | Kentz Rework | D100 | 8800
Constraint Type: | [5 empty] | S16 | Communications Drop Out (E.g. Cable Pulling Work Temp. Suspended) | D200 | 8900
[6 empty] | S17 | Downtime for rehydration breaks | E000
[6 empty] | S18 | Spare | E100
WILL THE MATTER REFERRED TO BELOW POTENTIALLY: (PLEASE CHECK BOX) | [5 empty] | S19 | Spare | E300
[6 empty] | S20 | Spare | E400
Increase Cost | [7 empty] | E500
[6 empty] | P1 | Disruption to Works caused by Client and/or Other Subcontractor (Note: We can continue to work in this instance) | E600
Delay Completion/Progress: | [5 empty] | P2 | Spare | OFFSITE
[6 empty] | P3 | Spare | SITEWIDE
Cause Disruption to Normal Operations | [5 empty] | P4 | Spare
[6 empty] | P5 | Spare
DESCRIPTION OF CONSTRAINT:
(E.g Include details on time constraint commenced and finished, who gave a direction, what happened or what led to the occurrence of the constraint.
If constraint is relating to unavailability of permits, scaffolding, FI materials, QA/QC inspections etc please attach details of Kentz advance requests)
DESCRIPTION OF ACTIONS TAKEN TO MINIMISE IMPACT OF CONSTRAINT:
ACTION OWNER:
ACTION REQUIRED BY:
(Fill in the above if there is a specific action required to remove the constraint)
ATTACHMENTS:
Double-click to Add Image

## Constraint 6 Code Reporting
[6 empty] | List of Constraint Codes |  | PCWBS Codes | FWBS Codes
[6 empty] | Code | Type of Constraint - Daily Timesheet Reporting (DRS) | A100 | 7000
[6 empty] | S1 | Wet Weather / Lightning Stoppages | A200 | 7100
[6 empty] | S2 | Permit Not Available (Be Specific) | A300 | 7300
[6 empty] | S3 | Scaffolding Not Available (Refer to and Attach Specific Scaff Request) | B100 | 7400
[6 empty] | S4 | Free Issue Materials Not Available (Refer to and Attach Specific CMIV) | B300 | 7500
CONSTRAINT DETAILS | [5 empty] | S5 | Unnamed Cyclone (Tie down and clean up)(BEFORE/AFTER Red Alert Event) | B400 | 7700
[6 empty] | S6 | Priority given to other Contractors / Redirection by JKC/others (Instructed to cease work and relocate resources) E.G. Hydrotesting in the area, lifting operations in the area etc. | B500 | 7800
CONTACT INFORMATION: | [5 empty] | S7 | Cranage Not Available (Beyond Kentz obligation(<50T)) | B600 | 7900
Raised By: | d |  | Date Raised: | Ref No.: | (Area No./Supervisor/0001) | S8 | Waiting on Client QA/QC (For Hold Points Only, Refer to and Attach Specific RFI) | C100 | 8000
Superintendent Details: | [5 empty] | S9 | Vendor Service Person Not Available | C200 | 8100
[6 empty] | S10 | High Winds | C300 | 8200
PROJECT CONTROL CODES: | [5 empty] | S11 | Stop Work Authority Enacted | C400 | 8300
FWBS Code: | [5 empty] | S12 | Crew Stand Down - Compassionate | C500 | 8400
[6 empty] | S13 | Emergency Evacuation / Drill (JKC or Kentz) | C600 | 8600
PCWBS Code: | [5 empty] | S14 | SIMOPS with Commissioning (Specific instances where works are impacted and Kentz Construction are required to cease and relocate resources) | C700 | 8700
[6 empty] | S15 | Kentz Rework | D100 | 8800
Constraint Type: | [5 empty] | S16 | Communications Drop Out (E.g. Cable Pulling Work Temp. Suspended) | D200 | 8900
[6 empty] | S17 | Downtime for rehydration breaks | E000
[6 empty] | S18 | Spare | E100
WILL THE MATTER REFERRED TO BELOW POTENTIALLY: (PLEASE CHECK BOX) | [5 empty] | S19 | Spare | E300
[6 empty] | S20 | Spare | E400
Increase Cost | [7 empty] | E500
[6 empty] | P1 | Disruption to Works caused by Client and/or Other Subcontractor (Note: We can continue to work in this instance) | E600
Delay Completion/Progress: | [5 empty] | P2 | Spare | OFFSITE
[6 empty] | P3 | Spare | SITEWIDE
Cause Disruption to Normal Operations | [5 empty] | P4 | Spare
[6 empty] | P5 | Spare
DESCRIPTION OF CONSTRAINT:
(E.g Include details on time constraint commenced and finished, who gave a direction, what happened or what led to the occurrence of the constraint.
If constraint is relating to unavailability of permits, scaffolding, FI materials, QA/QC inspections etc please attach details of Kentz advance requests)
DESCRIPTION OF ACTIONS TAKEN TO MINIMISE IMPACT OF CONSTRAINT:
ACTION OWNER:
ACTION REQUIRED BY:
(Fill in the above if there is a specific action required to remove the constraint)
ATTACHMENTS:
Double-click to Add Image